## Requirements
Initial drafting | [8 empty] | CRV review process (by reviewers) |  |  |  | Feedback from Request for information |  | Final review (during CRV TF/4)
Number | Reference (generated by Excel) | Category | Technical (T) - Service (S) - General (G) | Requirement (R) - Optional Requirement (OR) - Information statement (I) | Wording of Information Statement or Requirement | Note | External reference (annex, attachment, etc) | Requirements to be included in Terms and Conditions/Instructions to tenderers/Specification / SOW / IRS? | Questions / Comments | Reply / Comments | Status of wording (draft/final) | Is published in RFI (yes/no) | Feasibility assessment (OK/Partial/NOK) | Amendment needed after RFI? | Final Wording (or: No change) | Note | Operational Requirement from CONOPS (Cross reference) | Requirements to be included in Terms and Conditions/Instructions to tenderers/Specification / SOW / IRS?
10 | 10-ATFM Data-T-R | ATFM Data | T | R | The throughput of ATFM data flow shall be configurable in order to support different ATFM operation phase (e.g. Strategic, Pre-tactical, tactical). |  | Doc 9971 Manual on Collaborative ATFM - 2nd Edition | Specification | Througput requireed should be defined |  | draft | no
20 | 20-ATFM Data-T-R | ATFM Data | T | R | The QoS of ATFM data flow shall be configurable in order to support different ATFM operation phases (e.g. Strategic, Pre-tactical, tactical). |  |  | Specification | QoS of ATFM should be mapped and not left open |  | draft | no
XX | XX-ATFM Data-T-OR | ATFM Data | T | OR | In the future, CRV parties may also include not only ANSPs but also other ATFM stakeholders such as airspace user (AU), airport operator (AOP), etc. The CRV network should therefore support also the connection between all ATFM stakeholders. |  |  | SOW | Impact on DOA - to take into account |  | draft | no
XX | XX-ATFM Data-T-I | ATFM Data | T | I | During the Strategic phase (more than one day in advance of flight operation upto approximately 2 months), CRV parties may exchange flight schedules/cancellation/substitution data with each other. |  |  | Specification |  |  | draft | no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | The CRV networks shall support the exchange of flight schedules/cancellation/substitution data in support of ATFM Data. |  |  | Specification |  |  | draft | no
XX | XX-ATFM Data-T-I | ATFM Data | T | I | During the Pre-tactical phase (one day prior to flight operation), CRV parties may exchange ATFM daily plan (ADP) data with each other. |  |  | Specification |  |  | draft | no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | The CRV networks shall support the exchange of ATFM daily plan (ADP) data. |  |  | Specification |  |  | draft | no
XX | XX-ATFM Data-T-I | ATFM Data | T | I | During the Tactical phase (during flight operation), CRV parties may exchange flight data taken from AFTN/AMHS or FDP and other relevant data such as meteorological data with each other. |  |  | Specification | Too vague |  | draft | no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | For ANSP flight data from AFTN/AMHS, the CRV network shall be able to support the data flow in the same manner as support for AMHS/FPL, AMHS/NOTAM, AMHS/MET data flow. |  |  | Specification | Too vague |  | draft | no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | For surveillance data from FDP, the CRV network shall be able to support the data flow in the same manner as support for surveillance data flow. |  |  | Specification | Too vague |  | draft | no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | For AIDC data from FDP, the CRV network shall be able to support the data flow in the same manner as support for AIDC data flow. |  |  | Specification | Too vague |  | draft | no
XX | XX-ATFM Data-T-OR | ATFM Data | T | OR | In the future, the CRV network should be able to support ATFM data flow of meteorological data in the same manner as support for WXXM data flow. |  |  | Specification |  |  | draft | no
XX | XX-AFTN-T-OR | AFTN | T | OR | The Contractor may provide a gateway service to accommodate legacy AFTN flows that do not comply with the standard AMHS/IP interface. If so, the Contractor shall indicate the recurring cost for this AFTN gateway service |  | Technical provisions for the AFTN/AMHS gateway are specified in ICAO Doc. 9880 Part II [5], section 4 Standard AMHS/IP interface: ICAO Doc. 9880 Legacy interface: Asia/Pacific Regional Interface Control Document (ICD) for X.25 Protocol for AFTN (http://www.icao.int/APAC/Documents/edocs/cns/ICD_X25Protocol.pdf ) | Specification |  |  | draft | no
XX | XX-AMHS-T-R | AMHS | T | R | The Service Provider shall comply with the ASIA/PAC Technical Specification of the Air Traffic Services Message Handling System (AMHS). |  | http://www.icao.int/APAC/Documents/edocs/cns/APX.%20E%20-%20%20ASIA-PAC%20AMHS%20Techncal%20Specifications_v1.pdf | IRS | Not complete and generic |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The analog voice service shall provide 64Kbps bandwidth, Pulse Code Modulation (PCM), either µ-law or A-law as specified for a specific Member-pair connection. |  |  | Specification | Optional requirement? |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The analog voice service shall provide a 4-wire E&M Type V interface (6 wires) for connection to analog Voice Communication System (VCS) equipment. |  |  | IRS
XX | XX-Voice communications-T-R | Voice communications | T | R | The analog voice service shall provide a 2-wire Foreign eXchange Subscriber (FXS) interface for connection to a Foreign eXchange Office (FXO) interface of the analog Voice Communication System (VCS) equipment. | New |  | IRS
XX | XX-Voice communications-T-R | Voice communications | T | R | The analog voice service shall provide a 2-wire Foreign eXchange Office (FXO) interface for connection to a Foreign eXchange Station (FXS) interface of the analog Voice Communication System (VCS) equipment. | New |  | IRS
XX | XX-Voice communications-T-R | Voice communications | T | R | The analog voice service shall achieve a MOS score of at least 4.0, using a mutually agreed-upon measurement method. |  |  | Specification | Not only the analog but any type of voice (digital/analog) |  | draft | no
XX | XX-Voice communications-T-I | Voice communications | T | I | It is the responsibility of the Contractor to convert the analog voice provided by the VCS to the internal format used by the provider and back to analog voice at the far end of the connection. For example, if the provider internal format is VoIP with SIP signaling, the provider would use the technique commonly referred to as “SIP Trunking.” |  |  | IRS | Optional requirement? |  | draft | no
XX | XX-Voice communications-T-I | Voice communications | T | R | The CRV must detect analog signaling and provide appropriate SIP signaling and vice versa. | New |  | Specification
XX | XX-Voice communications-T-I | Voice communications | T | R | The CRV shall provide appropriate SIP signaling to support the Automatic Ring Down (ARD) functionality. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The Contractor shall provide a high priority, low latency path to support Voice over Internet Protocol (VoIP) transport. |  |  | Specification |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall support Internet Protocol version 4 (IPv4). |  |  | IRS |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall support Internet Protocol version 6 (IPv6). |  |  | IRS |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall use the high priority tags in the packet headers to ensure that VoIP traffic is given high priority and minimal delay. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall give an appropriate level of priority to SIP. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall provide maximum latency as shown in table xx.yyy. |  | table xx.yyy. | Specification |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall provide a maximum jitter of 40 ms. |  |  | Specification |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall provide a maximum packet loss of 1%. |  |  | Specification |  |  | draft | no
XX | XX-Voice communications-T-R | Voice communications | T | R | The VoIP Transport shall provide an availability greater than 99.9%. |  |  | Specification |  |  | draft | no
XX | XX-Voice communications-T-R | Network design and user's interface | T | R | The CRV shall provide a capability to establishing a VPN tunnel between two members. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall use the high priority tags in the VPN packet headers to ensure that VoIP traffic is given high priority and minimal delay. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall provide transport for the ED-137 VoIP. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall use the high priority tags in the packet headers to ensure that ED-137 VoIP RTP traffic is given high priority and minimal delay. | New |  | Specification
XX | XX-Voice communications-T-R | Voice communications | T | R | The CRV shall give an appropriate level of priority to ED-137 SIP signaling. | New |  | Specification
XX | XX-IWXXM format-T-I | IWXXM format | T | I | The Contractor may provide the ability to exchange the data in a GML-compliant format which is individual METER and SPECI (including TREND), TAF and SIGMET. |  |  | Specification |  |  | draft | no
XX | XX-IWXXM volume-T-I | IWXXM volume | T | I | The Contractor may provide the capacity to exchange XML/GML-coded METER and SPECI(including TREND), TAF and SIGMET to improve to global interoperability. If so, the individual file size of a report increases compared to the traditional alphanumerical code. | Include an estimation of volumetry with 2 scenarios: with or without compression |  | Specification |  |  | draft | no
XX | XX-IWXXM compression-T-I | IWXXM compression | T | I | Mainly three categories of compression could be considered. These are general-purpose compression, XML-wrapped binary code and binary XML encoding. |  |  | Specification |  |  | draft | no
XX | XX-FIXM format-T-I | FIXM format | T | I | The Contractor may provide the ability to exchange the data in a GML-compliant format which is ATS messages, Traffic Flow Management, Airport CDM and boundary crossing. |  |  | Specification |  |  | draft | no
XX | XX-FIXM volume-T-I | FIXM volume | T | I | The Contractor may provide the capacity to exchange XML/GML-coded ATS messages, Traffic Flow Management, Airport CDM, boundary crossing and Track data to improve to global interoperability. If so, the individual file size of a report increases compared to the traditional alphanumerical code. | Include an estimation of volumetry with 2 scenarios: with or without compression |  | Specification |  |  | draft | no
XX | XX-AIXM format-T-I | AIXM format | T | I | The Contractor may provide the ability to exchange the data in a GML-compliant format which is NOTAM and aeronautical data including obstacles, terminal procedures and airport mapping data. |  |  | Specification |  |  | draft | no
XX | XX-AIXM volume-T-I | AIXM volume | T | I | The Contractor may provide the capacity to exchange XML/GML-coded NOTAM and aeronautical data including obstacles, terminal procedures and airport mapping data to improve to global interoperability. If so, the individual file size of a report increases compared to the traditional alphanumerical code. | Include an estimation of volumetry with 2 scenarios: with or without compression |  | Specification |  |  | draft | no
XX | XX-User's interface-T-R | User's interface | T | R | The Contractor shall implement a standardised interface at each connection point interfacing with the users. This interface is defined in Annex 3 |  | Annex 3 - Standardized Users' interface | IRS |  |  | draft | yes
XX | XX-User's interface-T-R | User's interface | T | R | In case one of the Parties listed in Annex 1 and wishing to become a Party cannot comply against Annex 3, a dedicated process shall be conducted between the OOG coordinator, this Party and the Contractor to define temporary adjustments to the interface. |  |  | IRS |  |  | draft | yes
XX | XX-Volumetry-T-I | Volumetry | T | I | The flow matrix between the Pioneer States as of March 2014 is as provided in Annex 2 |  | Annex 2 - flow matrixes between States | Specification |  |  | draft | yes
XX | XX-RCP- availability-T-R | RCP- availability | T | R | The probability of availability of the CRV network for flight plan data shall be not less than 99.9%, averaged over 1 month period between any 2 user's interfaces |  |  | Specification |  |  | draft | yes
XX | XX-RCP- availability-T-R | RCP- availability | T | R | The Contractor shall ensure that in the CRV network design, any pair of users' interfaces can communicate via at least 2 diverse physical paths. Diverse paths means 2 physical paths not having any part in common. | This is to prevent any common failure mode at the physical level, so that routing algorithms can immediately establish an alternative path in case of link disruption. |  | Specification |  |  | draft | yes
XX | XX-Monitoring and Reporting-G-OR | Monitoring and Reporting | G | OR | The Contractor shall have a web portal to provide CRV Parties with information on the performance of the CRV Network. The portal shall include information on: a) any existing network faults or impairments, b) any historical faults or impairments for the last 3 months, c) any planned network maintenance, d) historical bandwidth utilisation reports for the last 6 months, and e) historical packet drop reports (e.g. dropped due to QoS, etc) for the last 6 months. |  |  | SOW |  |  | draft | no
XX | XX-Monitoring and Reporting-T-R | Monitoring and Reporting | T | R | The Contractor shall proactively monitor the performance of the CRV Network. |  |  | SOW |  |  | draft | no
XX | XX-Monitoring and Reporting-T-R | Monitoring and Reporting | T | R | The Contractor shall automatically detect Faults within the CRV Network. |  |  | SOW |  |  | draft | no
XX | XX-Monitoring and Reporting-T-R | Monitoring and Reporting | T | R | On detection of a Fault, the Contractor shall immediately commence diagnosis and repair. |  |  | SOW |  |  | draft | no
XX | XX-Monitoring and Reporting-T-R | Monitoring and Reporting | T | R | On detection of a Fault, the Contractor shall notify all effected CRV Parties and the OOG. |  |  | SOW |  |  | draft | no
XX | XX-Monitoring and Reporting-T-OR | Monitoring and Reporting | T | OR | The Contractor shall notify the CRV Party in the event of sustained traffic overload of their access point. |  |  | SOW |  |  | draft | no
XX | XX-Network design and user's interface-T-I | Network design and user's interface | T | I | For the purposes of this document, a Network Interface Device (NID) is defined as the demarcation point between the Contractor's equipment and the CRV Party. The NID is the property of the Contractor. |  |  | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Contractor shall provide a NID at the locations nominated by each CRV Party. |  |  | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The interface type provided by the NID to the CRV Party shall be Ethernet. |  | IEEE Std. 802.3 | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | Each CRV Party shall define which version of Ethernet interface should be used. If this is not specified then the interface shall be IEEE 802.3ab (1000 Base-T). |  | IEEE Std. 802.3ab | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The installation of a NID shall be tidy with appropriate labelling. |  |  | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall provide NIDs at the designated locations for those CRV Parties which require multiple access points. |  |  | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV network shall implement Quality of Service (QoS) to prioritise traffic. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-OR | Network design and user's interface | T | OR | The CRV network shall queue voice and data flows to ensure fairness during times of congestion (e.g. an oversubscribed voice queue shall not stop the operation of the data queues). |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | QoS shall be implemented using guidance from IETF RFC 4594 Configuration Guidelines for DiffServ Service Classes. The routing protocol, voice, voice signalling, real-time interactive and standard data types shall all be given separate QoS bandwidth. |  | RFC 4594 | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-I | Network design and user's interface | T | I | CRV Parties shall apply Differentiated Services Code Point (DSCP) QoS markings to traffic before it enters the Contractors network. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-I | Network design and user's interface | T | I | For the purposes of this document the CRV Network is defined as the telecommunications network provided by the Contractor to the CRV Parties. |  |  | Terms and Conditions |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall provide a private telecommunications network which is only accessible to the CRV Parties. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall not be accessible from the Internet. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall transport Internet Protocol version 4 packets between the CRV Parties. |  | RFC 791 (September 1981) | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall transport Internet Protocol version 6 packets between the CRV Parties. |  | RFC 2460 and RFC 3513 | IRS |  |  | draft | no
XX | XX-Network design and user's interface-T-I | Network design and user's interface | T | I | For the purposes of this document, Fault Tolerance is the property that enables a system to continue operating properly in the event of the malfunction or failure of some of its components. If its operating quality decreases at all, the decrease is proportional to the severity of the failure. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | Where a CRV Party has multiple access points then the CRV Network shall have Fault Tolerance. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-OR | Network design and user's interface | T | OR | Where a CRV Party has multiple access points then the CRV Network shall automatically direct traffic to the working access points. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | Where a CRV Party has multiple access points the Border Gateway Protocol (BGP) routing protocol shall be used to control the selection of which access point is used. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-I | Network design and user's interface | T | I | The CRV IP Address Plan will be managed by the OOG. |  | RFC 1918 | SOW |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Contractor shall implement the CRV IP Address Plan. |  |  | SOW |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Contractor shall restrict route advertisements so that each CRV Party which interacts with the CRV routing protocol can only advertise subnets which are allowed in the CRV IP Address Plan. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The CRV Network shall have a packet loss rate of less than 1 in a 1,000 packets. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-OR | Network design and user's interface | T | OR | The CRV Network should have a packet loss rate of less than 1 in a 10,000 packets. |  |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-OR | Network design and user's interface | T | OR | The CRV Network may include national links between CRV access points whenever a meshing is needed by a CRV Member and not provided through a national provision. | The need shall be confirmed by the CRV member |  | SOW |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Tenderers shall demonstrate how they will support the different flow matrixes and their evolution with their design |  | Annex 2 - flow matrixes between States (OSED) | Instructions to tenderers |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Contractor shall route IPv4 multicast packets | This stems from the need for a SWIM multi-distribution as more than 2 stakeholders may be involved in the publish/subscribe model for FIXM. This may also be useful if video streaming/webconferencing is delivered through CRV as part of miscelleneous data. |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | The Contractor shall route IPv6 multicast packets as soon as the standard is available | This stems from the need for a SWIM multi-distribution as more than 2 stakeholders may be involved in the publish/subscribe model for FIXM. This may also be useful if video streaming/webconferencing is delivered through CRV as part of miscelleneous data. |  | Specification |  |  | draft | no
XX | XX-Network design and user's interface-G-R | Network design and user's interface | G | R | The Tenderers shall propose a design in their proposal that is able to meet all requirements. They shall indicate which of the optional requirements are met. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall define the methodologies and process that would be used in the design of a solution and how you will iterate with the CRV Task Force to build and validate a final design. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The Contractor shall present its proposal as a catalog of services clearly identifying what are the requirements they comply with by filling in the compliance statement template. In case of partial compliance, the Contractor shall clearly state which part(s) of the requirement can and which part(s) cannot be satisfied. |  | Compliance statement template | Instructions to tenderers |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | Before signing any Individual Contract with any of the parties listed in Annex 1, the Contractor shall make sure that this Party has signed the Document of Agreement. The signed Document of Agreement, which incorporates the common provisions, shall be enclosed in the Individual Contract as an applicable document. |  | Annex 1 - List of potential Parties and associated geographical locations | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | Any individual contract shall have its final day of validity within 5 years from the date of issuance of the letter awarding the CRV contractor by ICAO |  |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | All individual contracts shall be renewable for five one-year options, from the day following the 5th anniversary of the issuance of the letter awarding the CRV contractor by ICAO |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | Termination of contracts TBD |  |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The decision to renew a one-year option is advertised year after year by the OOG coordinator through an official letter issued at the latest 3 months before the term of the year. |  |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | Any change to any individual contract shall be handled as a variation duly signed. The variation shall be forwarded by the Contractor to the OOG coordinator. |  |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | Any change planned to any contract involving 3 Parties or more shall be coordinated with the OOG coordinator. |  |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The Contractor shall send individual invoices to all the Parties on a separate basis. | Note: The control and payment of such invoices will be done by each Party separately |  | SOW |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The Contractor shall indicate if pricing per Participant country includes or excludes local and or national government taxes and charges. |  |  | SOW |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | For services offered to the Participants for operation and maintenance of the network, the Tenderers shall detail the billing method(s) proposed (One-Time Charge, Monthly, Quarterly, Yearly, Pre-Paid, Post-Paid, etc). |  |  | SOW |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide any cost associated with customer initiated changes in US Dollars |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide costs for typical Port Speeds at the Participants Sites in US Dollars for services annually over a 5 year contract and five one-year options. |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide costs for typical Line (Access) charges at the Participants Sites in US Dollars for services annually over a 5 year contract plus five one-year options. |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide one off costs associated with the provision of a new service at the Participants Site, including but not limited to commercial or enterprise works, setup of port charge, installation of access (NTU). |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | Should a final architecture include a managed device on the Participants Site such as but not limited to a Router, Switch and or Firewall, the Tenderers shall provide the annual costs associated with the provision of that device in US Dollars annually over a 5 years contract plus 5 one-year options |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide recurrent costs for the provision of the core CRV network per Participant in US Dollars annually over a 5 year contract plus five one-year options. |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide a pricing scheme based on a number of countries/sites/Service Level Agreement/years. |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide the cost of project management, including the development of the safety case. |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall provide separately the cost, if any, associated with the fulfilment of Optional Requirements. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract management-G-R | Contract management | G | R | The Tenderers shall describe in detail their proposed method of contracting each of the participants for the proposed core CRV and the services installed at each of the Participants Sites |  |  | Instructions to tenderers |  |  | draft | yes
XX | XX-Implementation management-G-R | Implementation management | G | R | The Tenderers shall provide a draft ITP (Installation and Transition Plan). The ITP shall describe the Contractor’s strategy, plans and methodologies for safely installing and transitioning to the CRV, and manage the migration of applications |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Implementation management-G-R | Implementation management | G | R | The Contractor shall propose an Installation and Transition Plan (ITP) and maintain it once it is accepted |  |  | SOW
XX | XX-Contract Management-G-R | Contract Management | G | R | The Tenderers shall provide a draft Billing Management Plan (BMP). The BMP shall detail how the Contractor with manage and control the Billing of the CRV. This should include but not limited to (a) how the Contractor will bill each Participant (b) how the Contractor will manage non-payment (c) Options for how the bills will be delivered (d) Options for currency the bills will be delivered (e) How the CORE CRV service will be charged (f) A schedule of pricing for the services offered for the duration of the ocntract. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor shall update the Billing Management Plan (BMP) at the start of the contract and maintain it once it is accepted |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Tenderers shall develop a Dispute Resolution Plan(DRP). The DRP shall detail the process the Contractor will deal with disputes (a) between the in Country Contractor and the Participant (b) between the in CRV Contractor and the Participant (c) between the in CRV Contractor and the OOG (d) between the in CRV Contractor and the Country Contractor |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor shall update the Dispute Resolution Plan (DRP) at the start of the contract and maintain it once it is accepted |  |  | SOW
XX | XX-Contract Management-G-R | Contract Management | G | R | Confirmation shall be given that the Tenderer will be the prime contractor. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Tenderers shall provide a draft Contract Management Plan (CMP). The CMP shall detail how the Contractor with manage and control the contracts (a) between the in Country Contractor and the Participant (b) between the in CRV Contractor and the Participant (c) between the in CRV Contractor and the OOG (d) between the in CRV Contractor and the in country Contractor |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor shall update the draft Contract Management Plan (CMP) at the start of the contract and maintain it once it is accepted |  |  | SOW
XX | XX-Contract Management-G-R | Contract Management | G | R | No subcontracting without approval: the Contractor shall not subcontract (including any use of a third party to perform) any aspect of the performance of the Works without the prior written approval of the OOG and Host Country which approval the OOG may withhold in its absolute discretion |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | Confirmation that the Tenderer, as prime contractor, will: (a) take full responsibility for the Response and any supply of the Requirement; (b) be the sole point of contact with the OOG in connection with this RFT unless Airservices Australia requires otherwise; and (c) be responsible for subcontractors performance in accordance with conditions of the Framework Agreement |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The tenderers shall provide details for each proposed subcontractor the Tenderer will not be the contracting party in country |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The provision of services to the CRV parties where relying on subcontracts (in country telecommunication providers, etc) shall be transparent to the CRV parties and written down in the draft CMP |  |  | Instructions to tenderers
XX | XX-Contract Management-G-R | Contract Management | G | R | In the draft CMP, the Tenderer shall provide details of which parts of the Requirement the Tenderer will be involved in supplying and which parts of the Requirement each subcontractor will be involved in supplying. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | Contractor Representative (a) The Contractor shall ensure that its Contractor Representative: (i) is the point of contact for OOG for the purposes of the Framework Agreement (ii) has the authority and is given the responsibility to perform for the Contractor each of the relevant tasks referred to in the Project Documentation; and (iii) is a full-time employee or contractor of the Contractor. (b) the OOG may reasonably direct that the Contractor replaces the Contractor Representative. The Contractor shall, as soon as possible after receiving a direction under this claus to replace the Contractor Representative, replace that Contractor Representative with a person acceptable to OOG at no additional cost to the OOG |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The parties will meet at the times and manner set out in the CRV Concept of Operations (or as otherwise agreed in writing between the parties) to discuss any issues in relation to the Framework Agreement or the progress of the performance of the CRV |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor shall ensure that the Contractor Representative, and the OOG shall ensure the OOG Representative, is reasonably available to attend such meetings and answer any queries relating to the performance of the CRV raised by either party. |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor Representative shall record the minutes of the meeting and distribute the minutes within three (3) Business Days of the meeting date for review by the OOG |  |  | SOW |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Tenderers shall state in the draft Contract Management Plan what are the countries where restrictions apply (such as embargo, and could affect their operations: their own procurement of hardware, software, fimware, their installation, their acceptance, their use or more generally any activity including the delivery of network services |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | For the countries where restrictions apply, the Tenderers shall explicit in the draft Contract Management Plan how they will operate. |  |  | Instructions to tenderers |  |  | draft | no
XX | XX-Contract Management-G-R | Contract Management | G | R | The Contractor shall update and propose for adoption all the draft plans to the CRV chairman or OOG coordinator |  |  | SOW |  |  | draft | no
XX | XX-Implementation management-G-R | Implementation management | G | R | The Contractor shall manage the initial CRV deployment as a program with modern program management principles. | There can be a debate on the word "modern". We can use the term "widely recognised/certified". | PMP certification principles | SOW | Nil | Nil | draft | no | OK | No | The Contractor shall manage the initial CRV deployment as a program with widely recognised/certified program management principles. | Nil | Nil | SOW
XX | XX-Implementation management-G-R | Implementation management | G | R | The Contractor shall designate a Program Manager for the CRV programme | OK | CV of Programme Manager | SOW | Nil | Nil | draft | no | OK | No | The Contractor shall designate a Program Manager for the CRV programme | Nil | Nil | SOW
XX | XX-Implementation management-G-R | Implementation management | G | R | The program manager shall hold a valid PMP certification (or equivalent) and sufficient background in IT and CNS/ATM | Widely recognised PMP; Should have two lines so we will know which one has the Tenderer meet the compliance. | Certificate of PMP personnel | Specification | Nil | Nil | draft | no | Partial | Yes | The program manager shall hold a valid PMP certification (or equivalent). Having appropriate sufficient background in IT and CNS/ATM will be advantageous (optional) | Nil | Nil | Specification
XX | XX-Implementation management-G-R | Implementation management | G | R | The tenderers shall provide an early high level milestone schedule of events and key decision points for the program taking into account the close coordination with each Civil Aviation Authority/Air Navigation Contractor for installation/decommissioning purposes. | Should have two lines, one to provide the high level milestone. The other is to take account of the close coordination for the installation and commissioning. I do not understand why decomissioning is required? | Milestone Schedule | SOW | Nil | Nil | draft | no | OK | Yes | The tenderers shall provide an early high level milestone schedule of events and key decision points for the program. The tenderers shall take into account the close coordination with each Civil Aviation Authority/Air Navigation Contractor for installation/commissioning purposes. | Nil | Nil | Instructions to tenderers
XX | XX-Implementation management-G-R | Implementation management | G | R | Service creation: the Contractor shall propose a process and an associated checklist to go through for the creation of a service. The process shall clearly identify coordination steps and stakeholders. The OOG coordinator shall be informed of the creation of the service. | Need to be clear what type of service? Telco-related service or aviation-related service. | Checklist | SOW | Nil | Nil | draft | no | Partial | Yes | CRV Service creation: the Contractor shall propose a process and an associated checklist to go through for the creation of a CRV service. The process shall clearly identify coordination steps and stakeholders. The OOG coordinator shall be informed of the creation of the CRV service. | Nil | Nil | SOW
XX | XX-Implementation management-G-R | Implementation management | G | R | Testing: the Contractor shall propose a process and an associated checklist to go through for the testing of a service at a creation and after any change. The process shall clearly identify coordination steps and stakeholders. | Need to be clear what type of service? Telco-related service or aviation-related service. | Checklist | SOW | Nil | Nil | draft | no | Partial | Yes | TBC | Nil | Nil | SOW
XX | XX-Implementation management-G-R | Implementation management | G | R | Testing: the Contractor shall present a comprehensive report of the testing process to all involved Parties. For tests passed unsuccessfully, the Contractor shall correct the anomalies, or propose an acceptable workaround. | OK | Sample Testing Report? | SOW | Nil | Nil | draft | no | OK | No | Testing: the Contractor shall present a comprehensive report of the testing process to all involved Parties. For tests passed unsuccessfully, the Contractor shall correct the anomalies, or propose an acceptable workaround. | Nil | Nil | SOW
XX | XX-Implementation management-G-R | Implementation management | G | R | Any planned termination of service shall be coordinated by the Contractor with the OOG coordinator. | OK | Nil | SOW | Nil | Nil | draft | no | OK | No | Any planned termination of service shall be coordinated by the Contractor with the OOG Coordinator/Chairman. | To include Chairman as alternate to Coordinator | Nil | SOW
XX | XX-Implementation management-T-R | Implementation management | T | R | The Tenderers shall summarize the main programmatic steps they will take to ensure the successful design, implementation, transition and cutover to operation of the CRV network system and required telecommunications services | OK | Checklist for process and procedures for the design, implementation and especially for transition. | Instructions to tenderers | Nil | Nil | draft | no | OK | No | The Tenderers shall provide the main programmatic steps they will take to ensure the successful design, implementation, transition and cutover to operation of the CRV network system and required telecommunications services. (SOW) Instructions to tenderers The details for the process and procedures shall be in a form of a checklist. (Specifications?) | Nil | Nil | Instructions to tenderers
XX | XX-Implementation management-T-R | Implementation management | T | R | Any change to the CRV shall be handled by the Contractor through a baselined configuration, clearly and uniquely referenced, with associated versions (firmware/software/hardware), test results and impact assessment. | OK | l Current Configurations and Settings Baseline Information lTest Result Form l Impact Assessment Form lAcknowledgement Form | Specification | Nil | Nil | draft | no | OK | No | Any change to the CRV shall be handled by the Contractor through a baselined configuration, clearly and uniquely referenced, with associated versions (firmware/software/hardware), test results and impact assessment. | Nil | Nil | Specification
XX | XX-Implementation management-T-R | Implementation management | T | R | Any termination of service shall be considered as a configuration change and be dealt with accordingly. | OK | None | Specification | Nil | Nil | draft | no | OK | No | Any termination of service shall be considered as a configuration change and be dealt with accordingly. | Nil | Nil | Specification
XX | XX-Implementation management-T-R | Implementation management | T | R | The Contractor shall provide a dedicated 24/7/365 Service Desk staff with technical personal that have awareness of aviation applications, knowledge of business recovery processes and knowledge of safety implications of disruption to the CRV | For the purpose of clarity and to invite more players into the tenders, we should make it separate. | None | SOW and Specification | Some tenderers may have the service desk 24/7/365 but may not have the aviation knowledge. Some will employ staff with aviation knowledge if they win the contract. | Having aviation knowledge is advantageous but rather optional. The more important thing is the mapping of the classes of services each of the application is utilising. | draft | no | OK | Amended | The Contractor shall provide a dedicated 24/7/365 Service Desk (SOW). Staff with technical personal that have awareness of aviation applications, knowledge of business recovery processes and knowledge of safety implications of disruption to the CRV is an advantage. (Optional requirement under Specifications for Service Desk) | Nil | Nil | SOW and Specification.
XX | XX-Implementation management-T-R | Implementation management | T | R | The Tenderers shall describe their change management and notification process for services impacted by their Planned Network Maintenance. This should include details supporting change to design documentation and scheduled maintenance. | To include unplanned or urgent maintenance process. | None | Specification | Nil | Nil | draft | no | OK | No | To be re-draft to include unplanned or urgent cases. | Nil | Nil | Instructions to tenderers
XX | XX-Implementation management-T-R | Implementation management | T | R | The Tenderers shall describe their general Global Service Desk including hours of contact, methods of contact, fault management, fault update guidelines, problem severities and national and international escalation process | OK | None | Specification | Nil | Nil | draft | yes | OK | No | The Tenderers shall describe their general Global Service Desk including hours of contact, methods of contact, fault management, fault update guidelines, problem severities and national and international escalation process | Nil | Nil | Specification
XX | XX-Performance management-T-R | Performance management | T | R | The Contractor shall report the monthly performance to the OOG Coordinator | SOW: SOW; draft: draft; no: no
XX | XX-Performance management-T-R | Performance management | T | R | The Contractor shall report the Service use (% average load, % peak load) | SOW: Specification; draft: draft; no: no
XX | XX-Performance management-T-R | Performance management | T | R | The Contractor shall measure and report on Technical Service levels indicators: availability for each user for all CRV services implemented round trip delay for all CRV services implemented jitter for all CRV services implemented IP packet loss for all CRV services implemented Mean Opinion Score (only for voice communications) detected corruption of IP packets all CRV services implemented | SOW: Specification; draft: draft; no: no
XX | XX-Performance management-T-R | Performance management | T | R | The Contractor shall measure and report on Incidents and service disruptions: CRV service(s) and user(s) concerned, causes, time, gravity, duration | SOW: Specification; draft: draft; no: no
XX | XX-Performance management-T-R | Performance management | T | R | Dedicated helpdesk: the Contractor shall measure and report monthly: Number of issues handled over the month Min/average/max time for diagnostic over the month Min/average/max time for resolution over the month Min/average/max time for implementing a change over the month | SOW: Specification; draft: draft; no: no
XX | XX-Performance management-T- | Performance management | T |  | INCLUDE relevant requirements from SCHEDULE 4: SERVICE LEVEL UNDERTAKINGS | SOW: Specification
XX | XX-Configuration Management-G-R | Configuration Management | G | R | The Tenderers shall describe their process for managing the customer initiated changes | SOW: Instructions to tenderers; draft: draft; no: yes
XX | XX-Configuration Management-G-R | Configuration Management | G | R | Standard process:The Contractor shall perform an impact assessment for any planned configuration change. The impact assessment shall include a safety assessment. If the safety impact is expected to not be negligible (and hence be either minor, major, hazardous or catastrophic), the OOG coordinator shall be informed about the assessment result before any further action is taken and the change shall be coordinated with the Parties involved and the OOG coordinator. | SOW: Specification; draft: draft; no: no
XX | XX-Configuration Management-G-R | Configuration Management | G | R | Fast-track process: If a change has to be performed in emergency as part of a corrective action, the Contractor shall coordinate with the involved Parties if the impact assessment can be skipped for the sake of reactivity. The agreement which results from the coordination shall be recorded by any appropriate means before the change is applied. | OK: The OOG coordinator may not be involved as it is an emergency, but shall be informed at the earliest. Note: Parties commit to have H24 points of contact; SOW: Specification; draft: draft; no: no
XX | XX-Configuration Management-G-R | Configuration Management | G | R | The Contractor shall implement any configuration change (standard and fast-track) in coordination with the Parties involved | SOW: SOW; draft: draft; no: no
XX | XX-Configuration Management-G-R | Configuration Management | G | R | The Tenderers shall list their typical site requirements (installation, power, remote logical access, etc), and detail if they vary in accordance with the service level agreement (expected performance). | SOW: Instructions to tenderers; draft: draft; no: no
XX | XX-Configuration Management-S-R | Configuration Management | S | R | The Contractor shall deliver a quarterly report on physical configuration between any two users' interfaces of the CRV network | SOW: Specification; draft: draft; no: yes
XX | XX-Configuration Management-S-R | Configuration Management | S | R | The Contractor shall conduct a periodic review of the physical configuration between any two users' interfaces for the purpose of preventing any common failure mode. Frequency of the review shall not be less than once every quarter.The result of the review shall be forwarded to all Parties and to the OOG coordinator. | SOW: Specification; draft: draft; no: yes
XX | XX-Fault Management-T-R | Fault Management | T | R | The Tenderers shall describe their fault resolution process, taking into account that tickets shall have a unique reference number shared between the Contractor and Parties and that tickets may be created by the Parties or by the Contractor | SOW: Instructions to tenderers; draft: draft; no: no |  |  | UC4.1 The CRV Contractor and the CRV Members shall have a clear fault resolution process.
XX | XX-Fault Management-T-R | Fault Management | T | R | The Contractor shall coordinate 24/7 the notification, troubleshooting and closure of issues with the Parties involved through a clear fault resolution process. Note: tickets shall have a unique reference number shared between the Contractor and Parties. Tickets may be created by the Parties or by the Contractor | SOW: SOW; draft: draft; no: no |  |  | UC4.1 The CRV Contractor and the CRV Members shall have a clear fault resolution process.
XX | XX-Fault Management-T-R | Fault Management | T | R | The Contractor shall escalate to the OOG coordinator any issue where the expected safety impact is not negligible, or where security is expected to be impacted | SOW: SOW; draft: draft; no: no
XX | XX-Fault Management-T-R | Fault Management | T | R | The Contractor shall map in its fault management process the severity of faults against the Safety risk severity table | Nil: Safety risk probability and severity tables (source: ICAO SMM); SOW: SOW; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The tenderers shall explain their experience and methodology to develop a safety case, and detail the process that will be applied in the CRV project in a draft Safety Management plan (SMP) | SOW: Instructions to tenderers; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall update its safety management plan (SMP) detailing the scope of the safety activity, how the safety process interacts with other processes, roles and responsiblities, milestones and deliverables at the start of the contract and maintain it. | SOW: SOW
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall develop a safety case based on the requirements attached and on the SMP approved by the CRV chairman or OOG coordinator. | Nil: List of safety requirements; SOW: SOW; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall bring the evidence that the requirements CSP-HUM- concerning its staff involved in the design or the provision of the CRV services will be met | Nil: List of safety requirements; SOW: Specification; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall bring the evidence that the requirements CSP-SER- concerning CRV services will be met Note: The safety requirement applies to the service as a whole or at the interface with the CRV party’s facilities | Nil: List of safety requirements; SOW: Specification; draft: draft; no: no
XX | XX-Safety management-G-OR | Safety management | G | OR | The Contractor shall bring the evidence that the requirements CSP-SER- concerning the software assurance level will be met | Nil: List of safety requirements; SOW: Specification; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall bring the evidence that the requirements CSP-PROC- concerning the procedures ruling the provision of CRV services will be met | Nil: List of safety requirements; SOW: Specification; draft: draft; no: no
XX | XX-Safety management-G-R | Safety management | G | R | The Contractor shall report monthly on safety indicators as per attached list | Nil: List of safety indicators; SOW: Specification; draft: draft; no: no
XX | XX-Security Management-G-R | Security Management | G | R | The Contractor shall handle any change planned for security reason as a configuration change (be it standard or fast track). | SOW: SOW; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall be able to apply a set of hierarchised security policies and principles in an homogeneous way over all nodes of the CRV network | SOW: SOW; draft: draft; no: yes
XX | XX-Security Management-T-R | Security Management | T | R | The tenderers shall detail in the draft security policy how they protect data directly associated with the CRV from unauthorized disclosure, modification, or deletion and protect CRV services and resources from unauthorized use and denial of service. | Nil: EUR AFS Security Guidelines, April 2014, annexes H2, H3 and H4; SOW: Instructions to tenderers; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor drafts, coordinates, and maintains with the Parties involved and the OOG coordinator a security policy and associated principles. | SOW: SOW; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall demonstrate that a due monitoring of cyber security threats is performed on a regular basis, that threats are analysed against the current CRV baseline, and that it receives notifications from a specialized organization when new occurrences of threats happen | SOW: SOW; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall demonstrate that an appropriate escalation process exists to mitigate the cyber security threats with the appropriate means (configuration change, procedure etc), and that this process applies to the specific context of CRV | SOW: SOW; draft: draft; no: no
XX | XX-Security Management-T-OR | Security Management | T | OR | Authentication: The Contractor may propose an authentication service based on a cooperative PKI infrastructure including IPSec for IPv6 and digital certificates management for public IP links between ANSPs. | SOW: SOW; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall record and report monthly on the number of security events over the reference period | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-OR | Security Management | T | OR | The CRV network may be managed by an Network Operations Center (NOC) designed for aeronautical purpose specifically located preferably in category 3 or less seismic zone and shall have redundant infrastructure in another seismic zone. The NOC shall be responsible for all aspects of the CRV network security. | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall notify the OOG immediately on becoming aware of any security incident or security breach. The Contractor agrees that if a security incident or a security breach occurs, the Contractor will immediately comply with all directions of the OOG in order to address the incident or breach, and ensure it does not occur again. | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-I | Security Management | T | I | Harmful Code: any computer program viruses or other code that is harmful, destructive, disabling or which is designed to assist in or enables theft, alteration, denial of service, unauthorised access to, or disclosure, or destruction or corruption of data. | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | Contractor responsibility to prevent Harmful Code The Contractor shall detect and prevent any Harmful Code from being introduced into (or sent from) any CRV including by: (a) use of the most appropriate and up-to-date virus detection software for preventing and detecting Harmful Code; (b) implementing practices and procedures that are consistent with industry best practice; (c) pro-actively monitoring known threats of Harmful Code; and (d) informingthe OOG of any Harmful Code and the steps necessary to avoid the introduction of Harmful Code | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The contractor shall detail in line with the security policy its pocedure if Harmful Code is found | SOW: Specification; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Tenderer shall develop a draft Security Management Plan (SecMP). The SecMP describes the Contractor's strategy, methodologies and processes for meeting the security requirements of the CRV | SOW: Instructions to tenderers; draft: draft; no: no
XX | XX-Security Management-T-R | Security Management | T | R | The Contractor shall update the Security Management Plan (SecMP) at the start of the contract and maintain it once it is approved | SOW: SOW; draft: draft; no: no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | The Contractor shall carry ATFM data | OK: Volumetry to be estimated; SOW: Specification; Nil: Comment raised during review; draft: draft; no: no
XX | XX-ATFM Data-T-R | ATFM Data | T | R | Quality of service for ATFM data | SOW: Specification; Nil: Comment raised during review; draft: draft; no: no
XX | XX-Contract Management-G-R | Contract Management | G | R | Site requirements (access, power, interface). Two way requirements (from CSP - from ANSP) | SOW: IRS; Nil: Comment raised during review
XX | XX-Network design and user's interface-T-R | Network design and user's interface | T | R | ICAO Doc 9896 to be referenced | SOW: IRS; Nil: Comment raised during review
XX | XX-Data Link communications-T-R | Data Link communications | T | R | The Contractor shall carry Data Link communications | OK: Volumetry to be estimated as per OSED; SOW: Specification
XX | XX-AIDC-T-R | AIDC | T | R | The Service Provider shall carry AIDC data | OK: Mature; Nil: AIDC
XX | XX-AMHS-T-R | AMHS | T | R | The Service Provider shall support extended services for AMHS such as Active Directory, Security Services, Binary Information transfer, etc | OK: Mature; Nil: AMHS Technical Specifications; Nil: The Service Provider shall support also the "binary information transfer" extended service
XX | XX-General-G-R | General | G | R | The Service Provider shall provide a reliable and redundant clock source (SNTP) to tap on in the network itself. | Nil: General
XX | XX-AMHS-G-R | AMHS | G | R | The Service Provider shall allow the application to request, repeat and forward the AMHS messages in accordance to such request. | OK: Mature; Nil: AMHS Technical Specifications
XX | XX-AMHS-T-R | AMHS | T | R | The Service Provider shall support all forms of protocol over IP, such as X.25 (XOT), ITU X.400 messaging protocol connections. | OK: Subject to change; Nil: The Service Provider shall support all forms of protocol over IP, such as X.25 (XOT), ITU X.400 messaging protocol
XX | XX-AMHS-T-R | AMHS | T | R | The Service Provider shall support all formats such as BUFR-code, XML, plain text, ITA-5, IA-2 standards | Nil: Annex 10, Volume III, Communication Systems Manual of Technical Provisions for the Aeronautical Telecommunication Network – Doc 9750 Manual of Air Traffic Services Data Link Applications – Doc 9694 Regional Supplement to the ASTERIX Interface Control Document (ICD) for the Asia/Pacific Region Asia/Pacific Regional Interface Control Document (ICD) for ATS Inter-facility Data Communications (AIDC) Guidance Material for End-to-End Safety and Performance Monitoring of ATS Data Link Systems in the Asia Pacific Region
XX | XX-AIDC-T-R | AIDC | T | R | The Service Provider shall support AIDC over AFTN and AIDC direct.
xx | xx-AIDC-G-I | AIDC | G | I | Reference to all the external documents for compliance and implementation reference.
XX | XX-AIDC-T-R | AIDC | T | R | Follow the GOLD standards for performance (RCP240/RCP400)
XX | XX-AIM-T-I | AIM | T | I | The Service Provider shall support the access of AIM information such as eAIP over Inernet protocol services. | OK: For the AIM data stream, the current available data is eAIP and one of the access method is via web browser tool.; Nil: ICAO Roadmap for the transition from AIS to AIM: first edition - 2009 ASBU B0-DATM - Service Improvement through Digital Aeronautical Information Management.
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide training to personnel at each ANSP about how to support the NIDs | OK: The assumption here is that the Service Provider will install the NIDs initially but then it will be up to ANSPs to support them. If they need to be replaced then that should be managed by the Service Provider
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide all training material to each ANSP
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide updated training material to each ANSP if there are any changes to the CRV, interface equipment, the fault reporting process or the web portal
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide training to personnel in each ANSP defining the process for raising faults with the CRV
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide training to personnel in each ANSP defining the process for requesting changes to the CRV
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide training on how to install, update and use the web portal.
XX | XX-TRAINING-S-R | TRAINING | S | R | The Service Provider shall provide a Training Plan which defines the following: The training to be devlivered, The method of delivery, The delivery schedule, The training material to be delivered
XX | XX-GENERAL-G-R | GENERAL | G | R | The Tenderers shall provide a first draft of all relevant ICD complying with IRS. | OK: From the teleconference #6
XX | XX-GENERAL-G-R | GENERAL | G | R | The Tenderers shall maintain the ICD based on IRS as part of the change management process. | OK: From the teleconference #6
|  |  |  | R | The Contractor shall support the format for SWIM services at no additional cost when they are released by ICAO | SOW: Specification; Nil: See if this requirement is kept or not

## data control
Network design and user's interface
Volumetry | T | R | yes | draft | OK
Routing and delivery | S | OR | no | final | Partial
User's interface | G | I |  |  | NOK
RCP- availability
RCP- continuity
RCP- integrity
Safety
Security
Priority handling
Monitoring
Billing
Implementation management
Performance management
Configuration Management
Fault Management
Safety management
Security Management
Contract management
AFTN/Distress and Urgency messages
AFTN/Flight safety and regularity messages
AFTN/Aeronautical Information Services Messages
AFTN/MET
AFTN
AMHS/FPL
AMHS/NOTAM
AMHS/MET
AMHS
ATFM
WXXM
Voice communications
Data Link communications
Surveillance data
AIDC
FIXM
AIM
AIXM
Miscellaneous data
Network services