NEW ICAO METHODOLOGY FOR ASSESSING AND REPORTING RUNWAY SURFACE CONDITIONS (GRF)

IMPLEMENTATION ACTION PLAN TEMPLATE1

__________________ [Insert name of State]

| ID | ACTION | ENTITY RESPONSIBLE | TARGET DATE2 | IMPLEMENTATION DATE3 | REMARKS3 |
| --- | --- | --- | --- | --- | --- |
| GRF 1 | Review ICAO provisions and guidance and other Organisations guidance (see References) | CAA | 31/12/2020 |  |  |
| GRF 2 | Designate a focal point to coordinate implementation activities at the national level | CAA | 31/12/2020 |  |  |
| GRF 3 | Identify concerned focal points in each entity (CAA, Airport, ANSP, Aircraft operators – include BA, GA and military as applicable) | CAA, Airports, ANSP, Aircraft operators | 31/12/2020 |  |  |
| GRF 4 | Establish an Implementation Coordination Team including staff from the identified stakeholder entities | CAA | 15/01/2021 |  |  |
| GRF 5 | Conduct the initial training for the CAA, Airports, ANSP and Aircraft Operators’ personnel (e.g. ICAO/ACI/IATA online courses, national awareness workshop, etc.) | CAA | 01/03/2021 |  |  |
| GRF 6 | Identify regulations, standards, procedures and guidance material to be developed/amended | National Focal Point and the Implementation Coordination Team | 01/04/2021 |  |  |
| GRF 7 | Develop a detailed national implementation plan and safety risk assessment. Each entity should also establish its specific implementation plan and safety risk assessment. | CAA, Airports, ANSP, Aircraft operators | 01/04/2021 |  |  |
| GRF 8 | Identify the necessary means and resources for the implementation (human, financial and material resources) | National Focal Point and the Implementation Coordination Team | 01/04/2021 |  |  |
| GRF 9 | Consult with Airport Runway Safety Teams | Airports | 14/05/2021 |  |  |
| GRF 10 | Develop and promulgate regulations and standards | CAA | 14/05/2021 |  |  |
| GRF 11 | Develop procedures and guidance material (translate if required) | National Focal Point and the Implementation Coordination Team | 15/06/2021 |  |  |
| GRF 12 | Provide the necessary means and resources for the implementation (human, financial and material resources) | CAA, Airports, ANSP, Aircraft operators | 30/06/2021 |  |  |
| GRF 13 | Conduct On-the-Job Training (OJT) on the implementation (ACI on-site GRF training course is available to support Airports) | CAA, Airports, ANSP, Aircraft operators | 01/08/2021 |  |  |
| GRF 14 | Perform tests/trials prior to the effective implementation | All | 01/10/2021 |  |  |
| GRF 15 | Applicability date for the new methodology for assessing and reporting runway surface conditions | All | 04/11/2021 |  |  |

Notes:  ICAO Runway Safety Go-Team Assistance Missions may be arranged to support States and Airports.  ACI APEX Safety Reviews are also available to support Airports.

Remarks: 1 To be tailored and detailed by States; 2 Target dates are indicative only; 3 For input by States

References

Publications / Websites

- Annexes 3, 6, 8, 14, & 15 – applicability date 4 Nov 2021

- PANS Aerodromes (Doc 9981), Aeronautical Information Management (Doc 10066), & Air Traffic Management (Doc 4444)

- Assessment, Measurement and Reporting of Runway Surface Conditions (Cir 355)

- Aeroplane Performance Manual (Doc 10064)

- ICAO GRF website https://www.icao.int/safety/Pages/GRF.aspx

- ICAO EUR/NAT Guidance on the Issuance of SNOWTAM https://www.icao.int/EURNAT/EUR%20and%20NAT%20Documents/EUR%20Documents/EUR%20Documents/SNOWTAM%20Guidance.pdf

Training / Events

- ICAO/ACI Online Course for Airport Operators https://www.olc.aero/product/icao-global-reporting-format/

- ICAO/IATA Online Course for Aircraft Operators & Flight Crew https://www.iata.org/en/training/courses/grf-runway-surface/talp38/en/

- Future ICAO-IATA-CANSO Online Course for ANSPs, ATS & AIS staff

- ICAO APAC Regional GRF Seminar https://www.icao.int/APAC/Meetings/Pages/2019-AOP-SG3-GRF-Seminar.aspx

- ICAO Global GRF Symposium https://www.icao.int/Meetings/grf2019/Pages/default.aspx