ATN/AMHS/AIDC Implementation Status in the APAC Region

| State/Organization | ATN G/G Boundary Intermediate System (BIS) Router/AMHS | AMHS Vendors Selected | AIDC | ATM System selected to support AIDC and Associated ICD (Implementation Status of the Basic 5 message set supported) | Remarks |
| --- | --- | --- | --- | --- | --- |
| AFGHANISTAN |  |  |  |  |  |
| AUSTRALIA | ATN tests were conducted. BIS Router and Backbone BIS Router and AMHS implemented. AMHS has been migrated to CRV. Connection with Singapore using AMHS was implemented October 2016; Another AMHS connections pending CRV (target date by March 2020) including both connection with New Zealand and USA. AMHS connection with Indonesia pending on CRV implementation AMHS connection with South Africa has been established Plan to upgrade AMHS support IWXXM traffic from Nov. 2020. | COMSOFT | AFTN/AMHS based AIDC Implemented between Brisbane and Melbourne, Oakland, Nadi and Auckland; Implemented between Melbourne and Johannesburg; AIDC is also in use between Melbourne and Mauritius; Operational trial between Brisbane and Ujung Pandang since May 2013. Implementation in July 2017. LOA needs to be updated. |  |  |
| BANGLADESH | In Q1/2013, Bangladesh installed ATN/AMHS and BIS Router at Dhaka (VGHS) with User Agents at Chittagong (VGEG) and Sylhet (VGSY). | COMSOFT | Tentative date of implementation of AIDC is Q4 of 2018 with Kolkata and Myanmar. |  | The Bangladesh ATM Upgrade Project (BATMUP) under Public Private Partnership (PPP) in Dhaka is expected to be completed by 2018. As soon as the ATM up- gradation is completed hopefully Bangladesh will be able to implement AIDC with Kolkata and Myanmar by the end of 2018. |
| BHUTAN | ATN/AMHS circuits, using IP over VPN, with Thailand (Bangkok) and India (Mumbai) commissioned in June and July 2017 respectively. IOT and POT with Mumbai completed on 27th June 2017. IOT and POT with Thailand completed on 2nd May 2017. TMC signing with both countries at final stage. | AEROTHAI’S AMHS System | Currently not applicable. If required in the future, will be decided after CRV implementation (scheduled for mid-2019). |  |  |
| BRUNEI DARUSSALAM | ATN BIS Router planned for 2015 and AMHS planned for 2015 |  |  |  |  |
| CAMBODIA | BIS Router and AMHS installed. Cambodia (CATS) AMHS connected with Bangkok via VSAT IP link since 10 December 2013 | AVITECH | AIDC function and capability made available. Ready for testing with neighbors ATS Facilities starting from 2017 and target date of implementation with Bangkok in 4Q2019 | THALES which supports AIDC ICD Version 1. |  |
| CHINA | ATN Router and AMHS including NCC deployed in 2008 which is being upgraded to support ATN/IPS with target date of completion in December 2013. The Beijing-Hong Kong AMHS link was put into operation in 2018; With Thailand is completed POT, after sign the TMC circuit and was put into operation in Q12020 AMHS/ATN technical tests with Macau completed in 2009. Plan for ATN/AMHS implementation with Macao China in 2019. ATN/AMHS circuit with ROK has been put into operation since June 2011. ATN/AMHS tests with India has been put into operation since 2016. ATN and AMHS IOT with Mongolia is completed in May 2018. Plan for commissioning after POT completion in 2020 Connection tests with Nepal is TBD. AMHS testing with Japan in 2020. AMHS testing with Russia in 2020. | IN-HOUSE (Aero-Info Technologies Co., Ltd) | AIDC between some of ACCs within China has been implemented. AIDC between several other ACCs are being implemented. AIDC between Sanya and Hong Kong put in to operational use since 8 Feb 2007. AIDC between Dalian and Incheon implemented in Nov. 2016; Guangzhou with Nanning/Zhanjiang/Zhuhai implemented; Nanning and Kunming/Guiyang/Zhanjiang implemented in 2011; Zhanjiang/Haikou; Chengdu and Chongqing/Guiyang implemented in 2011; Guiyang and Chongqing/Kunming implemented in 2011; For Beijing/Ulaanbaatar, planned date of testing in 2020. |  |  |
| HONG KONG, CHINA | Manila / Philippines CRV/AMHS circuit was put into operation in May 2019. Beijing / China ATN/AMHS circuit was put into operation in 2018. Plan to migrate to CRV in 2020. Bangkok / Thailand ATN/AMHS circuit was put into operation use in 2014. Plan to migrate to CRV in Q32020. Fukuoka / Japan Currently on AFTN. Plan to cut over to CRV/AMHS in Q1 2020. HoChiMinh / Vietnam Currently on AFTN. Plan to test ATN/AMHS in 2020. Taibei Currently on AFTN. Plan to test CRV/AMHS in 2020 | COMSOFT | AFTN-based AIDC with Sanya put into operational use in Feb 2007. AIDC technical trial with Taibei conducted in 2010 and completed in 2012 and put into operational use in Nov. 2012 AIDC technical and interoperability tests with Guangzhou were conducted successfully in April and June 2017 respectively and put into operational use in May 2018. AIDC technical and interoperability tests with Manila were conducted successfully in May 2018 with no observations on exchanging core set messages (EST, ACP, TOC, AOC, LAM, LRM). AIDC operational trial with Manila was commenced in March 2019. . | Raytheon ATM system Support AIDC ICD Version 3 commissioned in November 2016. | Already support exchange of IWXXM messages based on FTBP. |
| MACAO, CHINA | ATN/AMHS interoperability test with Beijing commenced in March 2009. ATN/AMHS circuit with Hong Kong put into operational use in end Dec. 2009. ATN/AMHS implementation with mainland China planned for 2019. | COMSOFT | (Not applicable for using AIDC, looking into the possible application (some way) between TWR and ACC/APP). |  |  |
| ## COOK ISLANDS |  |  |  |  |  |
| DEMOCRATIC PEOPLE’S REPUBLIC OF KOREA | The ATN BIS Router and AMHS planned for in 2011. |  | With neighboring ACCs to be implemented |  |  |
| FIJI ISLANDS | ATN BBIS IPS router and AMHS implemented over CRV for connection to USA in April, 2019 with Australia planned for June, 2019. . For connections with sub-regional centers: For New Caledonia using AMHS since 2017; For connection with Kiribati using UA/AMHS implemented in 2015. | COMSOFT | AFTN based AIDC implemented between Nadi/ Brisbane, Auckland and Oakland. | - Support and implemented AIDC messaging: ABI, EST, CPL, CDN, ACP, TOC, AOC with all three centers - AIDC ICD version 2.0 implemented with Auckland and Oakland. - AIDC ICD Version 1.0 implemented with Brisbane |  |
| FRANCE (French Polynesia Tahiti) | Planned for implementation of AMHS in 2020. Using IP with New Zealand since 2017. |  | Implementation of AIDC (based on Version 3) with adjacent centers (Oakland and Auckland) since 2009. | THALES EUROCAT for AIDC | Alternate routing for backup between Tahiti and Christchurch via Tahiti/New Caledonia IP link |
| INDIA | Dual stack ATN/IP router and AMHS implemented at Mumbai in 2011. Operational AMHS connections with Bangkok, Dhaka, Singapore, Kathmandu, Karachi implemented. With Beijing implemented in 2016; With Colombo implemented in May2017; With Bhutan implemented in July 2017; Planned for Nairobi in Q1 2020 and Muscat for 2020. | COMSOFT | -15-May-2017, AIDC implemented between Chennai and Kuala Lumpur with ABI and EST messages. CDN is done with voice confirmation. TOC/AOC to be implemented; - Chennai-Colombo under test trial; - Chennai-Male under test trial; - Chennai-Yangon under test trial; - Mumbai-Male test trials completed; LOA signed. - Trivandrum-Male under test trial. LOA signed. - Mumbai-Muscat under test trial; -Ahmedabad-Karachi under test trial. LOA signed. | 1) Raytheon at Mumbai and Chennai. 2) Selex at Hyderabad and Bengaluru. 3) INDRA at 40 locations | 1) Major Indian airports and ATC centers have integrated ATS Automation Systems having AIDC capability. Successful AIDC trials have been carried out amongst major ATSUs within India. 2) AIDC implemented between Chennai and Mumbai. 3) AMHS implemented and working between A. BBIS: Mumbai-Singapore, Bangkok B: BIS: Mumbai, Kathmandu, Dhaka, Karachi, Colombo & Paro |
| INDONESIA | ATN BIS Router and AMHS with Singapore implemented Since February 2018; AMHS Trial (IOT) with Brisbane pending for CRV implementation. | IDS ELSA | Implementation Jakarta (new ATM system in 4Q2020) The target date of AIDC implementation will commence testing in 4Q2020 including following pairs: Jakarta-Singapore; Jakarta-Chennai; Jakarta-Ujung Pandang; Jakarta-Melbourne; Jakarta – Kuala Lumpur Ujung Pandang –Brisbane: implemented in July 2017. Ujung Pandang – Manila - Successful testing conducted; Target date of implementation 4Q2019 Ujung Pandang - Kota Kinabalu - Implementation date TBC -Ujung Pandang – Oakland, test conducted, and target date for implementation in 3Q2019. - Ujung Pandang – PNG trial 3Q2020 | Thales in Makassar able to support ICD Version 3 since December 2015 | For CRV, contract in 1Q2020 and implementation in 2Q2020 |
| JAPAN | ATN BBIS router and AMHS installed at 2000. Connection tests with USA 2000 - 2004 and put into operational use in 2005. ATN BBIS router (to apply to Dual Stack) and AMHS (to upgrade in 2015. The connection test with each country which is not currently connecting is started after update. Upgrading connection with Hong Kong and Singapore using VPN will be implemented in 2020 after implementation of CRV. Coordinating for all other circuits upgrading. | NEC | AIDC implemented between Fukuoka ATMC and Oakland ARTCC in 1998. AIDC implemented between Fukuoka ATMC and Anchorage ARTCC in 2005. AIDC implemented between Tokyo ACC/Fukuoka ACC and Incheon ACC in 2010. Implemented between Fukuoka and Incheon since June 2009. AIDC implemented between Fukuoka ACC/Naha ACC and Taibei ACC implemented. AIDC between Fukuoka ACC and Shanghai ACC under negotiation. |  | Japan and USA conducting testing AIDC over AMHS and cutover date is 5 May 2017. |
| KIRIBATI | Connection with Nadi using UA/AMHS implemented in 2015. |  |  |  |  |
| LAO PDR | ATN BIS Router and AMHS completed, planned for operation with Bangkok since 4Q 2016. | THALES | AIDC testing with Bangkok in 2017 and target for implementation in 4Q2019. Testing with Hanoi on-going since 2017; with Cambodia operational test again in June 2018, and implementation 2Q 2019. Testing with Kunming and Yangon ongoing. | THALES which is able to support ICD Version 2. |  |
| MALAYSIA | ATN BIS Router completed 2007. AMHS implementation planned for Q42017; Malaysia – Singapore for AMHS implementation in March 2020. Malaysia – Thailand for AMHS implementation in 2019. | FREQUENTIS | AIDC testing with Bangkok ACC conducted since 2016. Operational trial will commence in August 2019. AIDC Between Kuala Lumpur/ Chennai implemented in phases from May 2017 implementation for ABI, EST and MAC along with response messages LAM, LRM and ACP. Review on the CDN message implementation conducted in Aug. 2017. SOP signed 26 April, 2017. AIDC testing with Singapore on going since 2016. Target date for operational trial from 3Q2018, and Implementation 2Q2019. Planned testing with Ho Chi Minh ACC – 3Q2019; AIDC between KK ACC and Manila ACC in 4Q2020 and technical testing 2Q 2019. KK ACC with Ujung Pandang TBC; AIDC between Kuching ACC and Singapore planned for 2Q2020; AIDC technical test between Kota Kinabalu ACC and Singapore planned for 3Q2019; AIDC between Kuala Lumpur and Jakarta testing planned for 4Q2020. | SELEX which is able to support ICD Version 3. |  |
| MALDIVES | In the process of replacing the existing operational AFTN system by AMHS. It is expected to complete the installation before the end of 2019. With the new AMHS, it is planned to establish a new IP connection between an additional neighboring ATSU as the current link is an X.25 connection between Colombo. Also will look for the possibility of implementing the CRV network to use with AMHS and AIDC during the same phase. |  | Connection established with all the adjacent ATSUs. Interoperability tests successfully completed in 2017. LOA signed for operational trials between Mumbai, Chennai, and Trivandrum. Operational trials were also successful with these ATSUs, while several issues were resolved from both ends. Ready to sign LOA with Melbourne and is expected during the 2nd quarter of 2019. Trials with Colombo had few issues, which Colombo is working to resolve it on their end with the automation system supplier. Connections between all 5 ATSUs are turned ON in the ATS automation system to conduct pre-notified operational trials. | SELEX which is able to support ICD Version 3. |  |
| MARSHALL ISLANDS |  |  |  |  |  |
| MICRONESIA (EDERATED STATES OF) |  |  |  |  |  |
| Chuuk |  |  |  |  |  |
| Kosrae |  |  |  |  |  |
| Pohnpei |  |  |  |  |  |
| Yap |  |  |  |  |  |
| MONGOLIA | AMHS/AFTN gateway implemented 2012. ATNBIS router implemented in 2014. ATN and AMHS IOT with China was completed in May 2018. Plan for commissioning after POT completion in 2019. | COMSOFT | ATM automation system supports both AIDC and OLDI. Coordinating with Russia on OLDI connection in target date 2016. Coordinating with China on AIDC connection between Beijing/Ulaanbaatar technical trials in progress. Planned date of testing in 2019. | INDRA Aircon 2100 supporting AIDC ICD Version 2. |  |
| MYANMAR | AMHS including ATFN/AMHS gateway implemented in Nov. 2011; Connection with Thailand implemented in 4Q2016; Planned for AMHS connection with Beijing. Target date TBC. | THALES | AIDC connection pre-operation test with Thailand conducted in 4Q2017 and Target date of implementation 1Q2020; AIDC testing with Kunming Chennai, Kolkata and Vientiane conducted in 2020. | THALES Automation system (Topsky ATC supports APAC AIDC ICD Ver. 2. |  |
| NAURU |  |  |  |  |  |
| NEPAL | AFTN/AMHS Gateway implemented in 2012. AMHS implemented with India since June 2014. AFTN connection with China. Plan to test AMHS connection soon. | COMSOFT | Nepal uses custom built ATM system from NEC. Some issues regarding ICD need to be resolved in order to proceed ahead with AIDC testing with India and China. |  |  |
| NEW CALEDONIA | New router and AMHS commissioned December 2016 | COMSOFT |  |  |  |
| NEW ZEALAND | AMHS connection with the USA over CRV was implemented in April 2019. AMHS connection to Australia over CRV is scheduled for June 2019. | COMSOFT | AIDC implemented between New Zealand, Australia, Fiji, Tahiti, Chile and USA. | Supported the Basic 5 message set. ATM systems are LEIDOS and ADACEL |  |
| PAKISTAN | ATN/AMHS connections with Mumbai since 2015. Planning for AMHS connection with Beijing and Kuwait after upgrading existing facilities between the Countries. Target dates for implementation TBC. | COMSOFT | Implemented between Karachi and Lahore ACCs Further testing to be conducted between Delhi/Karachi & Delhi/Lahore after system upgradation at Indian end; Mumbai/Karachi &AHM/Karachi on trial operation. For testing with Muscat planned for 4Q2019. Coordination for testing with Tehran is in progress. | ATM system from Intra AIRCON 2100 | Existing Radar system being upgraded. |
| PAPUA NEW GUINEA | Currently AFTN over IP. AMHS implementation is planned for after successful implementation of CRV this year. AMHS implementation planned for 2020. | COMSOFT is the supplier of PNG AFTN/AMHS system | AIDC using AFTN operational with Australia, testing/trial with Oakland (USA) started late last year and in progress. AIDC implementation with Indonesia to happen after CRV implementation this year. | New ATM System from Thales (TopSky-ATC) implemented and operational now supports AIDC V3. |  |
| PHILIPPINES | New ATN/AMHS was installed at the New CNS/ATM Center in Manila. Site Acceptance was successfully done on October 2015. The new AMHS commissioned and operational in March 2018. The international connection still using AFTN except Hong Kong. The AMHS Implemented over CRV with Hong Kong 1Q2019 and with Singapore is planned over CRV by end of 2Q2020. AMHS implementation with Oakland USA via CRV is planned for 3Q2020. | COMSOFT | On-going test with Singapore, Ujung Pandang and Taipei ACCs; Planned technical trial over new ATM system with other ACCs from 4Q2017 to 3Q2019: Coordination is underway for using AIDC function of the new ATM system with adjacent ACCs. Planned implementation: 2Q2019 – Singapore ACC; 4Q2019 – Ujung Pandang ACC; 3Q2019 – Taipei ACC; 2Q2019- Hong Kong ACC; | THALES which is able to support ICD Version 2. |  |
| REPUBLIC OF KOREA | ATN/AMHS circuit with China put into operational use in June 2011. AMHS implementation with China over CRV in 2Q2020. AMHS implementation with Japan over CRV in 4Q2020. | SAMSUNG | AIDC implemented between ACC and Fukuoka ATMC in 2010 AIDC between Incheon and Dalian implemented in Nov. 2016. | Rockheed Martin System |  |
| SINGAPORE | AMHS implemented. ATN/AMHS circuit with India put into operational use in March 2011. ATN/AMHS circuit with UK put into operational use in March 2012. ATN/AMHS circuit with Thailand put into operational use in December 2014. ATN/AMHS circuit with Australia put into operational use in October 2016. ATN/AMHS circuit with Indonesia put into operational use in February 2018. Inter-Operability Test (IOT) with Japan, Malaysia, and Vietnam started 2019, targeted in 2019. IOT with Philippines, Sri Lanka, Bahrain and Brunei targeted in 2020. | FREQUENTIS COMSOFT | Operational with Ho Chi Minh implemented July 2014 Kuala Lumpur operational trial started since September 2018 and is implemented Nov. 2019. Manila operational trial started in February 2019. Implementation Nov. 2019 Technical trials with Jakarta ACC will be initiated once the Jakarta ACC ATMS renewal is completed. | THALES supports ICD Version 3 since December 2018 |  |
| SRI LANKA | ATN BIS Router Planned for 2013. IP based AMHS implemented by Oct. 2017. - Mumbai tested May 2017 operational planned for Q4 2017; - Singapore testing in Q4 2017 operational for 2018; - Male testing and operational date TBD. | IDS | Trials with Male planned for in 3Q2019. Trial with Chennai on-going. Plan for implementation in 2018 and with Melbourne plan for 1Q2018. | INTELCAN which is able to support ICD Version 3. |  |
| THAILAND | BBIS/BIS Routers already implemented. AMHS has been implemented since July 2011. Connection with Bangladesh, Bhutan, Cambodia, China, India, Lao PDR, Myanmar, Singapore, Hong Kong China implemented. Implementation with Malaysia planned for 2019. Interoperability Test: with Viet Nam planned for end of 3Q2019 and Italy planned for end of 4Q2019 Connection with SITA (SITA AMHS Gateway inter-connections) implemented. | AEROTHAI's AMHS System | AIDC Connection test with Lao PDR, Cambodia, Myanmar and Malaysia underway since 2016; Operation trial with these States from late 2017 to early 2019. Target date of implementation is around 2Q2020. | THALES which is being implemented with planned completion in 4Q2019. AIDC feature supports APAC AIDC ICD V.3. |  |
| TONGA | AMHS planned for 2008. The provider is linked to the New Zealand AFTN |  |  |  | CPDLC and ADS-C is not considered for lower airspace |
| UNITED STATES | - Australia (1/2019) - Fiji (1/2019) - New Zealand (1/2019) - Japan (2/2019) - Philippines (3rd 2020) | IN-HOUSE | - Fiji, Japan, New Zealand, - Tahiti (via New Zealand), - Papua New Guinea (via Australia) - Philippines (3rd 2020) - Indonesia via Australia (2019) - Russian Federation (pending joining CRV) | IN-HOUSE which is able to support APAC and NAT ICDs currently Version 2. |  |
| VANUATU |  |  |  |  |  |
| VIET NAM | AMHS (basic) implemented. Trial phase from 4Q/2015 to 3Q/2018. IOT with Thailand in progress from 4Q/2017 Plan to use AMHS in 4Q/2018; Planned for IOT with Hong Kong, Singapore and Thailand in 2019 For IOT with Laos PDR and Cambodia in 2019. | IN-HOUSE | Operational between Ho Chi Minh and Singapore since July 2014. Trial for additional messages sets since 2018. Implementation between Ho Chi Minh with Philippines planned for 4Q2020; Technical testing with Cambodia already done; Trials between Hanoi and Vientiane, Lao. PDR on going. with Malaysia TBC Testing with Cambodia on – going; For operation trial TBC. | Support ICD Version 1.0 with THALES at Ho Chi Minh ATM system. Support ICD Version 3.0 with Selex at Hanoi ATM System. |  |
| Wallis and Futuna (FRANCE) | AMHS implementation planned for end of 2017 |  |  | COMSOFT |  |

_ _ _ _ _ _ _ _ _ _ _ _ _