# CRV IMPLEMENTATION TABLE

| State/ Administration | Intended date for CRV cut-over | Applications targeted | Migration scheme | Prerequisites/ dependencies |
| --- | --- | --- | --- | --- |
| Australia | Contract in May2018 and service readiness in 3Q 2018 | AFTN, ADS-B, AMHS, Voice With: Australia February,2019(AMHS/AIDC), March,2019(Voice) Fiji March,2019 (AMHS June 2019/AIDC, Voice completed April) New Zealand, February, 2019 (AMHS June 2019, AFTN May 2019/AIDC), March, 2019 (Voice April 2019 completed) Indonesia 4Q2019 (TBC) (AMHS/AIDC, Voice, ADS-B); PNG 4Q2019(TBC), (AMHS/AIDC, Voice) Singapore 2Q2019 TBC (AMHS/AIDC, Voice); South Africa TBC 3Q2019 TBC,(AMHS/AIDC, Voice); Japan would be end of 2019. | staged approach | Termination of current COM contract |
| Bhutan | Contract in 3Q2019, service readiness in 4Q2019 | Data(AMHS, AFTN) and voice |  | Administrative approval from the management for the direct contract and approval from BCAA |
| Cambodia | As early as convenient, dependent on neighboring countries |  |  | Internal decision making |
| China | Contract in 1Q2020, service readiness in 2Q2020 | Data(AMHS) With: Hong Kong 2Q2020; Japan 2Q2020; Thailand 2Q2020; India 2Q2020. Republic of Korea a.s.a.p ATFM traffic test May 2020 over CRV | staged approach |  |
| DemocraticPeople's Republic of Korea | Contract in 3Q2018 and service readiness in 4Q2018 | AFTN and VoIP |  |  |
| Hong Kong, China | Contract signed on 6 April 2018. Connection was installed successfully in June 2018. CRV-Voice with Manila was put into operation on 14 August 2018. | DATA (AMHS) With: Beijing 2Q2020; Manila operational May 2019 Japan 1Q2020; Thailand 3Q2020; | staged approach | Need to coordinate with relevant CAAs/ANSPs in joining CRV in a harmonized manner, etc. |
| Macao, China | To be confirmed |  |  | CBA migration fromX25toIP |
| Fiji | Contract in May 2018 and service readiness in 3Q 2018 | Data (AMHS) and VoIP With: Australia ATS voice April 2019 completed, AMHS planned June 2019, NZ ATS voice c. 2019 and USA ATS voice March 2019 completed. AMHS April 2019. | Staged approach | CBA, safety case |
| France (New Caledonia and French Polynesia) | 2019 is target for DNSA to sign contract subject to internal security assessment (done). | ATS Voice, AMHS with Fiji & AIDC, AMHS with USA, AIDC/AMHS with NZ and ATS voice. |  | CBA, cost must be affordable Wallis and Futuna: no dedicated connection to CRV |
| India | Contract in 1Q2020 and service readiness in 2Q2020. Available | . Data first then voice. | staged approach | safety case |
| Indonesia | Contract in 1Q2020 and Service readiness in 2Q2020 | AFTN, AMHS, ADS-B and voice |  | CBA completed |
| Japan | Contract signed in Nov.2017 and service readiness in1Q 2018for Fukuoka | Data first: With: Hong Kong 1Q2020 USA completed 1Q 2019 Singapore 3Q2019; China 2Q2020 | staged approach |  |
| Malaysia | Contract to be signed 2Q 2020 and service readiness in 4Q2020 | AFTN, AMHS, ADS-B and ATS voice | staged approach | New ATC centre operational in 2020. Contract issue with the new ATC main contractor. COM Project is part of the main contract. |
| Myanmar |  |  | Contract in 3Q 2020 |  |  | AFTN, AMHS, ADS-B and voice |  |  | Staged approach |  |  | CBA attractive if conterparts join in CRV |  |  |
| Nepal |  |  | Nepal intends to join CRV on staged approach with AMHS data connectivity as first priority and intends to sign the contract with PCCW within 2020. |  |  |  |  |  |  |  |  |  |  |  |
| New Zealand | Contract inMay2018 and service readiness in 3Q 2018 | Australia AMHS June 2019, French Polynesia AMHS and Voice Chile AMHS (SAM regional network REDDIG) AFTN, AMHS and voice |  | CBA attractive if all counterparts join in |
| Philippines | Contract signed in March 2018 and service readiness in 2Q2018 | Data (AMHS and AIDC) and voice with HK AIDC 2Q 2019,AMHS May 2019 with Taipei AIDC 3Q2019 , AMHS IOT 2Q 2019, Voice completed 1Q 2019. with USA AMHS &AIDC 4Q 2019. For Voice: with HK Aug. 2018, with USA June 2019 | staged approach | Success transition to the New ATM centre in 4Q2018 |
| Republic of Korea | Contract in 3Q2019 and service readiness in 4Q 2019 | Data (AMHS), AIDC and VoIP With CHN AMHS 4Q2019 With JPN xx | staged approach |  |
| Singapore |  |  | Contract in May Q2019 and service readiness in 3Q2019 |  |  | 1/AFTN/AMHS 2/Voice/AIDC/ADS-B AMHS With: Australia 2Q2020; Japan 2Q2020 Thailand 2020; India 2020. 3/Voice with Manila: to complete in Jan 2020 |  |  | staged approach |  |  | CBA attractive if all counterparts join in |  |  |
| Sri Lanka | As soon as CRV is available | AMHS connectivity with Mumbai, Singapore and Male. Direct Speech facilities with Chennai, Trivendrum, Mumbai, Male, Jakarta, Melbourne, Singapore | Phased approach with the implementation of CRV | CBA |
| Thailand | Contract in 1Q 2020 and service readiness in 4Q2020 | Data first Then voice, subject to safety case: China 4Q2019 Hong Kong 4Q2019; Singapore 4Q2019; India 2019. | Staged approach |  |
| United States |  |  | Contract in May 2018 and service readiness in 3Q 2018 |  |  | - with Australia AFTN to AMHS over IP: Feb 2019 Voice: March, 2019 - With Fiji AMHS/AIDC Feb 2019 Voice March, 2019 - With New Zealand AMHS/AIDC, Voice March 2019 - With Japan AMHS/AIDC Feb 2019 VOICE: June 2020 - With Philippines AMHS/AIDC 3Q2019 VOICESeptember, 2019 - With Indonesia Voice 2020 - With Russian Federation Pending joining CRV - With PNG Voice: Feb/2019 via Australia with direct CRV planned for 2020 - other FIRs as opportune (French Polynesia, Samoa, , etc.) 7) ATFM, AMHS with Attachment 8) BBIS with Fiji, Australia and Japan 3Q2018 (for only AMHS) |  |  | Staged approach |  |  |  |  |  |
| Viet Nam | To be confirmed later (After discussed with PCCW Global) |  |  |  |

_ _ _ _ _ _ _ _ _ _ _ _ _