## Sheet1
AMHS Reediness Report for Supporting IWXXM Traffic
No. | States/Administration | Name of State (Administration)/name of BBIS/BIS location where AMHS is installed: | AFTN/AMHS transition date/schedule | Readiness Status of AMHS for supporting File Transfer Body Part (FTBP), the Interpersonal Message (IPM) Heading Extension (IHE) to support for exchanging IWXXM reports of a maximum size of 4MB and FTBP of maximum 2MB: | Capacity status of the operational AFS links to support the exchange of the required meteorological information in both IWXXM GML form and TAC form:
|  | 1 | 2 | 3 | 4
1 | Hong Kong China | Hong Kong China | December 2009 | Support | 2MB for CRV and 64kbps for IPLCs
2 | Fiji | Fiji Airport/Air Traffic Management Centre | Completed. In June 2019, Fiji completed the transition of ATN BBIS to IPS for the AMHS service from Nadi to Salt Lake, USA & Brisbane, Australia over the CRV network. The local end User still operates on AFTN terminal and is converted to AMHS over the AFTN/AMHS Gateway. | The Comsoft AMHS System supports File Transfer Body Part (FTBP). Our system has the capability of exchanging IWXXM reports of a maximum size of 4MB and FTBP of maximum. | Nadi has contracted a 1.0Mbps bandwidth using CRV Package C+ for Voice & AMHS services. The total bandwidth usage for voice and data is 768K from the total 1.0Mbps. The bandwidth for AMHS is 64Kbps each to Brisbane & Salt Lake Center. It is noted in the ACSICG/7 WP04 presented by USA that 64Kbps is the minimum recommended required bandwidth for AMHS to exchange FTBP for IWXXM.
3 | India | AAI/Mumbai Airport | AMHS is in operation since 2011 | 2MB:
Mumbai AMHS is not able to receive AMHS messages with attachments, although Bangkok and Singapore sent the AMHS messages with attachment to Mumbai.
India is planning a replacement of existing AMHS system within a timeframe of 2 years.
4 | Japan | Japan/Fukuoka | ATN BBIS router and AMHS installed at 2000. | Already support exchange of IWXXM messages based on FTBP in August 2015. | The viewpoint of line bandwidth, it will be 192KBps.
|  |  | Connection tests with USA 2000 - 2004 and put into operational use in 2005 and over CRV in February 2019. | It is possible to send , receive and transfer up to 2,147,483,647byte for the contents such as FTBP,IPM and IHE.
Connection tests with Hong-Kong and Singapore using AMHS/FTBP over CRV since December 2019 and testing is still on-going.
AMHS/FTBP over CRV implementation with China in 4Q2020,and with Korea in 1Q2021
5 | Macao China | Macao China | Q4/2009 | Q3/2021 | To be determined
6 | Philippines | Philippines/ATMC Manila | Completed March 2018 | Can support IHE and FTBP maximum 1MB (tested with Taipei on 13-May-20) | 1MB
Philippines has contracted 2Mbps bandwidth using CRV package “A” voice and data services.
7 | Republic of Korea | Gimpo international airport | ATN/AMHS with China put into operational use in June, 2011. | AMHS implementation for supporting FTBP and IHE will be in 4Q, 2022. | AFS links over CRV is a Package A, Bandwidth 2M.
AMHS implementation with China and Japan over CRV will be in 4Q, 2022.
8 | Singapore | Singapore | March 2011 | Yes | 2MB for CRV and minimally 64kbps for IPLCs