ATN/AMHS/AIDC Implementation Status in the APAC Region

| State/Organization | ATN G/G Boundary Intermediate System (BIS) Router/AMHS | AMHS Vendors Selected | AIDC | ATM System selected to support AIDC and Associated ICD (Implementation Status of the Basic 5 message set supported) | Remarks |
| --- | --- | --- | --- | --- | --- |
| AFGHANISTAN |  |  |  |  |  |
| AUSTRALIA | ATN tests were conducted. BIS Router and Backbone BIS Router and AMHS implemented. AMHS has been migrated to CRV. Connection with Singapore using AMHS was implemented October 2016; Another AMHS connections pending CRV (target date by March 2020) including both connection with New Zealand and USA. AMHS connection with Indonesia pending on CRV implementation AMHS connection with South Africa has been established Plan to upgrade AMHS support IWXXM traffic from Nov. 2020. | COMSOFT | AFTN/AMHS based AIDC Implemented between Brisbane and Melbourne, Oakland, Nadi and Auckland; Implemented between Melbourne and Johannesburg; AIDC is also in use between Melbourne and Mauritius; Operational trial between Brisbane and Ujung Pandang since May 2013. Implementation in July 2017. LOA needs to be updated. |  |  |
| BANGLADESH | In Q1/2013, Bangladesh installed ATN/AMHS and BIS Router at Dhaka (VGHS) with User Agents at Chittagong (VGEG) and Sylhet (VGSY). | COMSOFT | Tentative date of implementation of AIDC is Q4 of 2023 with Kolkata and Yangon. |  | Implementation of AIDC is included in the “Modernization of CNS-ATM System of CAAB” project which is going on G2G agreement with French Government and likely to be implemented by the end of 2023. |
| BHUTAN | ATN/AMHS circuits, using IP over VPN, with Thailand (Bangkok) and India (Mumbai) commissioned in June and July 2017 respectively. IOT and POT with Mumbai completed on 27th June 2017. IOT and POT with Thailand completed on 2nd May 2017. TMC signing with both countries at final stage. | AEROTHAI’S AMHS System | Currently not applicable. If required in the future, will be decided after CRV implementation (scheduled for mid-2019). |  |  |
| BRUNEI DARUSSALAM | ATN BIS Router planned for 2015 and AMHS planned for 2015 |  |  |  |  |
| CAMBODIA | BIS Router and AMHS installed. Cambodia (CATS) AMHS connected with Bangkok via VSAT IP link since 10 December 2013 | AVITECH | AIDC function and capability made available. Ready for testing with neighbors ATS Facilities starting from 2017 and target date of implementation with Bangkok in 4Q2019 | THALES which supports AIDC ICD Version 1. |  |
| CHINA | ATN Router and AMHS including NCC deployed in 2008 which is being upgraded to support ATN/IPS with target date of completion in December 2013. The Beijing-Hong Kong AMHS link was put into operation in 2018; With Thailand is completed POT, after sign the TMC was put into operation in Q12020 AMHS/ATN technical tests with Macau completed in 2009. Plan for ATN/AMHS implementation with Macao China is TBD. ATN/AMHS circuit with ROK has been put into operation since June 2011. ATN/AMHS tests with India has been put into operation since 2016. ATN and AMHS IOT with Mongolia is completed in May 2018. Plan for commissioning after POT completion in 2020 Connection tests with Nepal is TBD. AMHS testing with Japan in Q4 2020. AMHS testing with Russia in 2020. | IN-HOUSE (Aero-Info Technologies Co., Ltd) | AIDC between some of ACCs within China has been implemented. AIDC between several other ACCs are being implemented. AIDC between Sanya and Hong Kong China put into operational use since 8 Feb 2007. AIDC between Dalian and Incheon implemented in Nov. 2016; AIDC between Shanghai/Guangzhou and Tapei put in to operational use since 2013. AIDC between Guangzhou and Hong Kong China put into operational use since May 2018. OLDI between Shenyang and Khabarovsk put into operational use since Oct.2019. For Beijing/Ulaanbaatar, Further testing is planned in 2020. Kunming/Yangon under test and progress since May 2017 Kunming/Vientiane under test and progress since Dec. 2018. Sanya/Hanoi under test trial since 2019. | ATN Router and AMHS including NCC deployed in 2008 which is being upgraded to support ATN/IPS with target date of completion in December 2013. The Beijing-Hong Kong AMHS link was put into operation in 2018; With Thailand is completed POT, after sign the TMC circuit and was put into operation in Q12020 AMHS/ATN technical tests with Macau completed in 2009. Plan for ATN/AMHS implementation with Macao China in 2019. ATN/AMHS circuit with ROK has been put into operation since June 2011. ATN/AMHS tests with India has been put into operation since 2016. ATN and AMHS IOT with Mongolia is completed in May 2018. Plan for commissioning after POT completion in 2020 Connection tests with Nepal is TBD. AMHS testing with Japan in 2020. AMHS testing with Russia in 2020 | IN-HOUSE (Aero-Info Technologies Co., Ltd) |
| HONG KONG, CHINA | Manila / Philippines CRV/AMHS circuit was put into operation in May 2019. Beijing / China ATN/AMHS circuit was put into operation in 2018. Plan to migrate to CRV in Q4 2020. Macao / China ATN/AMHS circuit was put into operation in December 2009. Wait for Macao to join CRV. Bangkok / Thailand ATN/AMHS circuit was put into operation use in 2014. Wait for Thailand to join CRV. Fukuoka / Japan Currently on AFTN. Plan to carry out IOT of CRV/AMHS in July 2020 and cut over to CRV/AMHS in Q3 or Q4 2020. HoChiMinh / Vietnam Currently on AFTN. Simple AMHS IOT was conducted in Dec 2019. Wait for Vietnam to join CRV. Taibei CRV/AMHS circuit was put into operation in June 2020. | COMSOFT | AFTN-based AIDC with Sanya put into operational use in Feb 2007. AIDC with Taibei put into operational use in Nov 2012. AIDC with Guangzhou put into operational use in May 2018. AIDC with Manila put in operational use in May 2019. | Raytheon ATM system Support AIDC ICD Version 3 commissioned in November 2016. | Already support exchange of IWXXM messages based on FTBP. Support of IHE is planned for October 2020. |
| MACAO, CHINA | ATN/AMHS interoperability test with Beijing commenced in March 2009. ATN/AMHS circuit with Hong Kong put into operational use in end Dec 2009. Upgrade of ATN/AMHS to support IPS and IWXXM planned with tentative target date of Q3 2021. | COMSOFT | [Not applicable for using AIDC, looking into the possible application between TWR and ACC/APP] |  |  |
| ## COOK ISLANDS |  |  |  |  |  |
| DEMOCRATIC PEOPLE’S REPUBLIC OF KOREA | The ATN BIS Router and AMHS planned for in 2011. |  | With neighboring ACCs to be implemented |  |  |
| FIJI ISLANDS | ATN BBIS IPS router and AMHS implemented over CRV for connection to USA in April, 2019 with Australia planned for June, 2019. . For connections with sub-regional centers: For New Caledonia using AMHS since 2017; For connection with Kiribati using UA/AMHS implemented in 2015. | COMSOFT | AFTN based AIDC implemented between Nadi/ Brisbane, Auckland and Oakland. | - Support and implemented AIDC messaging: ABI, EST, CPL, CDN, ACP, TOC, AOC with all three centers - AIDC ICD version 2.0 implemented with Auckland and Oakland. - AIDC ICD Version 1.0 implemented with Brisbane |  |
| FRANCE (French Polynesia Tahiti) | Planned for implementation of AMHS in 2020. Using IP with New Zealand since 2017. |  | Implementation of AIDC (based on Version 3) with adjacent centers (Oakland and Auckland) since 2009. | THALES EUROCAT for AIDC | Alternate routing for backup between Tahiti and Christchurch via Tahiti/New Caledonia IP link |
| INDIA | Dual stack ATN/IP router and AMHS implemented at Mumbai in 2011. Operational AMHS connections with Bangkok, Dhaka, Singapore, Kathmandu, Karachi implemented. With Beijing implemented in 2016; With Colombo implemented in May2017; With Bhutan implemented in July 2017; Planned for IOT with Nairobi and Muscat forQ4 2020. | COMSOFT | Initially-15-May-2017, AIDC implemented between Chennai and Kuala Lumpur with ABI and EST messages. India is currently using APAC AIDC ICD version 3. A. Implementation within India: Trials have been carried out between various ATS units listed below I Delhi: Ahmedabad, Varanasi, Nagpur I. Chennai: Mumbai, Kolkata, Trivandrum, Mangalore, Trichy, Hyderabad, Bengaluru II. Kolkata: Chennai, Nagpur, Varanasi, Guwahati III. Mumbai: Chennai, Ahmedabad, Nagpur AIDC operations between Chennai and Mumbai have been put into regular operations. B: Implementation with Neighbouring States: The status on trails with following ATSUs of neighboring FIRs is as under: - Chennai & Kuala Lumpur (Malaysia) – ABI, EST successful. CDN is done with voice confirmation. TOC/AOC will be implemented later. LOA signed. - Chennai & Male (Maldives) –Trails have been successful. LOA in process. - Chennai & Colombo (Sri Lanka) - Colombo in process to address the syntax errors in ABI. Thereafter, trails will be conducted. LOA in - Chennai & Yangon (Myanmar) – Trials commenced in January 2018. Issues of incorrect reference number in Counter CDN from Yangon persists V. Mumbai & Male (Maldives) – Operational. LOA signed. VI. Ahmedabad & Karachi (Pakistan) – Automatic message exchange (e.g. ABI, EST) happens for most of the East bound flights between Karachi & Ahmedabad. Karachi Automation system not generating auto ACP message in response of EST messages. VII Kolkata & Yangon (Myanmar) – Trials under process. Most of the message exchanges were successful C. Under Planning I. To conduct operational trials between Mumbai-Muscat, Kolkata-Dhaka, Mumbai Karachi (Pakistan), Delhi – Karachi (Pakistan), Delhi – Lahore (Pakistan), Chennai-Jakarta and Varanasi-Kathmandu subject to readiness from the concerned states. II. AFTN (AMSS) system upgradation to IP based AMSS is underway at various stations to address the latency issues for exchange of AIDC data. |  |  |
| INDONESIA | ATN BIS Router and AMHS with Singapore implemented since February 2018; AMHS Trial (IOT) with Brisbane pending for CRV implementation. | IDS | AIDC implementation in Ujung Pandang ACC conducted as follows: - Ujung Pandang ACC –Brisbane ACC: Implemented since July 2017. - Ujung Pandang ACC – Manila ACC: - Operational trial since October 2019; - Target date for implementation in 3Q2020. - Ujung Pandang ACC – Kota Kinabalu ACC: - Successfully tested and target date for operational trial in 4Q2020; - Target date for implementation 1Q2021. - Ujung Pandang ACC – Oakland ARTCC: - Successfully tested and target date for implementation in 4Q2020. - Ujung Pandang ACC – Port Moresby ACC: - Successfully tested on 7 July 2020; - Target date for operational trial in 3Q2020. - Target date for implementation 1Q2021. - Ujung Pandang ACC – Jakarta ACC (4Q2020); AIDC implementation in Jakarta ACC will be carried out with the following priorities: - Jakarta – Ujung Pandang (4Q2020); - Jakarta – Chennai (3Q2021); - Jakarta – Melbourne (4Q2021); - Jakarta – Colombo (2Q2022); - Jakarta – Singapore (3Q2022); - Jakarta - Kuala Lumpur (4Q2022); - Jakarta – Kota Kinabalu (4Q2022). | Thales TopSky in Makassar able to support ICD version 3 since December 2015. | For CRV, target of contract in 4Q2020 and implementation in 1Q2021. Priority is in accordance with Hot Spot identified by RASMAG/23 |
| JAPAN | ATN BBIS router and AMHS installed at 2000. Connection tests with USA 2000 - 2004 and put into operational use in 2005. ATN BBIS router (to apply to Dual Stack) and AMHS (to upgrade in 2015. The connection test with each country which is not currently connecting is started after update. Upgrading connection with Hong Kong and Singapore using VPN will be implemented in 2020 after implementation of CRV. Coordinating for all other circuits upgrading. Connection tests with Hong-Kong and Singapore using AMHS/FTBP over CRV since Dec 2019 and testing is going. AMHS/FTBP over CRV implementation with Beijing/China in 4Q2020, and with Incheon/Korea in 1Q2021. | NEC | AIDC implemented between Fukuoka ATMC and Oakland ARTCC in 1998. AIDC implemented between Fukuoka ATMC and Anchorage ARTCC in 2005. AIDC implemented between Tokyo ACC/Fukuoka ACC and Incheon ACC in 2010. Implemented between Fukuoka and Incheon since June 2009. AIDC implemented between Fukuoka ACC/Naha ACC and Taibei ACC implemented. AIDC between Fukuoka ACC and Shanghai ACC under negotiation. |  | Japan and USA conducting testing AIDC over AMHS and cutover date is 5 May 2017. |
| KIRIBATI | Connection with Nadi using UA/AMHS implemented in 2015. |  |  |  |  |
| LAO PDR | ATN BIS Router and AMHS completed, planned for operation with Bangkok since 4Q 2016. | THALES | AIDC testing with Bangkok in 2017 and target for implementation in 4Q2019. Testing with Hanoi on-going since 2017; with Cambodia operational test again in June 2018, and implementation 2Q 2019. Testing with Kunming and Yangon ongoing. | THALES which is able to support ICD Version 2. |  |
| MALAYSIA | ATN BIS Router completed 2007. AMHS for Malaysia – Singapore implemented in March 2020. AMHS for Malaysia – Thailand implemented in Dec 2019. | FREQUENTIS | AIDC technical test between Kuala Lumpur ACC and Bangkok ACC conducted since November 2016 (ABI/EST/ACP/LAM/LRM/CDN/REJ/TOC/AOC). The operational trial commenced in August 2019 (EST/ACP/LAM/ LRM). The operational implementation commenced on 14th March 2020 (EST/ ACP/LAM/LRM). AIDC technical test between Kuala Lumpur ACC and Chennai OCC conducted since February 2013. The operational trial implemented in phases from September 2016 (ABI/EST/MAC/LAM/LRM/ACP). Review on the CDN message implementation conducted in August 2017. SOP signed 26 April, 2017. The MOU signed on March 2020. The operational implementation commenced on 1st April 2020 (ABI/EST/ ACP/LAM/LRM/CDN/REJ/MAC). The operational trial for TOC/AOC started on 1st July until 1st August 2020. AIDC technical test between Kuala Lumpur ACC and Singapore ACC conducted since April 2015 (ABI/EST/ ACP/LAM/LRM/CDN/REJ). The operational trial started on September 2018 (EST/ACP/LAM/ LRM). The operational implementation commenced on 1st November 2019 (EST/ ACP/LAM/LRM). AIDC technical test between Kuala Lumpur ACC and Ho Chi Minh ACC To Be Discussed (TBD). AIDC technical test between Kuala Lumpur ACC and Jakarta ACC TBD. AIDC technical test between Kota Kinabalu ACC and Manila ACC started on May 2019 (EST/ACP/ LAM/LRM). The operational trial plan to be started in 4Q2020 (EST/ACP/ LAM/LRM). The operational implementation plan to be started in 1Q2021 (EST/ACP/LAM/ LRM). AIDC technical test between Kota Kinabalu ACC and Ujung Pandang ACC started on August 2019 (EST/ACP/LAM/ LRM). The operational trial plan to be started in 4Q2020 (EST/ACP/ LAM/LRM). The operational implementation plan to be started in 1Q2021 (EST/ACP/LAM/ LRM). AIDC technical test between Kota Kinabalu ACC with Jakarta ACC TBD. AIDC technical test between Kota Kinabalu ACC and Singapore ACC started on November 2019 (EST/ACP/LAM/ LRM). The operational trial to be commenced on October 2020 (EST/ ACP/LAM/LRM). The operational implementation to be started in 1Q2021 (EST/ACP/LAM/ LRM). AIDC technical test between Kuching ACC and Singapore ACC started on November 2019 (EST/ACP/LAM/ LRM). The operational trial to be commenced on 20th July until 18th October 2020 (EST/ACP/LAM/ LRM). The operational implementation to be started in 4Q2020 (EST/ACP/LAM/ LRM). AIDC between Kuching ACC and Jakarta ACC TBD. | SELEX which is able to support ICD Version 3. |  |
| MALDIVES | In the process of replacing the existing operational AFTN system by AMHS. It is expected to complete the installation before the end of 2019. With the new AMHS, it is planned to establish a new IP connection between an additional neighboring ATSU as the current link is an X.25 connection between Colombo. Also will look for the possibility of implementing the CRV network to use with AMHS and AIDC during the same phase. |  | Connection established with all the adjacent ATSUs. Interoperability tests successfully completed in 2017. LOA signed for operational trials between Mumbai, Chennai, and Trivandrum. Operational trials were also successful with these ATSUs, while several issues were resolved from both ends. Ready to sign LOA with Melbourne and is expected during the 2nd quarter of 2019. Trials with Colombo had few issues, which Colombo is working to resolve it on their end with the automation system supplier. Connections between all 5 ATSUs are turned ON in the ATS automation system to conduct pre-notified operational trials. | SELEX which is able to support ICD Version 3. |  |
| MARSHALL ISLANDS |  |  |  |  |  |
| MICRONESIA (EDERATED STATES OF) |  |  |  |  |  |
| Chuuk |  |  |  |  |  |
| Kosrae |  |  |  |  |  |
| Pohnpei |  |  |  |  |  |
| Yap |  |  |  |  |  |
| MONGOLIA | AMHS/AFTN gateway implemented 2012. ATNBIS router implemented in 2014. ATN and AMHS IOT with China was completed in May 2018. Plan for commissioning after POT completion in 2019. | COMSOFT | ATM automation system supports both AIDC and OLDI. Coordinating with Russia on OLDI connection in target date 2016. Coordinating with China on AIDC connection between Beijing/Ulaanbaatar technical trials in progress. Planned date of testing in 2019. | INDRA Aircon 2100 supporting AIDC ICD Version 2. |  |
| MYANMAR | AMHS including AFTN/AMHS gateway implemented in Nov 2011. Connection with Thailand implemented in 4Q2016. Planned for AMHS connection with Beijing. Target date TBC. | THALES | AIDC connection pre- operation test with Thailand conducted in 4Q2017 and Target date of implementation 4Q2020; AIDC testing with Chennai, Kolkata and Vientiane conducted in 2020. Myanmar improved ATS Surveillance Coverage at coordination point with China and will start AIDC test again with Kunming ACC in 2020. | THALES Automation system (Topsky ATC) supports APAC AIDC ICD Ver. 2. | AMHS including AFTN/AMHS gateway implemented in Nov 2011. Connection with Thailand implemented in 4Q2016. Planned for AMHS connection with Beijing. Target date TBC. |
| NAURU |  |  |  |  |  |
| NEPAL | AFTN/AMHS Gateway implemented in 2012. AMHS implemented with India since June 2014. AFTN connection with China. Plan to test AMHS connection soon. | COMSOFT | Nepal uses custom built ATM system from NEC. Some issues regarding ICD need to be resolved in order to proceed ahead with AIDC testing with India and China. |  |  |
| NEW CALEDONIA | New router and AMHS commissioned December 2016 | COMSOFT |  |  |  |
| NEW ZEALAND | AMHS connection with the USA over CRV was implemented in April 2019. AMHS connection to Australia over CRV is scheduled for June 2019. | COMSOFT | AIDC implemented between New Zealand, Australia, Fiji, Tahiti, Chile and USA. | Supported the Basic 5 message set. ATM systems are LEIDOS and ADACEL |  |
| PAKISTAN | ATN/AMHS connections with Mumbai since 2015. Planning for AMHS connection with Beijing and Kuwait after upgrading existing facilities between the Countries. Target dates for implementation TBC. | COMSOFT | Implemented between Karachi and Lahore ACCs Further testing to be conducted between Delhi/Karachi & Delhi/Lahore after system upgradation at Indian end; Mumbai/Karachi &AHM/Karachi on trial operation. For testing with Muscat planned for 4Q2019. Coordination for testing with Tehran is in progress. | ATM system from Intra AIRCON 2100 | Existing Radar system being upgraded. |
| PAPUA NEW GUINEA | Currently AFTN over IP. AMHS implementation is planned for after successful implementation of CRV this year. AMHS implementation planned for 2020. | COMSOFT is the supplier of PNG AFTN/AMHS system | AIDC using AFTN operational with Australia, testing/trial with Oakland (USA) started late last year and in progress. AIDC implementation with Indonesia to happen after CRV implementation this year. | New ATM System from Thales (TopSky-ATC) implemented and operational now supports AIDC V3. |  |
| PHILIPPINES | New ATN/AMHS was installed at the New CNS/ATM Center in Manila. Site Acceptance was successfully done on October 2015. The new AMHS commissioned and operational in March 2018. The AMHS Implemented over CRV with HONG KONG - May 2019. The AMHS Implemented over CRV with TAIPEI - September 2019. Planned AMHS implementation over CRV with SINGAPORE by end of 3Q2020. Planned AMHS implementation over CRV with OAKLAND, USA by 1Q2021. | Frequentis - Comsoft | MANILA with: HONG KONG – Implemented May 2019 via CRV; SINGAPORE – Implemented November 2019 via X25; TAIPEI – Implemented December 2019 via CRV; UJUNG PANDANG - Operational Trial since April 2020 via SINGAPORE (X25); HO CHI MINH – Tests conducted on October 2019. For further tests; KOTA KINABALU – Tests conducted on May and October 2019 via SINAGPORE (X25). For further tests; OAKLAND – Planned AIDC tests after AMHS successful implementation. | THALES which is able to support ICD Version 2. | New ATN/AMHS was installed at the New CNS/ATM Center in Manila. Site Acceptance was successfully done on October 2015. The new AMHS commissioned and operational in March 2018. The AMHS Implemented over CRV with HONG KONG - May 2019. The AMHS Implemented over CRV with TAIPEI - September 2019. Planned AMHS implementation over CRV with SINGAPORE by end of 3Q2020. Planned AMHS implementation over CRV with OAKLAND, USA by 1Q2021. |
| REPUBLIC OF KOREA | ATN/AMHS circuit with China put into operational use in June 2011. AMHS implementation with China over CRV in 2Q2020. AMHS implementation with Japan over CRV in 4Q2020. | SAMSUNG | AIDC implemented between ACC and Fukuoka ATMC in 2010 AIDC between Incheon and Dalian implemented in Nov. 2016. | Rockheed Martin System |  |
| SINGAPORE | AMHS implemented. ATN/AMHS circuit with India put into operational use in March 2011. ATN/AMHS circuit with UK put into operational use in March 2012. ATN/AMHS circuit with Thailand put into operational use in December 2014. ATN/AMHS circuit with Australia put into operational use in October 2016. ATN/AMHS circuit with Indonesia put into operational use in February 2018. ATN/ AMHS circuit with Malaysia put into operational in March 2020. Inter-Operability Test (IOT) with Japan and Vietnam started in 2019. IOT with Philippines, Sri Lanka, Bahrain and Brunei targeted in 2020/2021. | FREQUENTIS COMSOFT | Operational with Ho Chi Minh implemented July 2014 Kuala Lumpur operational trial started since September 2018 and is implemented Nov. 2019. Manila operational trial started in February 2019. Implementation Nov. 2019 Technical trials with Jakarta ACC will be initiated once the Jakarta ACC ATMS renewal is completed. | THALES supports ICD Version 3 since December 2018 | AMHS implemented. ATN/AMHS circuit with India put into operational use in March 2011. ATN/AMHS circuit with UK put into operational use in March 2012. ATN/AMHS circuit with Thailand put into operational use in December 2014. ATN/AMHS circuit with Australia put into operational use in October 2016. ATN/AMHS circuit with Indonesia put into operational use in February 2018. ATN/ AMHS circuit with Malaysia put into operational in March 2020. Inter-Operability Test (IOT) with Japan and Vietnam started in 2019. IOT with Philippines, Sri Lanka, Bahrain and Brunei targeted in 2020/2021. |
| SRI LANKA | ATN BIS Router Planned for 2013. IP based AMHS implemented by Oct. 2017. - Mumbai tested May 2017 operational planned for Q4 2017; - Singapore testing in Q4 2017 operational for 2018; - Male testing and operational date TBD. | IDS | Trials with Male planned for in 3Q2019. Trial with Chennai on-going. Plan for implementation in 2018 and with Melbourne plan for 1Q2018. | INTELCAN which is able to support ICD Version 3. |  |
| THAILAND | BBIS/BIS Routers already implemented. AMHS has been implemented since July 2011. Connection with Bangladesh, Bhutan, Cambodia, China, India, Lao PDR, Myanmar, Singapore, Hong Kong China, and Malaysia implemented. Bangkok -Viet Nam Circuit - IOT Test: Done - POT Test: Planned for end of 3Q2020 Bangkok - Rome Circuit - IOT Test: Planned for 4Q2020 Connection with SITA (SITA AMHS Gateway inter-connections) implemented. | AEROTHAI's AMHS System | The implementation with - Malaysia has done on 14th March 2020 - Lao PDR has done on 14th July 2020 In addition, it is planned to implement AIDC with Cambodia and Myanmar by 3Q2020 and 4Q2020 consecutively. | THALES which supports AIDC feature, APAC AIDC ICD V.3. |  |
| TONGA | AMHS planned for 2008. The provider is linked to the New Zealand AFTN |  |  |  | CPDLC and ADS-C is not considered for lower airspace |
| UNITED STATES | - Australia (1/2019) - Fiji (1/2019) - New Zealand (1/2019) - Japan (2/2019) - Philippines (1Q2021) | IN-HOUSE | - Fiji, Japan, New Zealand, - Tahiti (via New Zealand), - Papua New Guinea (via Australia) (4Q2021) - Philippines (3/2021) - Indonesia via Australia (2020) - Russian Federation (pending joining CRV) | IN-HOUSE which is able to support APAC and NAT ICDs currently Version 2. |  |
| VANUATU |  |  |  |  |  |
| VIET NAM | AMHS (basic) implemented. Trial phase from 4Q/2015 to 3Q/2018. IOT with Thailand in progress from 4Q/2017 Plan to use AMHS in 4Q/2018; Planned for IOT with Hong Kong, Singapore and Thailand in 2019 For IOT with Laos PDR and Cambodia in 2019. | IN-HOUSE | Operational between Ho Chi Minh and Singapore since July 2014. Trial for additional messages sets since 2018. Implementation between Ho Chi Minh with Philippines planned for 4Q2020; Technical testing with Cambodia already done; Trials between Hanoi and Vientiane, Lao. PDR on going. with Malaysia TBC Testing with Cambodia on – going; For operation trial TBC. | Support ICD Version 1.0 with THALES at Ho Chi Minh ATM system. Support ICD Version 3.0 with Selex at Hanoi ATM System. |  |
| Wallis and Futuna (FRANCE) | AMHS implementation planned for end of 2017 |  |  | COMSOFT |  |

_ _ _ _ _ _ _ _ _ _ _ _ _