# CRV IMPLEMENTATION TABLE

| SN | State/ Administration (with* is BBIS; marked in blue- not yet join CRV/ no updates provided) | States connected | Intended date for CRV cut-over | Applications targeted | Migration scheme | Prerequisites/ dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Afghanistan |  |  |  |  |  |
| 2 | Australia* | Fiji New Zealand Indonesia PNG Singapore Japan | Contract in May2018 and service readiness in 3Q 2018 | AFTN, ADS-B, AMHS, Voice With: Australia February,2019(AMHS/AIDC), March,2019(Voice) Fiji March,2019 (AMHS June 2019/AIDC, Voice completed April) New Zealand, February, 2019 (AMHS June 2019, AFTN May 2019/AIDC), March, 2019 (Voice April 2019 completed) Indonesia 4Q2019 (TBC) (AMHS/AIDC, Voice, ADS-B); PNG 4Q2019(TBC), (AMHS/AIDC, Voice) Singapore 2Q2019 TBC (AMHS/AIDC, Voice); South Africa TBC 3Q2019 TBC (AMHS/AIDC, Voice); Japan would be end of 2019. | Staged approach | Termination of current COM contract |
| 3 | Bangladesh |  |  |  |  |  |
| 4 | Bhutan |  | Contract signed on Oct 2019. CRV installed successfully in Dec 2021. CRV P2P Test between Paro-Mumbai & Paro-Bangkok to be done once India and Thailand join CRV | AMHS first and Voice & ADS-B will follow up after AMHS. |  | Dependent on India and Thailand for utilization of CRV network. |
| 5 | Brunei Darussalam |  |  |  |  |  |
| 6 | Cambodia |  | As early as convenient, dependent on neighbouring countries |  |  | Internal decision making |
| 7 | China* | Hong Kong China Japan Republic of Korea | Contract signed on 21 June 2020. | Applications targeted: Data(AMHS) With: Hong Kong 3Q2020; Japan 4Q2020; Thailand TBD; India TBD. Republic of Korea 4Q2020 ATFM test with Japan and ROK at Sep 2020 over CRV | staged approach |  |
| 8 | Hong Kong, China* | Philippines China Japan Thailand Vietnam | Contract signed on 6 April 2018. Connection was installed successfully in June 2018. | With Manila CRV-Voice put into operation in August 2018 CRV-AMHS put into operation in May 2019 With Taibei CRV-AMHS put into operation in May 2020 With Fukuoka CRV-AMHS put into operation in September 2020 With Beijing CRV - AMHS POT in March and operation in April 2021 Bangkok and Hochiminh Subject to their readiness | staged approach | Need to coordinate with relevant CAAs/ANSPs in joining CRV in a harmonized manner, etc. |
| 9 | Macau China |  | Service readiness in Q4 2021 | To be confirmed | Staged approach | Migration from X.25 to IPS |
| 10 | Cook Islands |  |  |  |  |  |
| 11 | Democratic People's Republic of Korea |  | Contract in 3Q2018 and service readiness in 4Q2018 | AFTN and VoIP |  |  |
| 12 | Fiji* | Australia New Zealand USA | Contract in May 2018 and service readiness in 3Q 2018. | Data (AMHS) and VoIP With: Australia ATS voice April 2019 completed, AMHS completed in July 2019, NZ ATS voice completed April 2019 and USA ATS voice completed in March 2019 and AMHS completed in April 2019. | Staged approach | CBA, safety case |
| 13 | France (New Caledonia and French Polynesia) |  | 2023 is target for DNSA to sign contract subject to internal security assessment (done). | ATS Voice, AMHS with Fiji & AIDC, AMHS with USA, AIDC/AMHS with NZ. |  | CBA, cost must be affordable Wallis and Futuna: no dedicated connection to CRV |
| 14 | India* |  | Contract for CRV implementation with M/s PCCW in India will be signed in 3Q of 2021 and CRV Service will be ready in 4Q of 2021. | AFTN/AMHS,ADS-B,AIDC,ATS Voice | staged approach | Internal Administrative approvals & safety case |
| 15 | Indonesia |  | Contract in 3Q2021 and service readiness in 4Q2021. | AFTN, AMHS, ADS-B and voice |  | CBA completed |
| 16 | Japan* | Hong Kong China USA Singapore China RoK | Contract signed in Nov.2017 and service readiness in1Q 2018for Fukuoka | Data first with: Hong Kong completed 3Q2020 USA completed 1Q2019 Singapore completed 4Q2020 China completed 1Q2021 Voice Plan with: USA 2Q2021 Daegu and Incheon (R.O.K) started in1Q2021 | staged approach |  |
| 17 | Kiribati |  |  |  |  |  |
| 18 | Lao PDR |  |  |  |  |  |
| 19 | Malaysia |  | Contract to be signed 4Q 2020 and service readiness in 1Q 2021 | AFTN, AMHS, ADS-B and ATS voice | staged approach | New ATC centre operational in 2021 Contract issue with the new ATC main contractor. COM Project is part of the main contract. |
| 20 | Maldives |  |  |  |  |  |
| 21 | Marshall Islands |  |  |  |  |  |
| 22 | Micronesia (Federated States of) |  |  |  |  |  |
| 23 | Mongolia |  |  |  |  |  |
| 24 | Myanmar |  | Contract will be signed 4Q2020. | AFTN/AMHS, AIDC, ADS-B and voice | staged approach | One of counterparts join in |
| 25 | Nauru |  |  |  |  |  |
| 26 | Nepal |  | Nepal intends to join CRV on staged approach with AMHS data connectivity as first priority and intends to sign the contract with PCCW within 2020. |  |  |  |
| 27 | New Zealand | Australia USA Fiji French Polynesia Chile | Contract signed in July 2018 and service implemented December 2018 | Australia Voice Completed March 2019 and AMHS June 2019 Completed USA Voice Completed March 2019 and AMHS March 2019 Completed Fiji Voice Completed April 2019 French Polynesia AMHS and Voice Chile AMHS (SAM regional network REDDIG) | Awaiting French Polynesia joining. Awaiting outcome of inter-regional network connectivity discussion. For Chile | CBA attractive if all counterparts join in. |
| 28 | Pakistan |  |  |  |  |  |
| 29 | Palau |  |  |  |  |  |
| 30 | Papua New Guinea |  |  |  |  |  |
| 31 | Philippines | Hong Kong China China Singapore USA Indonesia | Contract signed in March 2018 and service readiness in 2Q2018 | Completed: with HONG KONG AIDC - 2Q2019; AMHS - 2Q2019; Voice - 3Q2018. with TAIPEI AIDC 4Q2019; AMHS 3Q2019; Voice 1Q 2019. with SINGAPORE AIDC – 4Q2019; AMHS –4Q2020; Voice – 1Q2020. with USA AMHS – 2Q2021; Voice – 4Q2019; with INDONESIA AIDC – 4Q2020. | staged approach | Success transition to the New ATM center in 4Q2018 |
| 32 | Republic of Korea | Japan | Contract in 3Q 2019 and service readiness in 4Q 2019 | Completed: with Japan Voice –March 2021 Planned; With Japan Voice additional lines-from 2022 to 2023 AMHS-4Q 2022 With China Data(AMHS)-4Q 2022 c Cp | staged approach |  |
| 33 | Samoa |  |  |  |  |  |
| 34 | Singapore* | Australia Japan Philippines | Contract signed in May 2019 and service readiness in Dec 2019 | Data (AMHS over IP) with: Australia Dec 2020 (completed); Japan Nov 2020 (completed); and Philippines Dec 2020 (completed);and Malaysia Q3 2021. Voice with: Philippines Mar 2020 (completed). | Staged approach | Singapore |
| 35 | Solomon Islands |  |  |  |  |  |
| 36 | Sri Lanka |  | As soon as CRV is available | AMHS connectivity with Mumbai, Singapore and Male. Direct Speech facilities with Chennai, Trivandrum, Mumbai, Male, Jakarta, Melbourne, Singapore | Phased approach with the implementation of CRV | CBA |
| 37 | Thailand* |  | Contract in 3Q2021 and service readiness in 1Q2022 | Data first Then voice, subject to safety case: China 1Q2022 Hong Kong 1Q2022; Singapore 1Q2022; India 2022. | Staged approach |  |
| 38 | Timor Leste |  |  |  |  |  |
| 39 | Tonga |  |  |  |  |  |
| 40 | Tuvalu |  |  |  |  |  |
| 41 | United States* | Australia Fiji Japan Philippines New Zealand Papua New Guinea Tahiti Russia | Contract in January 2018 | - AMHS with Australia Fiji Japan Philippines New Zealand Papua New Guinea (2021) Indonesia (2022) - AIDC with Fiji Japan New Zealand Papua New Guinea (Direct planned 2021) Tahiti (via New Zealand) Indonesia (Direct planned 2022) Russia (when join CRV) - VoIP with Fiji Japan Philippines New Zealand Papua New Guinea (direct planned 2021) Indonesia (2022) Russia (when join CRV) | Staged approach |  |
| 42 | Valuatu |  |  |  |  |  |
| 43 | Viet Nam |  | To be confirmed later (After discussed with PCCW Global) |  |  |  |

_ _ _ _ _ _ _ _ _ _ _ _ _