## New SWIM Work Plan
SWIM TF Work Plan
Project Group | Old Task number | Old Task Description | New Task No | New Task Description | Objective and scope | Task Lead(s) | Planned Start | Planned completion | Dependencies | Guidance for SOW
Implementation Planning | 1-1 | Benchmarking of best practices | 1 | Regional implementation philosophy & roadmap | Develop and maintain the Asia/Pacific regional roadmap for SWIM implementation, including SWIM technical infrastructure, SWIM governance, aeronautical information service, flight information service, and weather information service | David Leow (Singapore) Dr. Amornrat Jirattigalachote (Thailand) | 2017 | 2018 | SWIM Task Force created, resources available Panels deliver as expected Task 1.7 (common vocabulary) | benchmark existing governance models (FAA, Europe), existing catalogues, existing arrangements for quality of service/SLA (availability/reliability), existing registries if any Benchmark mediation of legacy users Benchmark available existing SWIM and industry models for service descriptions ICCAIA IP13 to be included
|  | Guidance To States: Interregional workshop Develop SWIM implementation Guidance for phase 1 Develop SWIM implementation Guidance for phase 2 (dual operations) Regional workshops |  |  |  |  | 2017 2017 2017 2019 As needed | 2022 2017 2018 2020 | SWIM iKit (if confirmed by IMP) | From the task 1-3 APANPIRG WG/TF planning to use or using SWIM may need guidance (ad hoc basis) Guidance to States Mediation of legacy users Lessons learnt from ASEAN SWIM demonstration
|  | Guidance for publishers/consumers; |  |  |  |  | 2017 | 2018 | Task 1.1 Task 1-5 and 1-6 Task 1-4 (service descriptions) | Common vocabulary requirement on publishers and suscribers to use the common controlled vocabulary Should include developing a guide for the preparation of service descriptions (dependency = 1.4) Could include guidance for developers/publishers on a set of protocols/formats to use See WP/5 appendices b and c for FAA guidance Analyse which guidnace is necessary from IP/6 and WP/6
| 1-2 | SWIM Regional roadmap |  |  |  |  | 2019 | 2022 | SWIM Manual 10039 and Technical Manual | Roadmap needs to be updated to reflect the changes and developments that have occured in the last SWIM TF meetings. It needs to be more granular and help direct the work of the other task groups for APAC regional SWIM implementation. To decide and agree on the target architecture for APAC SWIM that will address all the members' concerns. To Include target timelines for the production of regional requirements and guidelines. To include plan for the actual implementation of the regional SWIM technical infrastructure, regional governance framework, Rregistry(s), and information services.
[7 empty] | 2022 | 2024 | New implementation Roadmap | 1st Set the timeframe for implementation 2nd Discuss with the TF and decide on the elements for impelementation 3rd Develop new roadmap for SWIM implementation.
SWIM infrastructure | 44569 | Regional SWIM Architecture | 2 | Regional SWIM infrastructure | • Define the high-level APAC SWIM Architecture including policies on implementation and distribution of SWIM services • Define the requirements for the APAC SWIM Infrastructure with the goal of ensuring technical interoperability • Outline policy to ensure backwards compatibility with non-SWIM capable entities • Develop a roadmap for the implementation of APAC SWIM Infrastructure | Mr. Xiaodong Lu (Japan) Mr. Yukinobu Ryu (Japan) Mr. Henry Chan (Hong Kong, China) | 2017 2021 | 2020 2023 | • Manual on SWIM, SARPS, PANS and Guidance material from IMP, CP or ATMRPP • Availability and capability of CRV implementation • Task 5 – Governance • Task 6 – Information Services • Task 8 – SWIM Service and Application Validation | Define a CRV-based APAC SWIM Architecture to assure interoperability during the transition period Develop APAC SWIM Infrastructure requirements based on the related ICAO documents Propose an approach to implement secure APAC SWIM Infrastructure by cooperating with Task 3 Security Services
| New | NA | 3 | Security service | • Advises TF Chair and Task Leads in the area of cybersecurity for APAC. Specific objectives include: • Determining the scope of security responsibility of SWIM, consistent with SWIM technical infrastructures envisioned by the ICAO Information Management Panel (IMP) and the APAC regional network infrastructures including the CRV. • Proposing a trust framework to ensure that the correct information is sent to the correct users, considering identity and access management initiatives (IAM) from member states. • Ensures interoperability of trust frameworks within APAC region and with other ICAO regions. • Developing SWIM Cyber Security Architecture Framework and SWIM security strategy for the Asia-Pacific Region. Analyses and capture SWIM security risks. • Provide security guidelines and best practices to be incorporated in SWIM APAC Governance activities. | Mr. Jim Laymon (USA) | 2023 | 2025 | ICAO 2022 approval of: 1. X.509 Certificate Policy for the International Aviation Trust Framework (IATF) Certification Authority 2. IATF CP Criteria and Methodology for Cross Certification Identity Management 3. IATF CP Life Cycle Management (CPLCM) Operating Rules, 4. International Aviation Trust Framework Bylaws 5. IATF Criteria and Methodology for Global Resilient Aviation Interoperable Network (GRAIN) | Objective: Proposing a trust framework to ensure that the correct information is sent to the correct users, considering identity and access management initiatives (IAM) from member states. Proposed Guidance: APAC establishment of a Regional SWIM PKI Policy Management Authority in alignment with ICAO IATF SARPS Objective: Ensures interoperability of trust frameworks within APAC region and with other ICAO regions. Proposed Guidance: APAC establishment of a Regional SWIM DT&E environment to conduct Interoperability testing with US FAA, EUROCONTROL and other Regional ANSPs. (MRTBO example) Objective: Developing SWIM Cyber Security Architecture Framework and SWIM security strategy for the Asia-Pacific Region. Analyses and capture SWIM security risks. Provide security guidelines and best practices to be incorporated in SWIM APAC Governance activities Proposed Guidance: FAA provide Technical interchange of SWIM IAM Phase 2 and SWIM IAM segment 3 planned investments that align with ICAO IATF requirements to include establishment of the FAA PKI Policy Management Authority to assist APAC development of SWIM Cyber Security Architecture Framework and PKI use governance.
Technical Architecture | 1-6 | Regional SWIM models | 4 | Development and maintenance of regional information exchange models | Support APANPIRG WG/TF regarding information exchange models and examine if any extension to the existing information exchange models, i.e. AIXM, FIXM, and IWXXM, and/or the new information exchange model(s) are required to support the Asia/Pacific regional operational requirements | Dr. Amornrat Jirattigalachote (Thailand) Mr. Wen Zhu (USA) | 2016 | 2017 TBD (Regional Extension will need to be maintained/updated to accommodate (i) new operational use cases and (ii) the release of new version of information exchange model(s)) | Global model definitions available | From the task 1-3 models may need extension /refinements - there is already a case for ATFM Interaction with "light" approach discussed by IMP, coordination with 1-7 Relation with CCB - coordination with task 1-4 Regional Extension may need refinement - There is already a case for ATFM and ATFM/A-CDM integration; Interaction with "light" approach discussed by IMP - Coordiantion with Task 9 Relation with CCB - Coordination with Task 5
Governance | 1-4 | SWIM governance | 5 | Regional SWIM Governance Framework | I. Establish a robust and sustainable Governance model to ensure that a common set of policies, rules, and standards for identifying, designing, implementing, discovering, and operating SWIM-enabling components is consistently applied and enforced throughout the APAC. II. Develop or adopt standards, policies, and procedural guidelines to support the functional requirements for implementing all aspects of service-oriented development in the context of APAC SWIM. III. Facilitate visibility and control for insight into all APAC SWIM-enabled services by supporting developments of flexible mechanisms for service discovery, including, but not limited to, service registries. | Mr. Dongkie Park (ROK) Mr. Mark Kaplun (USA), Mr. Yukinobu Ryu (Japan) Mr. Xiaodong Lu (Japan), Ms. Honglei Gao (China) | 2016 | TBD (Note: SWIM Governance will be implemented throughout the SWIM lifecycle.) | I. Procedures for Air Navigation Services (PANS) Information Management (IM), Volume I System Wide Information Management II. Manual on System Wide Information Management (SWIM), Doc 10039, VOLUME I: SWIM Concept III. SWIM Discovery Service Implementation Specfication Service Description Conceptual Model (SDCM) IV. APAC SWIM Roadmap | I. Effective governance will result in more consistent decision-making and reduce risk and uncertainty. II. Identify new areas for policy development based on collected input and present them to the APAC SWIM TF. III. Further update the SDS solution to reflect user experience, lessons learned, and emerging technological solutions. IV. Facilitate ongoing engagement with SDS implementers through regular feedback and reviews. V. Concentrate on what really needs to be delivered to SWIM consumers. VI. Ensure that consumers' and providers' needs are met by developing a comprehensive SLA-management solution that can be adapted to multiple states' SWIM deployment scenarios.
| 1-5 | Design Regional SWIM Registry and architecture for phase 2
| 2-1-2 2-1-4 | Implement SWIM registry and architecture Guidance and Requirements for Publishers and Consumers
Information Services | 37258 | Promote new needs and new services and maintain database of publishers (ID/access points/services/interface/format..) pending registry implementation | 6 | Information services | To develop and define the APAC version of the SWIM information service overview specifications and APAC version of data catalogue for information services based on operational needs in APAC. | Mr. Marco Kok (Hong Kong, China) | 2017 | 2023 | Dependent on new use cases and operational needs identiifed in APAC. | • Develop the APAC version of the required and optional information services for ANSP to prioritize the implementation of services • Develop the APAC version of data catalogue for information services • Identify any additional optional fields required for SWIM service overviews in APAC in addition to those as defined in PANS-IM
Validation & Demonstration | 2001-01-02 | Promote new needs and new services and maintain database of publishers (ID/access points/services/interface/format..) pending registry implementation | 7 | SWIM Demonstration | • Report on the SWIM in ASEAN demonstration, particularly the lessons learnt • Track and observe SWIM demonstrations and trials within the Asia/Pacific region and ensure that reports of those demonstrations and trails are presented to the SWIM Task Force • Provide, if requested, support for regional SWIM demonstrations | Mr. David Leow (Singapore) Dr. Amornrat Jirattigalachote (Thailand) | 2017 | 2019 |  | An "Excel" file? Include service descirptions etc Assume registry services can be available on CRV from 2019 onwards 70 FAA applications are available for use and should be referenced in the catalogue
| 36924 | SWIM generalization |  |  |  |  | 2021 | TBD (Depening on the demonstration/trial to be conducted in APAC) | Demonstration/Trial to be conducted within APAC
| 2-1-3 | Support validation and publication of SWIM based applications | 8 | SWIM services and application validation | • Construct a platform for SWIM service and application validation • Support the implementation of SWIM service and applications • Support the demonstration of SWIM based operations | Mr. Yukinobu Ryu (Japan) Mr. Xiaodong Lu (Japan) Ms. Honglei Gao (China) Mr. Dongkie Park (ROK) | 2017 2020 | 2019 2023 | • Manual on SWIM, SARPS, PANS and Guidance material from IMP, CP or ATMRPP • The status of SWIM TI implementation in APAC Region • Task 2 – Regional SWIM Infrastructure • Task 3 – Security Services • Task 5 – Governance • Task 6 – Information Services | Support the validation of FF-ICE/R1 service Develop validation requirements for Regional SWIM Infrastructure Support the validation of Regional SWIM Infrastructure with Security Services via the joint demonstration Support the validation of required SWIM services and applications for different operation levels
Coordination and Promotion | 1-7 | Monitoring of panels work | 9 | Monitoring of panels work | Monitor developments by IMP and escalate issues/inputs as required | Mr. Yukinobu Ryu (Japan) | 2016 | 2022 | SWIM Manual and Technical Manual | Escalate issues to the panels Report back from panels 2 IMP meetings per year, monthly conferences A need for a Discussion paper at IMP (deliverable of the task) Focal point for common controlled vocabulary, in coordination with 1-4 Version management should be coordinated regarding backward compatibility and the content of models (FIXm, AIXM) Focal pint to trigger change requests to the models
| 1-3 | Regional coordination within APAC and guidance and training to APANPIRG bodies | 10 | Regional coordination and SWIM-related information sharing | • Identify SWIM related activities (and their interdependencies) in planning or development within other WGs and TFs. • Liaise with relevant regional TF/WG to refine operational and communications requirements (ATFM SG, MET IE, AAITF, ACSICG, CRV OG, etc). • Provide guidance to APANPIRG WG/TF using SWIM. • Influence outcomes from other WGs and TFs that will support successful expansion of SWIM (eg: development of SWIM compatible CRV). • This involves confirming inclusion on agendas and appropriate discussions ensuing | Vacant | 2016 | 2022 | SWIM Manual and Technical Manual Guidance on IWXXM | Use APANPIRG organizational chart Revise on an annual basis Establish simple "MOU" between concerned APANPIRG bodies
|  | Guidance and training to APANPIRG WG/TF : - Provide guidance to APANPIRG WG/TF using SWIM |  |  |  |  | 2017 2017 2017 2019 As needed | 2022 2017 2018 2020 | SWIM iKit (if confirmed by IMP) | From the task 1-3 APANPIRG WG/TF planning to use or using SWIM may need guidance (ad hoc basis) Guidance to States Mediation of legacy users Lessons learnt from ASEAN SWIM demonstration
| New | NA | 11 | SWIM implementation education and promotion (New task) | ● Creation of an educational and promotional program needed to support SWIM implementation, operations, and facilitate cooperation among stakeholders within the region. ● Collaboration with other APAC SWIM TF task to ensure cohesiveness between the guidance materials and educational material deliverable from the APAC SWIM TF. ● Management, organization, and dissemination of all APAC SWIM educational material ● Creation of an APAC SWIM education and promotional catalog | Mr. Thomas Green (USA) | 2022 | TBD (See dependancies) | Completion of this task is reliant on the work completed in Task 1-10. As the task are completed and guidance is created, the catelog can be populated.
Note on H6: Amornrat Jirattigalachote: To reflect the year the first version of regional SWIM implementation philosophy was presented, i.e. SWIM TF/3 in 2019.

## Old SWIM Work Plan
Project | Old Task number | New Task No | Old Task Description | New Task Description | Planned Start | Planned completion | Dependencies | Guidance for SOW | SOW (reference) | Task Lead(s)
SWIM - Definition phase | 1-1 |  | Benchmarking of best practices |  | 2017 | 2018 | SWIM Task Force created, resources available Panels deliver as expected Task 1.7 (common vocabulary) | benchmark existing governance models (FAA, Europe), existing catalogues, existing arrangements for quality of service/SLA (availability/reliability), existing registries if any Benchmark mediation of legacy users Benchmark available existing SWIM and industry models for service descriptions ICCAIA IP13 to be included | 1-1 Benchmarking - SOW | David J. Almeida (USA)
|  |  | Guidance To States: Interregional workshop Develop SWIM implementation guidance for phase 1 Develop SWIM implementation guidance for phase 2 (dual operations) Regional workshops |  | 2017 2017 2017 2019 As needed | 2022 2017 2018 2020 | SWIM iKit (if confirmed by IMP) | From the task 1-3 APANPIRG WG/TF planning to use or using SWIM may need guidance (ad hoc basis) Guidance to States Mediation of legacy users Lessons learnt from ASEAN SWIM demonstration
|  |  | Guidance for publishers/consumers; |  | 2017 | 2018 | Task 1.1 Task 1-5 and 1-6 Task 1-4 (service descriptions) | Common vocabulary requirement on publishers and suscribers to use the common controlled vocabulary Should include developing a guide for the preparation of service descriptions (dependency = 1.4) Could include guidance for developers/publishers on a set of protocols/formats to use See WP/5 appendices b and c for FAA guidance Analyse which guidnace is necessary from IP/6 and WP/6
| 1-2 |  | SWIM Regional roadmap | Task 1 - Implementation Planning | 2019 | 2022 | SWIM Manual 10039 and Technical Manual | Roadmap needs to be updated to reflect the changes and developments that have occured in the last SWIM TF meetings. It needs to be more granular and help direct the work of the other task groups for APAC regional SWIM implementation. To decide and agree on the target architecture for APAC SWIM that will address all the members' concerns. To Include target timelines for the production of regional requirements and guidelines. To include plan for the actual implementation of the regional SWIM technical infrastructure, regional governance framework, Rregistry(s), and information services. | 1-2 Regional Roadmaps - SOW_TF1_AJv1 | David Leow (Singapore) and Amornrat Jirattigalachote (Thailand)
| 1-3 |  | Regional coordination within APAC and guidance and training to APANPIRG bodies |  | 2016 | 2022 | SWIM Manual and Technical Manual Guidance on IWXXM | Use APANPIRG organizational chart Revise on an annual basis Establish simple "MOU" between concerned APANPIRG bodies | 1-3 Regional Coordination - SOW_v0.1 | John Moore (IATA)
|  |  | Guidance and training to APANPIRG WG/TF : - Provide guidance to APANPIRG WG/TF using SWIM |  | 2017 2017 2017 2019 As needed | 2022 2017 2018 2020 | SWIM iKit (if confirmed by IMP) | From the task 1-3 APANPIRG WG/TF planning to use or using SWIM may need guidance (ad hoc basis) Guidance to States Mediation of legacy users Lessons learnt from ASEAN SWIM demonstration
| 1-4 |  | SWIM governance |  | 2018 | 2022 | SWIM Manual and Technical Manual draft SARPS (stable and mature) lessons learnt from existing governance models (FAA, Europe) | Should include all stakeholders in APAC Should identify SARPS and guidance issued by IMP/ATMRPP/METP Strong coordination required with 1-5 WP04 recommends two service Description models - task 1.4 to study options Version management should address backward compatibility and the content of models (FIXm, AIXM) possibility to operate PKI through the CRV service provider to be further explored | 1-4 SWIM Goverance - SOW_updated_fri | David Wills (New Zealand) for SWIM TF/1 and Mark Kaplun (USA) from SWIM TF/2
| 1-5 |  | Design Regional SWIM Registry and architecture for phase 2 |  | 2017 | 2019 | SWIM ConOPs and Technical Manual Overall requirements: Refer 2.5.4 of DOC 10039 | Should take into account how to efficiently implement 2.5.4 of DOC 10039. Search, access, discovery features Should include access control and search functionalities. Chapter 3.5 SWIM Registry For architecture should take into account CRV and that there is no central operational entity in APAC to run common services Input= paper about service description (FAA) Strong coordination required with 1-4 3 approaches proposed in WP07, not exclusive Not forget access to registries outside APAC Confirm if the option of PKI is suitable If yes coordinate with CRV OG to seek if PKI services provided by CRV provider would be a suitable option possibility to operate PKI through the CRV service provider to be further explored Consider SWIM architecture principles from IP02 | 1-5 SWIM Registry - SOW | Kang Jiseok (ROK) and David Leow (Singapore)
| 1-6 |  | Regional SWIM models |  | 2016 | 2017 | Global model definitions available | From the task 1-3 models may need extension /refinements - there is already a case for ATFM Interaction with "light" approach discussed by IMP, coordination with 1-7 Relation with CCB - coordination with task 1-4 | 1-6 SWIM Regional Models - SOW_TF1_AJv2 | Amornrat Jirattigalochote (Thailand)
| 1-7 |  | Monitoring of panels work |  | 2016 | 2022 | SWIM Manual and Technical Manual | Escalate issues to the panels Report back from panels 2 IMP meetings per year, monthly conferences A need for a Discussion paper at IMP (deliverable of the task) Focal point for common controlled vocabulary, in coordination with 1-4 Version management should be coordinated regarding backward compatibility and the content of models (FIXm, AIXM) Focal pint to trigger change requests to the models | 1.7 Monitoring Panels - SOW | Yukinobu Ryu (Japan)
SWIM Implementation Phase 1 - initial expansion of services and preparation of phase 2 | 2-1-1 |  | Promote new needs and new services and maintain database of publishers (ID/access points/services/interface/format..) pending registry implementation |  | 2017 | 2019 |  | An "Excel" file? Include service descirptions etc Assume registry services can be available on CRV from 2019 onwards 70 FAA applications are available for use and should be referenced in the catalogue | 2-1-1 SWIM IMP Phase 1 - SOW_v1 | Marco Mang Hin Kok (Hong Kong China)
| 2-1-2 |  | Implement SWIM registry and architecture |  | 2019 | 2022 | Task 1-5 completed CRV implemented | Assume registry services can be available on CRV from 2019 onwards Design and implement a mediation service (see SWIM TF-1, WP05) | 2-1-2 SWIM Registry - SOW | David Leow (Singapore)
| 2-1-3 |  | Support validation and publication of SWIM based applications |  | 2017 | 2019 | Availability of SWIM applications (task 2-1-2) SWIM registry and architecture (DNS service, security, etc) (task 2-1-4) Procedures/SLA: Task 1-4 Models: 1-6 | SARPS and guidance Envisage a regional validation as a final step - see report of SWIM TF-1 for large scale tabletop exercise | 2-1-3 SWIM IMP Phase 1 - SOW-v1 | Xiaodong Lu (Japan), Gao Honglei (China) and Jiseok Kang (Republic of Korea)
SWIM Implementation Phase 2 -generalization | 2-2-1 |  | SWIM generalization |  | 2022 | 2025 | SWIM Manual and Technical Manual National transition roadmaps Task 2-1-2 Task 2-1-3 Task 2-1-1 | Populate registry (2-1-2) using catalogue (2-1-1), and maintain it Make systematic cross-validation of new services using testbeds from 2-1-3 Optimize architecture on CRV (DNS, proxies) Assist States in their transition to full SWIM Assist States with LOA and guidance (1-1) | SOW to be drafted later on | TBD later on
| 2-2-2 |  | Facilitate dual operations |  | 2022 | 2025 |  | Operate a mediation service (see SWIM TF-1, WP05) until all states have transitioned to SWIM (2-2-1) | SOW to be drafted later on | TBD later on
Note on F5: Amornrat Jirattigalachote: To reflect the year the first version of regional SWIM implementation philosophy was presented, i.e. SWIM TF/3 in 2019.