# APAC CRV IMPLEMENTATION TABLE

Please review the following table and share updated information in track mode by email at vmeefuengsart@icao.int  and snibhani@icao.int

CRV focal points of States/Administrations are requested to also update the telecommunication infrastructure table on the CRV Portal (please click at the link to update the table) hosted by Airways New Zealand.

| SN | State/ Administration (with* is BBIS; marked in blue- not yet join CRV/ no updates provided) | States /Administrations connected | Intended date for CRV cut-over | Applications targeted | Migration scheme | Prerequisites/ dependencies |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Afghanistan |  |  |  |  |  |
| 2 | Australia* | Fiji New Zealand USA PNG Singapore | Contract in May2018 and service readiness in 3Q 2018 | AFTN, ADS-B, AMHS, Voice With: Completed: Fiji March,2019 (AMHS June 2019/AIDC, Voice completed April) New Zealand, February, 2019 (AMHS June 2019, AFTN May 2019/AIDC), March, 2019 (Voice April 2019 completed) Singapore Dec, 2020 (AMHS/AIDC); PNG June 2021 (AFTN) Oct 2021 (Voice) USA March 2019 (AFTN) March 2019 (Voice) Pending: South Africa TBC (AMHS/AIDC, Voice); Indonesia TBC 2022 (AMHS/AIDC, Voice, ADS-B); | Staged approach | Termination of current COM contract |
| 3 | Bangladesh |  |  |  |  |  |
| 4 | Bhutan | Thailand (Bangkok) | Contract signed on Oct 2019. CRV installed successfully in Dec 2021. CRV P2P Test between Paro-Bangkok completed. CRV P2P Test between Paro-Mumbai completed on Jan 2023 CRV cutover between Paro-Mumbai is scheduled on March 2023 | AMHS first. Voice and ADS-B – to be decided. | Staged Approach | Dependent on India for full utilization of CRV network. |
| 5 | Brunei Darussalam |  |  |  |  |  |
| 6 | Cambodia |  | As early as convenient, dependent on neighbouring countries |  |  | Internal decision making |
| 7 | China* | Hong Kong China Japan Republic of Korea | Contract signed on 21 June 2020. | Applications targeted: Data(AMHS) With: Hong Kong 3Q2020; Japan 4Q2020; Thailand TBD; India 2022. Republic of Korea 4Q2022 Mongolia 4Q2022 ATFM test with Japan and ROK at Sep 2020 over CRV ADP exchange with Mongolia 4Q2022 | Staged approach |  |
| 8 | Hong Kong, China* | Philippines China Japan Thailand Vietnam | Contract signed on 6 April 2018. Connection was installed successfully in June 2018. | With Manila CRV-Voice put into operation in August 2018 CRV-AMHS put into operation in May 2019 With Fukuoka CRV-AMHS put into operation in September 2020 With Beijing CRV - AMHS POT in March and operation in April 2021 With Bangkok CRV-AMHS put into operation in August 2022 With Hochiminh Subject to Hochiminh’s readiness | Staged approach | Need to coordinate with relevant CAAs/ANSPs in joining CRV in a harmonized manner, etc. |
| 9 | Macau China |  | December 2022 | To be confirmed | Staged approach | Migration from X.25 to IPS |
| 10 | Cook Islands |  |  |  |  |  |
| 11 | Democratic People's Republic of Korea |  | Contract in 3Q2018 and service readiness in 4Q2018 | AFTN and VoIP |  |  |
| 12 | Fiji* | Australia New Zealand USA | Contract in May 2018 and service readiness in 3Q 2018. | Data (AMHS) and VoIP With: Australia ATS voice April 2019 completed, AMHS completed in July 2019, NZ ATS voice completed April 2019 and USA ATS voice completed in March 2019 and AMHS completed in April 2019. | Staged approach | CBA, safety case |
| 13 | France: -New Caledonia -French Polynesia | Fiji New-Zealand | Q3/2023 Q3/2023 | ATS Voice, AMHS AFTN/AMHS with NZ. | Staged approach | Depends on an agreement with peer States on adding a layer of encryption (PSK) over CRV |
| 14 | India* | The GRE tunnels has been setup between: Mumbai–Bangkok, Mumbai- Singapore, Mumbai–Beijing and Mumbai-Paro. Mumbai-Kathmandu GRE Tunnel under tests Note: AMHS trails between Mumbai-Bangkok over CRV has been carried out successfully. AMHS trails between Mumbai-Singapore, Mumbai - Bhutan over CRV are presently in progress. | Contract for CRV implementation with M/s PCCW in India Signed on 15th March, 2022. CRV Circuit has been delivered in Dec, 2022. CRV Cutover: End of 1Q2023 | AFTN/AMHS, , ATS Voice & ADS-B | Staged approach | Note: On successful trial Operation with BBIS/BIS States, the CRV Cutover will be planned. |
| 15 | Indonesia |  | Contract in 1Q2022 and service readiness in 2023. | Australia 2023 (voice & data) Malaysia 2023 (voice) Papua New Guinea 2023 (voice) Philippine 2023 (voice) Singapore 2023(voice & data) USA 2023(voice) |  |  |
| 16 | Japan* | Hong Kong China USA Singapore China RoK Philippine | Contract signed in Nov.2017 and service readiness in1Q 2018 for Fukuoka | USA AMHS(1Q 2019) Voice(2Q 2021) Hong Kong, China AMHS(3Q 2020) Singapore AMHS(4Q 2020) China AMHS(1Q 2021) ATFM(1Q 2021) Taipei ACC Voice(1Q 2022) AIDC(planned 1Q 2023) R.O.K AMHS(4Q 2022) Voice(1Q 2021) and additonal line plan in progress AIDC(planned 1Q 2024) Philippine Voice(2Q 2022) | In progress |  |
| 17 | Kiribati |  |  |  |  |  |
| 18 | Lao PDR |  |  |  |  |  |
| 19 | Malaysia | Thailand Singapore Indonesia India | Contract signed between CAAM and PCCWG in Sept 2022. CRV service readiness started in Nov 2021. | Thailand 1) Network connectivity testing (AMHS/AIDC ) – Oct 2022 2) Completed cut over & migration (AMHS /AIDC) – Jan 2023 3) Voice & ADS-B (testing, migration- TBD Singapore 1) Network connectivity testing (AMHS/AIDC) – May 2022 2) Estimate cut over & migration (AMHS/AIDC) – Q1/2023 3) Voice & ADS-B (testing, migration- TBD India 1) Estimate network connectivity testing (AMHS/AIDC) – Q1/ 2023 2) Estimate cut over & migration (AMHS/AIDC) – Q1/2023 3) Voice & ADS-B (testing, migration- TBD Indonesia 1) Estimate network connectivity testing (AMHS/AIDC) – Q2/2023 2) Estimate cut over & migration (AMHS/AIDC) – Q2/2023 3) Voice & ADS-B (testing, migration- TBD | Staged approach |  |
| 20 | Maldives |  |  |  |  |  |
| 21 | Marshall Islands |  |  |  |  |  |
| 22 | Micronesia (Federated States of) |  |  |  |  |  |
| 23 | Mongolia | CAAM and PCCWG made ICMP package test in 2021. | Contract in 1Q2022 and service readiness in 4Q2022 | AFTN, ADS-B, AMHS, Voice With: China Dec, 2022(AMHS), (ADP) TBD Voice, ADS-B, AFTN Russia TBD (AFTN, ADS-B, AMHS, Voice) | staged approach | Negotiations with neighbouring countries and stakeholders on CRVs and its use are critical to implementation. |
| 24 | Myanmar | China , India, Thailand, Laos, Bangladesh. | Contract will be signed after discussed with PCCW Global. Implementation was targeted in Q4/2023 depends on PCCW’s proposal quotation. Already sent to high level questionnaire form V 2.1 in June 2021 and V 2.2 again to PCCWG in Feb 2023 to join the CRV implementation. | AFTN/AMHS, AIDC, ADS-B and Voice | Staged approach | Need to coordinate with relevant CAAs/ANSPs in joining CRV network to be harmonized regionally. |
| 25 | Nauru |  |  |  |  |  |
| 26 | Nepal |  | SO signed with PCCW | AFTN/AMHS | Staged Approach | BBIS-state India joining the CRV network, as most traffic is routed through it |
| 27 | New Zealand | Australia USA Fiji French Polynesia Chile | Contract signed in July 2018 and service implemented December 2018 | Australia Voice Completed March 2019 and AMHS June 2019 Completed USA Voice Completed March 2019 and AMHS March 2019 Completed Fiji Voice Completed April 2019 French Polynesia AMHS and Voice Chile AMHS (SAM regional network REDDIG) | Awaiting French Polynesia joining. Awaiting outcome of inter-regional network connectivity discussion. For Chile | CBA attractive if all counterparts join in. |
| 28 | Pakistan | China India | Duly Signed Service Order Form Submitted on 23rd Jan 2023 for Finalization / Execution of the Contract. As per timeline given by PCCW Global the CRV will be implemented by August / Sept 2023 | AMHS /AFTN / VOICE | In progress | Package-D is opted to establish link between China and India. Connectivity with other neighbouring regions / FIRs i.e. Tehran, Kuwait, Kabul & Muscat could be migrated on CRV only if the states join CRV. |
| 29 | Palau |  |  |  |  |  |
| 30 | Papua New Guinea | Australia USA-Oakland USA-Aireon |  | Australia: AFTN June 2021, Voice Oct 2021 USA-Oakland Voice November 2021 USA-Aireon Space based ADSB-July 2021 | Staged approach | Completed |
| 31 | Philippines | Hong Kong China Singapore USA Japan | Contract signed in March 2018 and service readiness in 2Q2018 | Completed: With HONG KONG AIDC - 2Q2019; AMHS - 2Q2019; Voice - 3Q2018. With SINGAPORE AIDC – 4Q2019; AMHS – 4Q2020; Voice – 1Q2020. With USA AMHS – 2Q2021; Voice – 4Q2019. With JAPAN Voice – 1Q2022. Operational Trial: With USA AIDC – 4Q2022 Planned: With INDONESIA Ujung Pandang Voice – 1Q2023 | staged approach | Success transition to the New ATM center in 4Q2018 Dependencies: AIDC with Kota Kinabalu implemented via BBIS Singapore AIDC with Ujung Pandang implemented via BBIS Singapore |
| 32 | Republic of Korea | Japan China | Contract in 3Q 2019 and service readiness in 4Q 2022 | Completed: with Japan Voice –March 2021 Data(AMHS) - December 2022 With China Data(AMHS) – November 2022 Planned; With Japan Voice additional lines-from 2022 to 2023 c Cp | staged approach | Data(AMHS) POT in 4Q and operation from 4Q 2022 |
| 33 | Samoa |  |  |  |  |  |
| 34 | Singapore* | Australia Japan Philippines Thailand | Contract signed in May 2019 and service readiness in Dec 2019 | Data (AMHS over IP) with: Australia Dec 2020 (completed); Japan Nov 2020 (completed); Philippines Dec 2020 (completed); Thailand Sep 2022 (completed); India Q1 2023 (in progress, testing completed); and Malaysia Q1 2023 (in progress, testing completed). Voice with: Philippines Mar 2020 (completed). | Staged approach |  |
| 35 | Solomon Islands |  |  |  |  |  |
| 36 | Sri Lanka | Planned: Australia India Indonesia Maldives Singapore | Nov-Dec 2022 | Q1 2023 - AMHS with Singapore TBD - AMHS connectivity with Mumbai, and Male. TBD - Direct Speech facilities with Chennai, Trivandrum, Mumbai, Male, Jakarta, Melbourne, Singapore. | Phased Approach | Package D is planned based on CBA conducted. Comparison of performance of Package D and existing IPLC circuit. |
| 37 | Thailand |  | - Contract in 3Q2021 Status: Completed - Service readiness in 2Q2022 Status: Completed | Data first Then voice, subject to safety case: Bhutan 3Q2022 (Completed) Hong Kong 3Q2022 (Completed); Singapore 3Q2022 (Completed); Malaysia 1Q2023(Completed); India 1Q2023; Beijing 2Q2023 | Staged approach |  |
| 38 | Timor Leste |  |  |  |  |  |
| 39 | Tonga |  |  |  |  |  |
| 40 | Tuvalu |  |  |  |  |  |
| 41 | United States* | Australia Fiji Japan Philippines New Zealand Papua New Guinea Tahiti Russia | Contract in January 2018 | - AMHS with Australia Fiji Japan Philippines New Zealand Papua New Guinea (2021) Indonesia (2022) - AIDC with Fiji Japan New Zealand Papua New Guinea (Direct planned 2021) Tahiti (via New Zealand) Indonesia (Direct planned 2022) Russia (when join CRV) - VoIP with Fiji Japan Philippines New Zealand Papua New Guinea (direct planned 2021) Indonesia (2022) Russia (when join CRV) | Staged approach |  |
| 42 | Vanuatu |  |  |  |  |  |
| 43 | Vietnam | Hong Kong, China Singapore Philippines | Contract signed in M 4Q/2022, Service readiness in May -2023 | AFTN/AMHS connectivity with Hong Kong Voice and AFTN/AMHS with Singapore Voice and AFTN/AMHS with Philippines | staged approach |  |

_ _ _ _ _ _ _ _ _ _ _ _ _