| Project Title | EUR Doc 031 Review Project Team (EUR Doc 031 Review- PT) |
| --- | --- |
| Parent Group | PCG |
| Project Supervisory body | EASPG |
| Project Period | December 2021 to May 2022 |
| Project Objective | To review the current EUR Doc 031, amend it with lessons learned from the COVID-19 pandemic crisis and consider the EUR/NAT DGCA meeting (29 Sep 2021) conclusions, as well as the HLCC outcome |
| Project High Level Tasks | - Based on lessons learned from the COVID-19 crisis and taking into consideration the discussions from the HLCC, identify the areas where the Doc 031 needs to be reviewed - Amend the risk register table and align it with the improved EACCC risk register - Consider the EUR/NAT DGCA meeting conclusions in the revision of EUR Doc 031 - Coordinate the revised version of EUR Doc 031 with all involved aviation stakeholders in the EUR Region - Develop the new edition of ICAO EUR Doc 031, ICAO Crisis Management Framework Document for endorsement by EASPG written consultation procedure before the end of April 2022 - Publish the new version of EUR Doc 031 before the end of May 2022 |
| Membership | ICAO, EC, EASA, EUROCONTROL Network Manager, States and stakeholders such as ACI, CANSO and IATA Note: Other subject matter experts may also participate, as deemed appropriate by the EASPG/PCG |
| Working arrangements | Virtual meetings and initial proposal developed for circulation amongst EACCC focal points and ANSISG members |
| Project Outcomes | Preparation of a new edition of ICAO EUR Doc 031, ICAO Crisis Management Framework Document |
| Project Lead | Tbd |
| Project Secretariat Support | ICAO EUR NAT Office |

--END--