## Sheet1
DEF ID | DEF Priority | State | DEF Type | DEF Req - ICAO Doc | DEF Req - Detail | DEF Descr | Reported by | Date Reported | DEF Rmk | Cor Act Recom ICAO | CAP Submited | CAP Description | CAP Exec Body | CAP / Expected Target Date | Last review | Date Removed
Remark: According to the Uniform Methodology, deficiencies are prioritized with regard to their implications on the safety or regularity and eficiency, as follows: U priority = Urgent requirements having a direct impact on safety and requiring immediate corrective actions. A priority = Top priority requirements necessary for air navigation safety. B priority = Intermediate requirements necessary for air navigation regularity and efficiency.
EUR-AIS-01-05 | A | Tajikistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 2004-01-12 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Tajikistan CAA | 2011-12-01
EUR-AIS-01-06 | A | Turkmenistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 2004-01-12 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Turkmenistan CAA | 2018-12-01
EUR-AIS-01-07 | A | Uzbekistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 2004-01-12 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Uzbekistan CAA | 2018-12-01
EUR-AIS-02-05 | A | Kyrgyzstan | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | COG/ AIM TF | 15/05/2008 |  | Implement QMS for AIS | N |  | Kyrgyzstan CAA | 2011-12-01
EUR-AIS-02-08 | A | Tajikistan | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | COG/ AIM TF | 15/05/2008 |  | Implement QMS for AIS | N |  | Tajikistan CAA | 2018-12-01
EUR-AIS-02-09 | A | Turkmenistan | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | COG/ AIM TF | 15/05/2008 |  | Implement QMS for AIS | N |  | Turkmenistan CAA | 2018-12-01
EUR-AIS-02-11 | A | Bosnia& Herzegovina | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | Eurocontrol / COG | 20/10/2009 |  | Implement QMS for AIS | N |  | Bosnia& Herzegovina CAA | 2011-12-01
EUR-AIS-02-12 | A | Greece | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | Eurocontrol / COG | 20/10/2009 |  | Implement QMS for AIS | N |  | Greece CAA | 2011-12-01
EUR-AIS-02-13 | A | Malta | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | Eurocontrol / COG | 20/10/2009 |  | Implement QMS for AIS | N |  | Malta CAA | 2011-12-01
EUR-AIS-04-01 | A | Azerbaijan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Azerbaijan CAA | 2011-12-01 |  |  | Proposal for deletion by COG/AIM TF-33
EUR-AIS-04-05 | A | Kyrgyzstan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Kyrgyzstan CAA | 2011-12-01 |  |  | Proposal for deletion by COG/AIM TF-33
EUR-AIS-04-08 | A | Tajikistan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Tajikistan CAA | 2011-12-01 |  |  | Proposal for deletion by COG/AIM TF-33
EUR-AIS-04-09 | A | Turkmenistan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Turkmenistan CAA | 2011-12-01 |  |  | Proposal for deletion by COG/AIM TF-33
EUR-AIS-05-01 | A | Bosnia& Herzegovina | Publication of air navigation obstacles in AIP | PANS AIM | Par. 4.1.1, Appendix 2 | Air navigation obstacles are not published in AIP | EANPG/56 | 2014-11-26 | Air navigation obstacles to be published in the National AIP section ENR 5.4 (EANPG Conclusion 54/8 refers) | Comply with ICAO SARPs | N
EUR-AIS-05-02 | A | Bulgaria | Publication of air navigation obstacles in AIP | PANS AIM | Par. 4.1.1, Appendix 2 | Air navigation obstacles are not published in AIP | EANPG/56 | 2014-11-26 | Air navigation obstacles to be published in the National AIP section ENR 5.4 (EANPG Conclusion 54/8 refers) | Comply with ICAO SARPs | N
EUR-AIS-05-03 | A | North Macedonia | Publication of air navigation obstacles in AIP | PANS AIM | Par. 4.1.1, Appendix 2 | Air navigation obstacles are not published in AIP | EANPG/56 | 2014-11-26 | Air navigation obstacles to be published in the National AIP section ENR 5.4 (EANPG Conclusion 54/8 refers) | Comply with ICAO SARPs | N
EUR-ATM-03-01 | A | Cyprus | ATS coordination procedures | An 11, EUR ANP | SARPs and reg. procedures related to coordination between ACCs | Safety deficiencies in the N part of Nikosia FIR |  |  | Long lasting issue. Any solution envisaged requires political agreement between the parties involved |  | N |  | Cyprus | 2011-12-01
EUR-ATM-03-02*,** | A | Turkey | ATS coordination procedures | An 11, EUR ANP | SARPs and reg. procedures related to coordination between ACCs | Safety deficiencies in the N part of Nikosia FIR |  |  | Long lasting issue. Any solution envisaged requires political agreement between the parties involved |  | N |  | Turkey | 2011-12-01
EUR-ATM-04-11 | U | Morocco | Provision of air space safety monitoring data | An 11 | Par. 3.3.5.1 | The State authority concened does not report the required data to the RMA | EUR RMA | 15/11/2007 | THE EUR air space SAFETY MONITORING REPORTS- Reporting Status "N" | Required monitoring data to be sent to the RMA on a regular basis | N |  | Morocco CAA | 2011-12-01 | COG/66 EUR RMA TBC?
*Note: Turkey expressed disagreement with deficiency (paragraph 6.12 of the EANPG/49 report refers). **Note: CAP under development. On-going negociations facilitated by EC, Eurocontrol and ICAO.
EUR-ATM-05-02 | A | Andorra | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-03 | A | Bosnia and Herzegovina | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-04 | A | Bulgaria | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-05 | A | Croatia | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-07 | A | Morocco | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-09 | A | Turkmenistan | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-MET-01-03 | A | Belarus | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | DMG of METG | 2013-09-01 |  | comply with SARPs | N |  |  | 2017-12-01 | METG/31 | EASPG /3 Dec.2021
EUR-MET-01-05 | A | Kyrgyzstan | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | DMG of METG | 2013-09-01 |  | comply with SARPs | N |  |  | 2017-12-01 | METG/31 | EASPG /3 Dec.2021
EUR-MET-01-07 | A | Monaco | METAR availability | EUR FASID | Table MET 1A | LNMC METAR not available internationally | DMG of METG | 2015-06-01 |  | Make LNMC METAR available internationally | N |  |  | 2017-12-01
EUR-MET-01-10 | A | Tajikistan | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | DMG of METG | 2013-09-01 |  | comply with SARPs | N |  |  | 2017-12-01 | METG/31 | EASPG /3 Dec.2021
EUR-MET-01-11 | A | Tajikistan | 24-hour TAF | EUR FASID | Table MET 1A | 24-hour TAF required, but 12-hour TAF provided for UTDD | DMG of METG | 2015-06-01 |  | Make 24-hour TAF available for UTDD | N |  |  | 2017-12-01
EUR-MET-01-12 | A | Turkmenistan | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | DMG of METG | 2013-09-01 |  | comply with SARPs | N |  |  | 2017-12-01
EUR-MET-01-13 | A | Turkmenistan | QMS | An 3 | Annex 3, 2.2.2 | establish and implement a properly organized quality system comprising procedures, processes and resources necessary to provide for the quality management of the meteorological information to be supplied to the users listed in 2.1.2 | WMO | 2017-09-19 |  | comply with SARPs | N |  |  | 2017-12-01 | COG/69
EUR-MET-01-14 | A | Uzbekistan | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | SADIS inventory | 2016-09-05 |  | comply with SARPs | N |  |  | 2017-12-31
EUR-AIS-06-01 | B | Albania | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 outside Tirana TMA | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 outside Tirana TMA should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  | 2016-12-01 | COG75/RCOG12
EUR-AIS-06-02 | B | Algeria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for DAAG 23 and Terrain dataset area 4 for DAAG 23 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-03 | B | Austria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LOWG 35C, LOWK 28R, LOWL 26, LOWL 08, LOWS 15, LOWW 16 and LOWW 29 and Terrain dataset area 4 for LOWG 35C, LOWK 28R, LOWL 26, LOWL 08, LOWS 15, LOWW 16 and LOWW 29 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-04 | B | Azerbaijan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UBBB 17 and UBBB 35 and Terrain dataset area 4 for UBBB 17 and UBBB 35 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-05 | B | Belarus | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 4 for UMMC 31 and Terrain dataset area 4 for UMMC 31 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-06 | B | Belgium | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EBBR 25L, EBBR 25R, EBCI 25, EBLG 05R, EBLG 23L, EBLG 23R, EBOS 08 and EBOS 26. and Terrain dataset area 4 for EBBR 25L, EBBR 25R, EBCI 25, EBLG 05R, EBLG 23L, EBLG 23R, EBOS 08 and EBOS 26. should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-07 | B | Bosnia and Herzegovina | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-08 | B | Bulgaria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LBSF 27 and Terrain dataset area 4 for LBSF 27 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-09 | B | Croatia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LDZA 05 and Terrain dataset area 4 for LDZA 05 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-10 | B | Czechia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LKMT 22 and LKPR 24 and Terrain dataset area 4 for LKMT 22 and LKPR 24 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-11 | B | Denmark | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for: EKAH 28L, EKBI 09, EKBI 27, EKCH 04L, EKCH 22L, EKEB 26, EKKA 27L and EKYT 26R. and Terrain dataset area 4 for: EKAH 28L, EKBI 09, EKBI 27, EKCH 04L, EKCH 22L, EKEB 26, EKKA 27L and EKYT 26R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-12 | B | Estonia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-13 | B | France | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LFBL 21, LFJL 22, LFOB 12, LFQQ 26, LFRB 25L and LFOK 10 and Terrain dataset area 4 for: LFBL 21, LFJL 22, LFOB 12, LFQQ 26, LFRB 25L and LFOK 10 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-14 | B | Georgia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12 | EASPG/3 Dec. 2021
EUR-AIS-06-15 | B | Germany | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EDDB 25, EDDB 07, EDDC 22, EDDE 28, EDDE 10, EDDF 07L, EDDF 07C, EDDF 07R, EDDF 25L, EDDF 25C, EDDF 25R, EDDG 25, EDDH 23, EDDK 32R, EDDK 14L, EDDL 05R, EDDL 23L, EDDL 23R, EDDM 08L, EDDM 08R, EDDM 26L, EDDM 26R, EDDN 28, EDDP 08L, EDDP 08R, EDDP 26L, EDDP 26R, EDDS 07, EDDS 25, EDDT 26L, EDDT 26R, EDDT 08L, EDDV 09L, EDDV 27R, EDDW 09, EDDW 27, EDFH 21, EDLV 27, EDLW 06, EDNY 24 and EDSB 21 and Terrain dataset area 4 for:EDDB 25, EDDB 07, EDDC 22, EDDE 28, EDDE 10, EDDF 07L, EDDF 07C, EDDF 07R, EDDF 25L, EDDF 25C, EDDF 25R, EDDG 25, EDDH 23, EDDK 32R, EDDK 14L, EDDL 05R, EDDL 23L, EDDL 23R, EDDM 08L, EDDM 08R, EDDM 26L, EDDM 26R, EDDN 28, EDDP 08L, EDDP 08R, EDDP 26L, EDDP 26R, EDDS 07, EDDS 25, EDDT 26L, EDDT 26R, EDDT 08L, EDDV 09L, EDDV 27R, EDDW 09, EDDW 27, EDFH 21, EDLV 27, EDLW 06, EDNY 24 and EDSB 21 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-16 | B | Greece | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LGAV 03L, LGAV 03R, LGAV 21L, LGAV 21R and LGTS 16 and Terrain dataset area 4 for LGAV 03L, LGAV 03R, LGAV 21L, LGAV 21R and LGTS 16.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-17 | B | Hungary | TOD | An 15 | Para 5.3.3.3 | Lack of Terrain dataset for TOD area 4 | AIM/SWIM Team | 2016-10-11 | Terrain dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for: LHBP 13L, LHBP 13R, LHBP 31L and LHBP 31R. | Provide the required terrain dataset(s) for TOD area 4. | N |  |  |  | COG75/RCOG12
EUR-AIS-06-18 | B | Iceland | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for BIKF 02, BIKF 11, BIKF 20 and BIKF 29 and Terrain dataset area 4 for BIKF 02, BIKF 11, BIKF 20 and BIKF 29.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-19 | B | Israel | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  | 2018-12-01 | COG75/RCOG12
EUR-AIS-06-20 | B | Italy | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LIMC 35R, LIMC 35L, LIME 28, LIMF 36, LIML 36, LIMP 20, LIPE 12, LIPH 07, LIPO 32, LIPQ 09, LIPX 04, LIPZ 04R, LIRF 16L, LIRF 16R and LIRF 34R and Terrain dataset area 4 for LIMC 35R, LIMC 35L, LIME 28, LIMF 36, LIML 36, LIMP 20, LIPE 12, LIPH 07, LIPO 32, LIPQ 09, LIPX 04, LIPZ 04R, LIRF 16L, LIRF 16R and LIRF 34R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-21 | B | Kyrgyzstan | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | COG/AIM TF | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | N |  |  |  | COG75/RCOG12
EUR-AIS-06-22 | B | Luxembourg | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for ELLX 24 and Terrain dataset area 4 for ELLX 24 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-23 | B | Malta | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LMML 32 and Terrain dataset area 4 for LMML 32 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-24 | B | Montenegro | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-25 | B | Morocco | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for GMMN 35L, GMMN 35R and Terrain dataset area 4 for GMMN 35L, GMMN 35R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-26 | B | Netherlands | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for EHAM 06, EHAM 18C, EHAM 18R, EHAM 27, EHAM 36C, EHAM 36R and EHBK 21 and Terrain dataset area 4 for EHAM 06, EHAM 18C, EHAM 18R, EHAM 27, EHAM 36C, EHAM 36R and EHBK 21 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-27 | B | Poland | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EPGD 29, EPKT 27, EPMO 08, EPKK 25, EPWA 11 and EPWA 33 and Terrain dataset area 4 for EPGD 29, EPKT 27, EPMO 08, EPKK 25, EPWA 11 and EPWA 33 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-28 | B | Portugal | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LPFR 28, LPPR 17 and LPPT 21 and Terrain dataset area 4 for LPFR 28, LPPR 17 and LPPT 21.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-29 | B | Romania | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LRAR 27, LRBS 07, LRCL 25, LRIA 14, LROP 08L, LROP 08R, LRTM 07, LRTR 11 and LRTR 29 and Terrain dataset area 4 for LRAR 27, LRBS 07, LRCL 25, LRIA 14, LROP 08L, LROP 08R, LRTM 07, LRTR 11 and LRTR 29 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-30 | B | Russian Federation | TOD | An 15 | Para 5.3.3.3 | Lack of Terrain dataset for TOD area 4 | COG/AIM TF | 2016-10-11 | Terrain dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for UHPP 34L, URWW 06, UWKD 11, UWUU 14R, UEEE 23L, ULLI 10R, 10L, 28R, UNKL 11, 29, UNNT 16, URMM 12, URRR 04, UUWW 19, 06, 24, UUDD 32R, 14R, UUEE 24L, 24R, 06R, UHWW 25L, UHHH 23L | Provide the required terrain dataset(s) for TOD area 4. | N |  |  | 2020-12-01 | COG75/RCOG12
EUR-AIS-06-31 | B | Serbia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LYBE 12 and Terrain dataset area 4 for LYBE 12 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-32 | B | Spain | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 forLEVD 23 and Terrain dataset area 4 for GCXO 30 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-33 | B | Sweden | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for ESGG 03, ESGG 21, ESMS 17, ESSA 19L, ESSA 01L and ESSA 01R and Terrain dataset area 4 for ESGG 03, ESGG 21, ESMS 17, ESSA 19L, ESSA 01L and ESSA 01R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-34 | B | Switzerland | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for: LSGG 22, LSZH 16 and LSZH 14. | Provide the required obstacle dataset(s) for TOD area 4. | N |  |  |  | COG75/RCOG12
EUR-AIS-06-35 | B | Tajikistan | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | COG/AIM TF | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | N |  |  |  | COG75/RCOG12
EUR-AIS-06-36 | B | North Macedonia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-37 | B | Tunisia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | Y | - Implementation of the National TOD policy - launch of an international call for tenders for the collection of obstacle and field data for 5 Tunisian INTL airports. (The obstacle collection surfaces take into consideration: 1. Areas 2a, 2b and 2d of Annex 15. 2. the surfaces of the final approach segments (LNAV & VNAV) of the PANS-OPS. 3. OLS of Annex 14. 4. the take-off surface The terrain data will comply with the requirements of Area 2 of Annex 15) - Collection of obstacle data of the Area 1 - launch of an international call for tenders for the collection of obstacle and field data for 04 Tunisian international airports. | OACA/CEO | 2023(Q1-Q2) | EASPG/3
EUR-AIS-06-38 | B | Turkmenistan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UTAA 12R, UTAA 30L, UTAA 12L, UTAA 30R and Terrain dataset area 4 for UTAA 12R, UTAA 30L, UTAA 12L, UTAA 30R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-40 | B | United Kingdom | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EGAA 17, EGAA 25, EGBB 15, EGBB 33, EGHH 26, EGGD 27, EGCN 20, EGNX 09, EGNX 27, EGPH 06, EGPH 24, EGPF 05, EGPF 23, EGNS 08, EGNS 26, EGNM 32, EGGP 27, EGKK 08R, EGKK 26L, EGLL 09L, EGLL 09R, EGLL 27L, EGLL 27R, EGGW 08, EGGW 26, EGSS 04, EGSS 22, EGCC 05L, EGCC 23R, EGNT 07, EGNT 25 and EGHQ 30 and Terrain dataset area 4 for EGAA 17, EGAA 25, EGBB 15, EGBB 33, EGHH 26, EGGD 27, EGCN 20, EGNX 09, EGNX 27, EGPH 06, EGPH 24, EGPF 05, EGPF 23, EGNS 08, EGNS 26, EGNM 32, EGGP 27, EGKK 08R, EGKK 26L, EGLL 09L, EGLL 09R, EGLL 27L, EGLL 27R, EGGW 08, EGGW 26, EGSS 04, EGSS 22, EGCC 05L, EGCC 23R, EGNT 07, EGNT 25 and EGHQ 30 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-41 | B | Uzbekistan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UTTT 08L, UTSA 07, UTSA 25 and Terrain dataset area 4 for UTTT 08L, UTSA 07, UTSA 25 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-07-01 | B | Russian Federation | Aeronautical information publication | An 11 An 15 | Par. 2.1.2, 2.1.3 Par 2.1.2 | Publication of the aeronautical information not in compliance with ICAO provisions | Ukraine | 16/10/2016 | Publication by the Russian Federation of several aeronautical information related documents, such as NOTAMs, AICs, Amendments, and Supplements to the AIP of the Russian Federation, concerning the Simferopol FIR | To remove the incompliant AIS publication | N |  |  |  | EANPG/59 RASG-EUR/06 |  | IOM 18-0151.RD was sent to ICAO HQ on 12 March 2018 ICAO COG/RCOG Air Navigation Deficiency Methodology review project team was established according to COG/71 RCOG/0/ C1. Progress of the PT work to be presented to the upcoming COG/72 RCOG/09 and the Spring COG/RCOG in 2019.