## Sheet1
(1) STATE | (2) AIP Data Set |  |  | (3) Obstacle Data Set for Area 1 |  |  | (4) Obstacle Data Sets for Airports (Area 2, 3, 4, as applicable) |  |  | (5) Instrument Flight Procedures Data Sets (IFPD) |  | (6) Airport Mapping Data Sets (AMD) |  |  | (7) Terrain Data Set for Area 1 |  |  | (8) Terrain Data Sets for Airports (Area 2, 3, 4, as applicable) |  |  | (9) Removal of AIP tables
| Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Will remove tables | Remarks (list of tables planned to be removed incl. removal date)
Albania | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 4.5; CSV | FC | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 4.5; CSV | 2a: FC / 3: no info / 4: NA | 2023/Q1 |  | TBD | TBD | Aerodrome mapping data sets are not made available for aerodromes regularly used by international civil aviation. Albania is working towards developing a policy that will enable compliance with the aerodrome mapping data sets requirements. | 2019/Q2 | GeoTIFF | FC | 2019/Q2 | GeoTIFF | 2a: FC / 3: no info / 4: NA Actually terrain data sets are provided to external parties contracted for instrument flight procedure designing, charting and minimum safety altitude warning purposes. | Yes | We intend to remove only AIP tables related to ATS routes. AIP tables related to obstacle data are already removed. ENR 3.3-2023/Q1 ENR 5.4-2019/Q2 AD 2.10-2019/Q2
Algeria | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Armenia | 2021/Q2 | Other | “ARMATS” have a local DB based on AIXM 5.1 | 2019/Q1 | CSV | FC | 2021/Q1 | CSV | 2a: FC / 3: no info / 4: FC (UDYZ) See eAIP Gen 3.1.6 | 2022/Q1 |  | 2021/Q2 | AIXM 5.1 |  | 2019/Q1 | CSV | FC | 2019/Q1 | CSV | 2a: FC / 3: no info / 4: FC (UDYZ) For further information see eAIP Armenia , Gen 3.1.6 | No | No
Austria | 2022/Q2 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec); Other | PC | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); Other | 2a: PC / 3: no info / 4: PC | TBD | Details will be provided as soon as a plan is available | TBD | TBD | Details will be provided as soon as a plan is available | 2021/Q4 | TBD |  | 2021/Q4 | TBD | 2a: no info / 3: no info / 4: NC Only available via the National Geodetic Institute (Federal Office of Metrology and Surveying) | Yes | only after a transition phase in which the present AIP-tables as well as the new digital data sets will be published in parallel.
Azerbaijan | 2022/Q2 | AIXM 5.1.1 (Eurocontrol Spec) | We expect to provide this service based on our system but as we are DP in EAD this data will be available through EAD platform | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | PC | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC | 2022/Q4 |  | 2022/Q4 | TBD | we need upgrades in the current system. Initially planned to investigate during 2020 | 2022/Q4 | TBD | NC | 2022/Q2 | TBD | 2a: NC / 3: no info / 4: NC The AIM system is under adaptation, expect to finish till the end of the year 2020. After will start activities in the area of Terrain Data Sets | No | No
Belarus | [5 empty] | FC |  |  | 2a: PC / 3: no info / 4: NC | [7 empty] | FC |  |  | 2a: NC / 3: no info / 4: NC
Belgium | TBD | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | FC Available at the National Geographical Institute | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD |  | TBD | TBD |  | 2019/Q1 | ESRI Shape Files | FC Available at the National Geographical Institute | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD | TBD
Bosnia and Herzegovina | No info | No info |  | No info | No info | NC | No info | No info | 2a: NC / 3: no info / 4: FC | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: NC / 3: no info / 4: FC | No info | No info
Bulgaria | TBD | AIXM 5.1.1 (Eurocontrol Spec) | Finalisation of new AIM system is expected in 2022 as enabler for this functionality | TBD | AIXM 5.1.1 (Eurocontrol Spec) | NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available | TBD | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available. | TBD | Data set is under development in AIXM 5.1. No plan for provision until newer version is adopted | TBD | TBD | AMDB is not considered by any of the stakeholders | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available. | Yes | TBD
Croatia | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Precondition is a successful deployment of the local DB | 2022/Q4 | CSV | NC Awaiting State eTOD policy | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: NC / 3: no info / 4: NC Awaiting State eTOD policy | TBD |  | TBD | TBD |  | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD | TBD
Cyprus | No info | No info |  | 0 | No info | FC | No info | No info | 2a: NC / 3: no info / 4: FC | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: NC / 3: no info / 4: FC | No | No
Czech Republic | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC The ANS CR currently provides the Obstacle Data Set for Area 1 on request. This Data Set is not according to Eurocontrol Specification which has not been published yet. | 2023/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: NC / 3: no info / 4: NC ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Obstacle Data Sets for Airports depends on the provision of the data from the relevant airports. | 2024/Q4 |  | 2023/Q4 | AIXM 5.1; AMXM | ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Airport Mapping Data Sets depends on the provision of the data from the relevant airports. | 2020/Q1 | GeoTIFF | FC | 2023/Q4 | GeoTIFF | 2a: NC / 3: no info / 4: NC ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Terrain Data Sets for Airports depends on the provision of the data from the relevant airports. | No | No
Denmark | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment of a new AIXM 5.1-based AIS production system (expected in- operation 2021), which will enable provision and exchange of AIP data set as a service. The AIP data set is the prime targeted dataset service. | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | NC Obstacle data set provision depends on the deployment of a new AIXM 5.1-based AIS production system, expected in operation in Q4 2021 | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC The plan for providing airport obstacle data set in AIXM depends on the deployment of a new AIXM 5.1-based AIS production system, expected in operation Q4 2021. | 2023 | In planning stage. | 2023 | AIXM | In planning stage | 2022 | In planning state | FC | No info | No info | 2a: NC / 3: no info / 4: NC | TBD | No decision has been made yet.
Estonia | No info | No info |  | No info | No info | PC | No info | No info | 2a: PC / 4: NA | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: FC / 3: no info / 4: NA | No info | No info
Finland | 2023/Q1 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC (Electronic list of obstacles) | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: PC / 4: FC | TBD |  | TBD | TBD |  | 2019/Q1 | GeoTIFF | FC | 2019/Q1 | GeoTIFF | 2a: FC / 3: no info / 4: FC | Yes | ENR 5.4-2020/Q1 AD 2.10-2020/Q1
France | 2022/Q2 | AIXM 5.1 | The existing AIP data set will be updated in accordance with national specifications as soon as they are available. | 2021/Q2 | XLS | FC AIXM 5.1 Obstacle Data Set will be provided in 2022 | 2021/Q4 | Shapefile | 2a: FC / 4: PC (LFBO,LFST,LFPG,LFBD,LFLL,LFPO,LFSB,LFLC,LFBP) Obstacle Data Set will be provided as a new AIS product | TBD |  | 2022/Q2 | AIXM 5.1 | AMDB is depending on the CINEA-funded GeoDB project (ongoing -> 2022) | Available | Available from the National Geographic Institute (IGN) | FC | 2021/Q4 | ASCII | 2a: FC 4: FC (LFBO,LFST,LFPG,LFBD,LFLL,LFPO,LFSB,LFLC,LFBP, LFBL LFJL, LFOB, LFQQ, LFRB and LFOK) | Yes | ENR 5.4 - Q2 2021
Georgia | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | The existing AIP data set will be updated in accordance with national specification as soon as it (specification) is available. | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | FC | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 4: NA The obstacle data set for Airports is available, however it has not been provided to the users (customers) yet. | 2020/Q4 |  | 2024/Q4 | TBD |  | 2020/Q4 | GeoTIFF | NC | 2020/Q4 | GeoTIFF | 2a: NC / 3: no info / 4: NA | Yes | TBD
Germany | 2024/Q3 | AIXM 5.1 | The publication of an AIXM 5.1 AIP data set depends on the implementation of the EAD data upload in AIXM 5.1 | 2020/Q2 | XML, CSV | FC | 2024/Q1 | AIXM 5.1 | 2a: NC / 4: NC Depends on the implementation of eTOD in Germany | No info |  | No info | No info |  | 2019/Q1 | TBD | FC Provided by BKG | 2019/Q1 | TBD | 2a: NC / 3: no info / 4: NC Provided by BKG | Yes | ENR 5.4-2020/Q2 AD 2.10-No
Greece | 2023/Q1 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2024/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | NC HANSP/AIS Div is the authorised Aeronautical Dataset Service Provider | 2024/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 4: NC HANSP/AIS Div is the authorised Aeronautical Dataset Service Provider | 2024/Q1 | HANSP/AIS Div is the authorised Aeronautical Dataset Service Provider | 2024/Q1 | TBD | HANSP/AIS Div is the authorised Aeronautical Dataset Service Provider | 2024/Q1 | TBD | NC | 2024/Q1 | TBD | 2a: NC / 3: no info / 4: NC HANSP/AIS Div is the authorised Aeronautical Dataset Service Provider | TBD | TBD
Hungary | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2016/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC | 2018/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: PC / 4: FC (2a for LHBP, LHUD available) | TBD |  | No info | No info |  | TBD | TBD | NC | 2022/Q4 | TBD | 2a: NC / 3: no info / 4: NC | Yes | AD 2.10-2018/Q4
Ireland | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 4: NC | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
Israel | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA
Italy | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | According to the current EAD development program ESI clients are not included in this EAD capability | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC | 2024/Q4 | According to the current EAD development program ESI clients are not included in this EAD capability | 2024/Q4 | TBD | According to the current EAD development program ESI clients are not included in this EAD capability | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC According to the current EAD development program ESI clients are not included in this EAD capability | No | No
Kazakhstan | [5 empty] | FC |  |  | 2a: FC / 3: no info / 4: FC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Kyrgyzstan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Latvia | 2020/2 | AIXM 5.1.1 (Eurocontrol Spec) | AIP Data Set will be provided as a new aeronautical information product as specified in latest ICAO provisions. The source for AIP Data Set is Integrated AIM DB (AIXM 5.1). AIXM 5.1 AIP Data Set using AIXM 5.1.1 will be prepared when the appropriate EUROCONTROL Specification will be ready. | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | FC Obstacle Data Set will be provided as a new aeronautical information product as specified in latest ICAO provisions. The source for Obstacle Data Set for Area 1 is Integrated AIM DB (AIXM 5.1). Obstacle Data Set for Area 1 using AIXM 5.1.1 will be prepared when the appropriate EUROCONTROL Specification will be ready. | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: FC / 3: no info / 4: FC (EVRA RWY18/36) Obstacle Data Set for Airports (Area 2, 3 and 4) will be provided as a new aeronautical information product as specified in latest ICAO provisions. The source for Obstacle Data Set for Areas 2, 3 and 4 is Integrated AIM DB (AIXM 5.1). Obstacle Data Set for Areas 2, 3 and 4 using AIXM 5.1.1 will be prepared when the appropriate EUROCONTROL Specification will be ready. | 2020/Q1 | Instrument Flight Procedure Data Sets will be prepared using AIXM 5.1.1 or AIXM 5.1.2 when the appropriate EUROCONTROL Specification will be ready. | TBD | AMXM 2.0 | PANS-AIM specifies 5.3.3.3 Aerodrome mapping data sets | 2019/Q1 | GeoTIFF | FC | 2019/Q1 | GeoTIFF | 2a: FC / 3: no info / 4: FC (EVRA RWY18/36) | Yes | TBD
Lithuania | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | We are planning to implement national data base until 2022/Q4 | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec); ESRI Shape | FC We are planning to implement national data base until 2022/Q4 | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec); ESRI Shape | 2a: PC / 3: no info / 4: PC We are planning to implement national data base until 2022/Q4 | 2022/Q4 | We are planning to implement national data base until 2022/Q4 | 2024/Q1 | ESRI shape | We are planning to implement national data base until 2022/Q4 | 2020/Q4 | GeoTIFF | FC | 2022/Q4 | GeoTIFF | 2a: FC / 3: no info / 4: FC We are planning to implement national data base until 2022/Q4 | Yes | AD 2.10-2020-22
Luxembourg | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | Luxembourg is focussing on the upstream data chain and the national data processes. Data sets will only be generated and provided after the required infrastructure is in place. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | NC Current TOD implementation approach under review. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | 2a: NC / 3: no info / 4: NC Current TOD implementation approach under review. | 2026/Q4 | Will be considered based on user requirements. | TBD | TBD | At present no user requirement for AMDB Sets | 2022/Q4 | TBD | NC | 2024/Q4 | TBD | 2a: NC / 3: no info / 4: NC will depend on the State's policy | Yes | Depending on user requirments the AIP tables provided as data sets may be removed from the AIP. All other tables will remain in the AIP
Malta | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info |  | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
Montenegro | No info | No info |  | No info | No info | NC | No info | No info |  | No info |  | No info | No info |  | No info | No info | FC | No info | No info |  | No info | No info
Morocco | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Netherlands | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info |  | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
North Macedonia | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2022/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | NC | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2022/Q3 |  | 2023/Q1 | TBD |  | 2022/Q1 | TBD |  | 2022/Q3 | TBD |  | Yes | TBD
Norway | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: FC / 3: no info / 4: FC | TBD |  | TBD | AMXM |  | 2019/Q1 | GeoTIFF; USGS DEM | FC | 2019/Q1 | GeoTIFF; USGS DEM | 2a: FC / 3: no info / 4: FC | Yes | ENR 5.4-2019/Q3 AD 2.10-2019/Q3
Poland | 2022/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | After Eurocontrol Specification Delivery est. Dec 2020 | 2022/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC After Eurocontrol Specification Delivery | 2022/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: NC / 3: no info / 4: NC Area 2 obstacle data set containing only data on obstacles penetrating Obstacle Limitation Surfaces (OLS) at the first stage. | 2023/Q4 | After Eurocontrol Specification Delivery | TBD | TBD |  | TBD | TBD | NC | TBD | TBD | 2a: no info / 3: no info / 4: NC | TBD | Depending on user requirments. Decision will be taken after public consultations.
Portugal | 2023 | AIXM 5.1.1 (Eurocontrol Spec) | Depends on the deployment of a new AIXM 5.1-based system (expected to enter in operation in 2022/Q2) and development of eEAD | 2023 | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | PC Depends on the deployment of a new eTOD database and on originators capability in providing data. Awaiting State eTOD policy | 2023 | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | 2a: PC / 3: no info / 4: NC (LPPT, LPPR, LPFR) Depends on the deployment of a new eTOD database (expected to enter in operation in 2022/Q2) | TBD | On planning stage | No info | No info | The provision of the Airport Mapping Data Sets depends on the provision of the data from the relevant airports | TBD | TBD | FC Only available via the National Geodetic Institute | TBD | TBD | 2a: NC / 3: no info / 4: NC (LPPT, LPPR, LPFR) will depend on the State's policy | TBD | No decision has been made yet
Republic of Moldova | 2023/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2017/Q1 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 5.1 | FC | 2017/Q1 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 5.1 | 2a: FC / 3: no info / 4: FC | 2025/Q4 |  | 2029/Q4 | ESRI shape file format |  | 2012/ Q1 | ESRI Grid; GeoTIFF | FC | 2017/Q1 | ESRI Grid; GeoTIFF | 2a: FC / 3: no info / 4: FC | No | No
Romania | 2023 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023), which will enable provision and exchange of AIP data set as a service. | 2023 | AIXM 5.1.1 (Eurocontrol Spec), CSV, ESRI Shape | NC Obstacle Data Set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023) and on originators capability in providing data. No State eTOD policy for Area 1. | 2023 | AIXM 5.1.1 (Eurocontrol Spec), CSV, ESRI Shape | 2a: NC / 3: no info / 4: NC Obstacle Data Set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023) and on originators capability in providing data. | TBD | After Eurocontrol Specification Delivery | No info | No info | The provision of the Airport Mapping Data Sets depends on the provision of the data from the data originators (airports). | Available | GeoTIFF; USGS DEM | FC | 2023 | GeoTIFF; USGS DEM | 2a: NC / 3: no info / 4: NC | TBD | No decision has been made yet.
Russian Federation | [5 empty] | FC |  |  | 2a: PC / 3: no info / 4: FC | [7 empty] | PC |  |  | 2a: PC / 3: no info / 4: PC
Serbia | No info | No info |  | No info | No info | NC | No info | No info | 2a: NC / 3: no info / 4: NC | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: NC / 3: no info / 4: NC | No info | No info
Slovakia | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Depends on the deployment of an AIXM 5.1-based AIS production system, which depends on migration to AIXM 5.1 EAD SDD (expected Q2 2024). | 2019/Q1 | AIXM 4.5 | FC | TBD | AIXM 4.5 or AIXM 5.1 according the date of implementation (see AIP DS remark) | Area 2 - NC (no data) Area 3 - NC (no data) Area 4 - PC (LZIB, LZKZ) Depends on data originators. | TBD | Data originator denies PT coding of conventional procedures | TBD | TBD | No such data available | 2019/Q1 | ESRI Grid; Other | FC | Area 2 AD by AD from 2022/Q1 to 2023/Q2 Area 3 2022/Q4 Area 4 FC from 2019/Q1 | ESRI Grid; Other | Area 2 follows LIDAR scanning of state teritory Area 3 fully depends on AD operators Area 4: FC | No | -
Slovenia | TBD | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | CSV, ESRI Shape | FC | TBD | AIXM 5.1.1 (Eurocontrol Spec) | 2a: FC / 3: no info / 4: FC | TBD |  | TBD | TBD |  | 2019/Q1 | ESRI Shape Files; CSV | FC | TBD | TBD | 2a: NC / 3: no info / 4: NC | No | AIP table
Spain | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | The AIP dataset might be available earlier on a beta test status. To guarantee the dataset as official AIP data processes have to be developed and implemented to guarantee that the final data sets maintain all data quality requirements. | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | FC Digital obstacle data already available on the AIP. Current work is to fix existing AIXM5.1 format known errors and prepare the processes to claim Obstacle Datasets availability | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: FC / 3: no info / 4: PC Digital obstacle data already available on the AIP. Current work is to fix existing AIXM5.1 format known errors and prepare the processes to claim Obstacle Datasets availability | TBD | Waiting to have more information on the coding guidelines and what is expected to be in this datasets. No current plans to develop them as part of the official AIP but some flight procedure data will be made accessible as digital data on an alpha digital data service. | TBD | TBD | Waiting to have more information on the coding guidelines and what is expected to be in this datasets. No current plans to develop them as part of the official AIP but some flight procedure data will be made accessible as digital data on an alpha digital data service. | 2022/Q4 | WMS; GeoTIFF | FC | 2022/Q4 | WMS; GeoTIFF | 2a: NC / 3: no info / 4: PC Most of the terrain datasets are already available with some limitations. New data is being acquired to provide full quality compliant datasets. | No | No
Sweden | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment of a new AIXM 5.1-based AIS production system (expected in- operation 2021), which will enable provision and exchange of AIP data set as a service. The AIP data set is the prime targeted dataset service. | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec); Other | NC | 2021/Q4 | Other | 2a: PC / 3: no info / 4: PC The plan for providing airport obstacle data set in AIXM depends on the deployment of a new AIXM 5.1-based AIS production system, expected in operation 2021. | 2022/Q4 | In planning-stage. This data set product/service is depending on originators capability in providing data, and how LFV can support with relevant interface/tools. The service depends on the deployment of a new AIXM 5.1-based AIS production system (expected in- operation 2021). | 2022/Q4 | AIXM; AMXM | In planning-stage. Airport Mapping Data Set provision is planned in conjunction with airports own production/services and LFV’s capability to produce/make data set available. To be continued. | 2021/Q1 | Other | FC | TBD | Other | 2a: NC / 3: no info / 4: NC The terrain data set will be provided by the Swedish mapping, cadastral and land registration authority and made available in the National Height Model SWEN17, equivalent to EGM96. | Yes | LFV considers removal of AIP tables as a step towards an efficient AIS provision, once data sets are established as a service. At the moment, LFV has no timetable for removal of AIP tables; this will be planned in-line with the capability of providing AIP data set (AIXM 5.1) and likely be a phased approach. The first AIP table-candidate to be removed is ENR 5.4 (En-route obstacles), currently published in parallel with the Obstacle data set available on LFV web.
Switzerland | 2019/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | The AIP Data Set is availbale on customer request from skyguide. | 2019/Q1 | Other | PC Currently under the responsibility of the Federal Office of Civil Aviation (REF AIP Switzerland GEN 3.1 § 6.2) | 2020/Q1 | Other | 2a: NC / 3:NC/ 4: NC Currently under the responsibility of the Federal Office of Civil Aviation (REF AIP Switzerland GEN 3.1 § 6.2) | 2020/Q1 | Not yet planned, as some Eurocontrol specifications are not available (e.g. conventional navigation flight procedures). However, PBN PROC data sets are available on customer request from Skyguide. | No info | No info | Is not provided in Switzerland currently | 2019/Q1 | ESRI Grid, GeoTiff | PC Currently provided by the Federal Office of Topography swisstopo (https://shop.swisstopo.admin.ch/en/products/height_models/dhm25) REF AIP Switzerland GEN 3.1 § 6.1 | 2019/Q1 | ESRI Grid, GeoTiff | 2a: PC / 3: PC / 4: PC Currently provided by the Federal Office of Topography swisstopo (https://shop.swisstopo.admin.ch/en/products/height_models/alti3D) REF AIP Switzerland GEN 3.1 § 6.1 | Partly | The removal of tables other than for obstacles is not considered yet. Discussions with the FOCA (CAA) are ongoing.
Tajikistan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Tunisia | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA
Turkey | 2025/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2014/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC Digital obstacle data already available on the AIP as of 2014/Q4 | 2014/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: FC / 3: no info / 4: FC Digital obstacle data for some AD already available on the AIP as of 2014/Q4, Currently all AD obstacle data set available on the AIP. | 2025/Q4 |  | TBD | TBD |  | 2014/Q4 | DTED; GeoTIFF | FC | 2016/Q4 | DTED; GeoTIFF | 2a: FC / 3: no info / 4: FC | Yes | AIP tables related to obstacle data are already removed. ENR 5.4-2014/Q4 AD 2.10-2014/Q4
Turkmenistan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Ukraine | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | FC | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: PC / 3: no info / 4: PC (UKHH, UKBB, UKLL) | 2025/Q4 |  | No info | No info |  | 2022/Q4 | ESRI Shape Files; GDB | FC | TBD | TBD | 2a: NC / 3: no info / 4: NC (UKHH, UKBB, UKLL) | No | No
United Kingdom | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | PC Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: PC / 3: no info / 4: PC Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | As Procedures are provided. Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan -Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM | Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2019/Q1 | GML; ESRI Shape Files; GeoPackage | PC UK Area 1 terrain dataset is widely available, more information to be provided in GEN 3.1.6. | 2022/Q1 | GeoTIFF; GML | 2a: PC / 3: no info / 4: PC Terrain datasets for Areas 2-4 provided directly by the aerodorme operators. More information to be provided in GEN 3.1.6.For Area 1: GML 3.2 and ASCII (DTM grid); GeoPackage, GML 3.2 and Esri shapefile (Contours). | Yes | UK CAA support the implementation of ICAO datasets, but also recognises the importance of keeping information in the AIP during a transition period, which will be as long as needed. No tables will be removed until there is a level of assurance that users are ready to use datasets instead of the AIP tables and no data will become unavailable to users.
Uzbekistan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC