## Sheet1
(1) STATE | (2) AIP Data Set |  |  | (3) Obstacle Data Set for Area 1 |  |  | (4) Obstacle Data Sets for Airports (Area 2, 3, 4, as applicable) |  |  | (5) Instrument Flight Procedures Data Sets (IFPD) |  | (6) Airport Mapping Data Sets (AMD) |  |  | (7) Terrain Data Set for Area 1 |  |  | (8) Terrain Data Sets for Airports (Area 2, 3, 4, as applicable) |  |  | (9) Removal of AIP tables |  | (10) Date of last update/review
| Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Provision date | Specification / Format | Remarks | Will remove tables | Remarks (list of tables planned to be removed incl. removal date)
Albania | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 4.5; CSV | FC | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 4.5; CSV | 2a: FC / 3: no info / 4: NA | 2023/Q1 |  | TBD | TBD | Aerodrome mapping data sets are not made available for aerodromes regularly used by international civil aviation. Albania is working towards developing a policy that will enable compliance with the aerodrome mapping data sets requirements. | 2019/Q2 | GeoTIFF | FC Only available via the State Authority for Geospatial Information (ASIG) | 2019/Q2 | GeoTIFF | 2a: FC / 3: no info / 4: NA Only available via the State Authority for Geospatial Information (ASIG) | Yes | ENR 5.4. and AD 2.10. already removed No other tables will be removed until there is a level of assurance that users are ready to use datasets instead of the AIP tables | 2023-01-23
Algeria | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Armenia | 2025/Q2 | AIXM 5.1.1 (Eurocontrol Spec) | Depends on the deployment of an AIXM 5.1-based AIS production system, which depends on migration to AIXM 5.1 EAD SDD (expected Q2 2025). | 2019/Q1 | CSV (xls) | FC | 2021/Q1 | CSV (xls) | 2: FC / 3: FC / 4: FC (UDYZ) 2:FC / 3:FC (UDSG) For further information see eAIP Armenia , Gen 3.1.6 | TBD | NI | TBD | TBD | Details will be provided as soon as a plan is available | 2019/Q1 | CSV (xls) | FC | 2019/Q1 | CSV (xls) | 2: FC / 3: FC / 4: FC (UDYZ) 2:FC / 3:FC (UDSG) For further information see eAIP Armenia , Gen 3.1.6 | No | No | 2023-02-01
Austria | 2022/Q2 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec); Other | PC | 2021/Q2 | AIXM 5.1.1 (Eurocontrol Spec); Other | 2a: PC / 3: no info / 4: PC | TBD | Details will be provided as soon as a plan is available | TBD | TBD | Details will be provided as soon as a plan is available | 2023/Q2 | GeoTIFF | FC (from 2023/Q2) Source: INSPIRE / BEV | 2023/Q2 | GeoTIFF | FC (for Area 2 from 2023/Q2) NC (for Area 3 and 4) | Yes | Will be implemented step by step (feature by feature) | 2023-02-01
Azerbaijan | 2022/Q2 | AIXM 5.1.1 (Eurocontrol Spec) | We expect to provide this service based on our system but as we are DP in EAD this data will be available through EAD platform | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | PC | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC | 2022/Q4 |  | 2022/Q4 | TBD | we need upgrades in the current system. Initially planned to investigate during 2020 | 2023/Q4 | TBD | NC | 2024/Q2 | TBD | 2a: NC / 3: no info / 4: NC The AIM system is under adaptation, expect to finish till the end of the year 2023. After will start activities in the area of Terrain Data Sets | No | No | 2023-02-01
Belarus | [5 empty] | FC |  |  | 2a: PC / 3: no info / 4: NC | [7 empty] | FC |  |  | 2a: NC / 3: no info / 4: NC
Belgium | TBD | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | FC Available at the National Geographical Institute | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD |  | TBD | TBD |  | 2019/Q1 | ESRI Shape Files | FC Available at the National Geographical Institute | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD | TBD
Bosnia and Herzegovina | TBD | AIXM 5.1 | We expect to provide this service but as we are DP in EAD (B2C client) this data will be available through EAD platform | NC | NC | NC | NC | NC | 2a: NC / 3: no info / 4: FC | NC |  | NC | NC |  | NC | NC | FC | NC | NC | 2a: NC / 3: no info / 4: FC | No info | No info | 2023-02-01
Bulgaria | TBD | AIXM 5.1.1 (Eurocontrol Spec) | Finalisation of new AIM system is expected in 2022 as enabler for this functionality | TBD | AIXM 5.1.1 (Eurocontrol Spec) | NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available | TBD | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available. | TBD | Data set is under development in AIXM 5.1. No plan for provision until newer version is adopted | TBD | TBD | AMDB is not considered by any of the stakeholders | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC Finalisation of new AIM system is expected in 2022 as enabler for this functionality. Currently the data is not available. | Yes | TBD
Croatia | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Precondition is a successful deployment of the local DB | 2022/Q4 | CSV | NC Awaiting State eTOD policy | 2022/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: NC / 3: no info / 4: NC Awaiting State eTOD policy | TBD |  | TBD | TBD |  | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC | TBD | TBD
Cyprus | TBD | AIXM 5.1.1 (Eurocontrol Spec) |  | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | FC | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | NC | TBD |  | TBD | TBD |  | TBD | TBD | NC | TBD | TBD | NC | TBD | TBD | Feb 23
Czech Republic | 2023 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2023 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC The ANS CR currently provides the Obstacle Data Set for Area 1 on request. This Data Set is not according to Eurocontrol Specification which has not been published yet. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: NC / 3: no info / 4: NC ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Obstacle Data Sets for Airports depends on the provision of the data from the relevant airports. | 2024/Q4 |  | 2024/Q4 | AIXM 5.1; AMXM | ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Airport Mapping Data Sets depends on the provision of the data from the relevant airports. | 2020/Q1 | GeoTIFF | FC | 2023 | GeoTIFF | 2a: NC / 3: no info / 4: NC ANS CR has not received all the needed data from the relevant airports so far, therefore the provision of the Terrain Data Sets for Airports depends on the provision of the data from the relevant airports. | TBD | A discussion with the CAA is needed. | Feb 23
Denmark | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment of a new AIXM 5.1-based AIS production system (expected in- operation 2021), which will enable provision and exchange of AIP data set as a service. The AIP data set is the prime targeted dataset service. | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | NC Obstacle data set provision depends on the deployment of a new AIXM 5.1-based AIS production system, expected in operation in Q4 2021 | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 3: no info / 4: NC The plan for providing airport obstacle data set in AIXM depends on the deployment of a new AIXM 5.1-based AIS production system, expected in operation Q4 2021. | 2023 | In planning stage. | 2023 | AIXM | In planning stage | 2022 | In planning state | FC | No info | No info | 2a: NC / 3: no info / 4: NC | TBD | No decision has been made yet.
Estonia | No info | No info |  | No info | No info | PC | No info | No info | 2a: PC / 4: NA | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: FC / 3: no info / 4: NA | No info | No info
Finland | TBD | AIXM 5.2 |  | 2019 | CSV | PC | 2019 | CSV | 2a: PC / 4: PC | TBD |  | TBD | TBD |  | 2019/Q1 | GeoTIFF | FC | 2019/Q1 | GeoTIFF | 2a: FC / 3: no info / 4: FC depending on the State's policy | Yes | ENR 5.4-2020/Q1 AD 2.10-2020/Q1 | 2023-02-23
France | 2025 Q1 | AIXM 5.1 | The existing AIP data set (AIXM 4.5) will be updated when the new AIM system (SEPIA) is operational | 2021/Q2 | XLS | FC AIXM 5.1 Obstacle Data Set will be provided in 2025 | 2021/Q4 | Shapefile | 2a: FC / 4: PC (LFBO,LFST,LFPG,LFBD,LFLL,LFPO,LFSB,LFLC,LFBP) Obstacle Data Set is provided as a new AIS product | TBD |  | 2025/Q1 | AIXM 5.1 | Aeronautical Mapping Data Set provision is depending on CINEA-funded Projects | Available | Available from the National Geographic Institute (IGN) | FC | 2021/Q4 | ASCII | 2a: FC 4: FC (LFBO,LFST,LFPG,LFBD,LFLL,LFPO,LFSB,LFLC,LFBP, LFBL LFJL, LFOB, LFQQ, LFRB and LFOK) | Yes | ENR 5.4 - Q2 2021 | 2023-02-23
Georgia | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | The existing AIP data set will be updated in accordance with national specification as soon as it (specification) is available. | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | FC | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: NC / 4: NA The obstacle data set for Airports is available, however it has not been provided to the users (customers) yet. | 2020/Q4 |  | 2024/Q4 | TBD |  | 2020/Q4 | GeoTIFF | NC | 2020/Q4 | GeoTIFF | 2a: NC / 3: no info / 4: NA | Yes | TBD
Germany | 2023/Q4 | AIXM 5.1 | Target date for the complete AIP dataset is 2023/Q4. Currently four data subsets are available. | 2020/Q2 | AIXM 5.1.1 | FC | 2024/Q1 | AIXM 5.1.1 | 2a: NC / 4: NC Ongoing implementation based on national eTOD policy | 2024/Q3 | Under development | tbd | AIXM 5.1.1 | AIS Provider Germany has not received data from all effected aerodromes. First datasets will be made available in 2023. | 2019/Q1 | TBD | FC Provided by BKG | 2019/Q1 | TBD | 2a: NC / 3: no info / 4: NC Provided by BKG | Yes | ENR 5.4-2020/Q2 AD 2.10-No | 2023-02-01
Greece | 2025/Q3 | AIXM 5.1 | The existing AIP data set (AIXM 4.5) will be updated, which depends on migration to AIXM 5.1 EAD SDD (expected 2025). | 2025/Q3 | AIXM 5.1 | Depends on migration to AIXM 5.1 EAD SDD (expected 2025). | TBD | AIXM 5.1 (Eurocontrol Spec) | NC HASP/AIS Div is the authorised Aeronautical Dataset Service Provider - Depends on the implementation of eTOD | TBD | Details will be provided as soon as a plan is available | TBD | TBD | AMDB is depending on the EAD migration | 2024/Q4 | TBD | NC | 2024/Q4 | TBD | 2a: NC / 3: no info / 4: NC | TBD | No decision has been made yet. | 2023-02-20
Hungary | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | The migrtion to the AIXM 5.1 EAD SDD is ongoing. A projekt will be planned after the successful migration. | 2016/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC | 2018/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: PC / 4: FC (2a for LHBP, LHBC, LHDC, LHNY, LHPP, LHPR, LHSM, LHUD available) | TBD |  | TBD | TBD |  | 2022/Q2 | DDM10 | NC | No info | TBD | 2a: NC / 3: no info / 4: NC | Yes | AD 2.10-2018/Q4 | 2023-01-01
Ireland | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 4: NC | No info |  | No info | No info |  | No info | No info | FC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
Israel | 2024/Q4 | AIXM 5.1 | Depends on the deployment of an AIXM 5.1-based AIS production system, which depends on migration to AIXM 5.1 EAD SDD (expected Q2 2024). | 2023/Q1 | CSV, EAD | NC | 2023/Q3 | CSV | 2a: NC / 3: no info / 4: NA | TBD | all FP are implemented into the EAD | 2022/Q4 | TBD | NC | No info | No info | FC | No info | No info | 2a and 3:FC / 4: NA | LLBG removed. | LLBG - AD 2.10 | 2022-02-01
Italy | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | According to the current EAD development program ESI clients are not included in this EAD capability | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC | 2024/Q4 | According to the current EAD development program ESI clients are not included in this EAD capability | 2024/Q4 | TBD | According to the current EAD development program ESI clients are not included in this EAD capability | TBD | TBD | NC | TBD | TBD | 2a: NC / 3: no info / 4: NC According to the current EAD development program ESI clients are not included in this EAD capability | No | No | 2023-01-01
Kazakhstan | TBD |  |  |  |  | FC | 2019/Q1 | AIXM 5.1 | 2a: FC / 3: no info / 4: FC | 2022/Q4 | Instrument Flight Procedure Data can be provided in the AIXM 5.1 | TBD | TBD |  | No info | No info | NC | 2019/Q1 | GeoTIFF | 2a: NC / 3: no info / 4: NC 2a, 3 for UAAA, UACC, UAII, UARR, UASK, UATE, UATG, UATT. 4 for UAAA, UACC, UATG | No | No | 2022-03-01
Kyrgyzstan | 2022 | AIXM 5.1.1 (Eurocontrol Spec) |  |  |  | NC |  |  | 2a: NC / 3: no info / 4: NC | 2025 | Instrument Flight Procedure Data can be provided in the AIXM 5.1 |  |  |  | No info | No info | NC | No info | No info | 2a: NC / 3: no info / 4: NC | No | No | 2023-03-01
Latvia | 2020/Q2 - initialy planned 2022/Q1 - implemented | AIXM 5.1 | FC AIP Data Set already provided since 2022/Q1. (WEF 27-JAN-2022). The source for AIP Data Set is Integrated AIM DB (AIXM 5.1). | 2019/Q1 | AIXM 5.1 | FC Obstacle Data Set already provided. The source for Obstacle Data Set for Area 1 is Integrated AIM DB (AIXM 5.1). | 2019/Q1 | AIXM 5.1 | Area 2:FC (EVRA, EVLA, EVGA, EVVA) Area 3:FC (EVRA, EVLA) Area 4:FC (EVRA) Obstacle Data Set source for Areas 2, 3 and 4 is Integrated AIM DB (AIXM 5.1). | 2024/Q4 | Instrument Flight Procedure Data Sets will be prepared using AIXM 5.2 when the appropriate EUROCONTROL Specification will be ready and national data base upgraded to AIXM 5.2. | TBD | AMXM 2.0 | PANS-AIM specifies 5.3.3.3 Aerodrome mapping data sets. AMDB implementation for AD EVRA in progress. | 2019/Q1 | GeoTIFF | FC | 2019/Q1 | GeoTIFF | Area 2:FC (EVRA, EVLA, EVGA, EVVA) Area 3:FC (EVRA, EVLA) Area 4:FC (EVRA) | Yes | ENR 5.4. and AD 2.10. already removed Lateral limits of airspaces already removed from AIP by initial publication of AIP Data Set 2022/Q1, but based on user requirements will be temporarily provided also in the standardized presentation in the form of AIP SUP till 2023/Q1. All other tables ( GEN 2.5, ENR 2.1, ENR 3.3, ENR 3.6, ENR 4.1, ENR 4.4, ENR 5.1, ENR 5.2, EN 5.5, AD 2.17, AD 2.19, AD 3.16) are planned to be removed from AIP 2023/Q4. | 2023-02-23
Lithuania | 2023/Q2 | AIXM 5.1 | AIP Data Set will be provided as a new aeronautical information product as specified in latest ICAO provisions, when the AIM system be implemented. | Availabe | AIXM 4.5 | Obstacle Data Set (Area 1) is provided as aeronautical information product. | Available | AIXM 5.1 | Obstacle Data Set for EYVI, EYKA, EYPA, EYSA Airports (Area 2, 3 and 4) are provided as aeronautical information product. | 2023/Q2 | AIXM 5.1 | 2023/Q2 | TBD |  | Available | GeoTIFF | FC | Available | GeoTIFF | 2a: FC / 3: no info / 4: FC (EYVI) | Yes | AIP tables related to Aerodromes obstacle data are already removed. | 2022-02-01
Luxembourg | 2026/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | Luxembourg is focussing on the upstream data chain and the national data processes. Data sets will only be generated and provided after the required infrastructure is in place. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | NC Current TOD implementation approach under review. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) or 5.2 if required | 2a: NC / 3: no info / 4: NC Current TOD implementation approach under review. | 2026/Q4 | Will be considered based on user requirements. | TBD | TBD | At present no user requirement for AMDB Sets | 2024/Q4 | TBD | NC | 2024/Q4 | TBD | 2a: NC / 3: no info / 4: NC will depend on the State's policy | Yes | Depending on user requirments the AIP tables provided as data sets may be removed from the AIP. All other tables will remain in the AIP | 2023-02-23
Malta | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info |  | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
Montenegro | N/A | N/A | NI No implementation plans for the timebeing. | No info | No info | NC | No info | No info | 2a: NC 2b, 2c, 2d and 3: NI 4: N/A | N/A | NI No implementation plans for the timebeing. | N/A | N/A | NI AMDB is not considered, as there are no user requirements. | 2012 | No info | FC Terrain data for area 1 is provided by Property Administration, ref. AIP Serbia/Montenegro GEN 3.1. | TBD | TBD | 2a: NC 2b, 2c, 2d and 3: NI 4: N/A | No | After data set implementation, removal of AIP tables provided as data sets will be considered depending on user requirments. All other tables will remain in the AIP. | 2023-01-01
Morocco | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Netherlands | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info |  | No info | No info |  | No info | No info | NC | No info | No info | 2a: no info / 3: no info / 4: NC | No info | No info
North Macedonia | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2022/Q1 | AIXM 5.1.1 (Eurocontrol Spec) | NC | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2022/Q3 |  | 2023/Q1 | TBD |  | 2022/Q1 | TBD |  | 2022/Q3 | TBD |  | Yes | TBD
Norway | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC | 2019/Q1 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: FC / 3: no info / 4: FC | TBD |  | TBD | AMXM |  | 2019/Q1 | GeoTIFF; USGS DEM | FC | 2019/Q1 | GeoTIFF; USGS DEM | 2a: FC / 3: no info / 4: FC | Yes | ENR 5.4-2019/Q3 AD 2.10-2019/Q3
Poland | 2022/Q1 | AIXM 5.1 | FC | 2022/Q1 | AIXM 5.1; CSV | FC | 2022/Q1 | AIXM 5.1; CSV | 2a: NC / 3: no info / 4: NC Area 2 obstacle data set containing only data on obstacles penetrating Obstacle Limitation Surfaces (OLS) at the first stage. | 2024/Q4 | After Eurocontrol Specification Delivery | 2025/Q4 | AIXM 5.1 + extension |  | Not planned | Not planned | Digital Elevation Model (DEM) and Digital Sufrace Model (DSM) are made available by the the Main Office of Geodesy and Cartography on: https:// www.geoportal.gov.pl/dane/numeryczny-model-terenu or https://www.geoportal.gov.pl/dane/numeryczny-model-pokrycia-terenu | 2025/Q4 | TBD | 2a: no info / 3: no info / 4: TBD | TBD | Depending on user requirments. Decision will be taken after public consultations. | 2023-03-01
Portugal | 2024/Q2 | AIXM 5.1.1 (Eurocontrol Spec) | Depends on the deployment of a new AIXM 5.1-based system (expected to enter in operation in 2022/Q2) and development of eEAD | No info | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | PC Depends on the deployment of a new eTOD database and on originators capability in providing data. Awaiting State eTOD policy | 2024/Q3 | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | eTOD area 2 & 4 will be available on 2024 Q3 | TBD | On planning stage | No info | No info | The provision of the Airport Mapping Data Sets depends on the provision of the data from the relevant airports | TBD | TBD | FC Only available via the National Geodetic Institute | 2024/Q3 | TBD | Area 2 and 4 terrain data will be available on 2024 Q3 | TBD | No decision has been made yet | 2023-02-01
Republic of Moldova | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2017/Q1 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 5.1 | FC | 2017/Q1 | AIXM 5.1.1 (Eurocontrol Spec); AIXM 5.1 | 2a: FC / 3: no info / 4: FC | 2024/Q4 |  | 2024/Q4 | ESRI shape file format |  | 2012/ Q1 | ESRI Grid; GeoTIFF | FC | 2017/Q1 | ESRI Grid; GeoTIFF | 2a: FC / 3: no info / 4: FC | No | No | 2023-02-23
Romania | 2023 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023), which will enable provision and exchange of AIP data set as a service. | 2023 | AIXM 5.1.1 (Eurocontrol Spec), CSV, ESRI Shape | NC Obstacle Data Set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023) and on originators capability in providing data. No State eTOD policy for Area 1. | 2023 | AIXM 5.1.1 (Eurocontrol Spec), CSV, ESRI Shape | 2a: NC / 3: no info / 4: NC Obstacle Data Set provision depends on the deployment the new AIXM 5.1-based AIM System (expected in operation 2023) and on originators capability in providing data. | TBD | After Eurocontrol Specification Delivery | No info | No info | The provision of the Airport Mapping Data Sets depends on the provision of the data from the data originators (airports). | Available | GeoTIFF; USGS DEM | FC | 2023 | GeoTIFF; USGS DEM | 2a: NC / 3: no info / 4: NC | TBD | No decision has been made yet. | 2023-02-01
Russian Federation | 2023 | AIXM 5.1 | Implementation planned after approval AIXM 5.1 national standards | 2023/Q4 | AIXM 5.1 | PC | 2023/Q4 | AIXM 5.1 | 2: PC / 3: PC / 4: PC (area 2 is not divided into zones) | 2023/Q4 | AIXM 5.1 | TBD | TBD | N/A | 2023/Q4 | GeoTIFF | PC | 2023/Q4 | GeoTIFF | 2: PC / 3: PC / 4: PC (area 2 is not divided into zones) | TBD | TBD | 2022-03-01
Serbia | N/A | N/A | NI | No info | No info | NC | No info | No info | 2a: NC / 3: no info / 4: NC | N/A | NI | N/A | N/A | NI | 2013 | ASCII xyz; shapefile | FC; Area 1 terrain dataset is provided by Republic Geodetic Authority | TBD | TBD | 2a: NC / 3: NC / 4: NC | No | Removal of AIP tables shall be based on user requirments once digital data sets are implemented. | 2023-01-23
Slovakia | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Depends on the deployment of an AIXM 5.1-based AIS production system, which depends on migration to AIXM 5.1 EAD SDD (expected Q2 2024). | 2019/Q1 | AIXM 4.5. Implemetation of AIXM 5.1 together with update of the SW is planned. (expected Q2 2024). | FC | TBD | AIXM 4.5 or AIXM 5.1 according the date of implementation (see AIP DS remark) | Area 2 - NC (no data) Area 3 - NC (no data) Area 4 - PC (LZIB, LZKZ) Depends on data originators. | TBD | Data originator denies PT coding of conventional procedures. Waiting for Appropriate Eurocontrol Specification Delivery. Instrument Flight Procedure Data Sets will be prepared using AIXM 5.1 after transition process to AIXM 5.1 in EAD 2024/Q2 | TBD | TBD | No such data available | 2019/Q1 | ESRI Grid; Other | FC | Area 2 AD by AD from 2022/Q2 to 2023/Q2. Area 3 TBD Area 4 FC from 2019/Q1 | ESRI Grid; Other | Area 2 from ICAO perspectivie - FC. Area2 from EU perspective LZIB, LZPP - FC. LZZI, LZTT, LZKZ - NC, follows LIDAR scanning of state teritory. Area 3 fully depends on AD operators Area 4: FC | No | - | 2022-10-01
Slovenia | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2019/Q1 | CSV, ESRI Shape | FC | 2019/Q1 | CSV, ESRI Shape | 2a: FC / 3: no info / 4: FC | TBD | Details will be provided as soon as a plan is available | TBD | TBD | Details will be provided as soon as a plan is available | 2019/Q1 | ASCII file format (*.XYZ) | FC | 2019/Q1 | ASCII file format (*.XYZ) | 2a: FC / 3: no info / 4: FC | No | AIP tables will remain in AIP, for use of the GAT | 2023-02-01
Spain | 2022/Q3 | AIXM 5.1.1 (Eurocontrol Spec) | PI. The AIP dataset is partially available with ussage limitations. | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV; GeoJSON | FC Digital obstacle data already available on the AIP. Current work is to fix existing AIXM5.1 format known errors and prepare the processes to claim Obstacle Datasets availability | 2020/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | 2a: FC / 3: no info / 4: PC Digital obstacle data already available on the AIP. Current work is to fix existing AIXM5.1 format known errors and prepare the processes to claim Obstacle Datasets availability | TBD | Waiting to have more information on the coding guidelines and what is expected to be in this datasets. No current plans to develop them as part of the official AIP but some flight procedure data will be made accessible as digital data on an alpha digital data service. | TBD | TBD | Waiting to have more information on the coding guidelines and what is expected to be in this datasets. No current plans to develop them as part of the official AIP but some flight procedure data will be made accessible as digital data on an alpha digital data service. | 2022/Q4 | WMS; GeoTIFF | FC | 2022/Q4 | WMS; GeoTIFF | 2a: NC / 3: no info / 4: PC Most of the terrain datasets are already available with some limitations. New data is being acquired to provide full quality compliant datasets. | No | No | 2023-02-23
Sweden | 2023/Q3 | AIXM 5.1.1 (Eurocontrol Spec) | AIP data set provision depends on the deployment of a new AIXM 5.1-based AIS production system (expected in- operation 2023), which will enable provision and exchange of AIP data set as a service. The AIP data set is the prime targeted dataset service. | 2023/Q4 | AIXM 5.1.1 (Eurocontrol Spec); Other | Partially implemented. Obstacle data set for area 1 is provided since a number of years in csv.format. Obstacle data set in AIXM 5 is planned based on implementation of updated AIS database, planned in operations Q4/2023. | 2023/Q4 | Other | 2a: PC / 3: no info / 4: PC The plan for providing airport obstacle data set in AIXM depends on the deployment of a new AIXM 5.1-based AIS database, planned in operation Q4/2023. | 2023/Q4 | In planning-stage. This data set product/service is depending on originators capability in providing data, and how LFV can support with relevant interface/tools. The service depends on the deployment of the implementation of AIXM 5.1-based AIS production system, planned in operation Q4/2022. | 2024/Q4 | AIXM; AMXM | In planning-stage. Airport Mapping Data Set provision is planned in conjunction with airports own production/services and LFV’s capability to produce/make data set available. To be continued. | Compliant | Other | Electronic terrain data meeting the ICAO Annex 15 for Area 1 requirementis maintained and stored by the Swedish National Land Survey, link made available i AIP GEN 3.1.6. | Partly compliant | Other | 2a: FC / 3: no info / 4: FC Electronic terrain data meeting the ICAO Annex 15 for Area 2 and 4 requirementis maintained and stored by the Swedish National Land Survey, link made available i AIP GEN 3.1.6. | Planned | LFV considers removal of AIP tables as a step towards an efficient AIS provision, once data sets are established by consumers and as a service. There is currently no timetable for removal of AIP tables. Removal of other tables will be planned in-line with the capability of providing AIP data set (AIXM 5.1), communication with users of AIS and will likely be a phased approach. The first AIP table to be removed is ENR 5.4 (En-route obstacles), currently published in parallel with the Obstacle data set available on LFV web. This is planned for Q4/2023. | 2023-01-01
Switzerland | 2019/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | NC The AIP Data Set is available from Skyguide upon customer request, however not intended for operational use as not yet formally approved by the national CAA (FOCA). | 2019/Q1 | Other | NC Currently provided by the Federal Office of Civil Aviation (REF AIP Switzerland GEN 3.1 § 6.2) Full Compliance is planned by end of 2023, provision of the Data Set by the AISP Skyguide. | 2020/Q1 | Other | 2a: NC / 3:NC/ 4: NC Currently only partially provided by the Federal Office of Civil Aviation (REF AIP Switzerland GEN 3.1 § 6.2) Full Compliance is planned by end of 2023, provision of the Data Set by the AISP Skyguide. | 2020/Q1 | NC Not yet planned, as some Eurocontrol specifications are not available (e.g. conventional navigation flight procedures). However, PBN PROC data sets are available on customer request from Skyguide, however not intended for operational use as not yet formally approved by the national CAA (FOCA). | No info | No info | NI Is not provided in Switzerland currently | 2019/Q1 | ESRI Grid, GeoTiff | PC Currently provided by the Federal Office of Topography swisstopo (https://shop.swisstopo.admin.ch/en/products/height_models/dhm25) REF AIP Switzerland GEN 3.1 § 6.1 | 2019/Q1 | ESRI Grid, GeoTiff | 2a: PC / 3: PC / 4: PC Currently provided by the Federal Office of Topography swisstopo (https://shop.swisstopo.admin.ch/en/products/height_models/alti3D) REF AIP Switzerland GEN 3.1 § 6.1 | Partly | The removal of tables other than for obstacles is not yet decided. Discussions with the national CAA (FOCA) are ongoing. | 2023-02-01
Tajikistan |  |  |  | 2023/Q3 | ESRI, GeoTiff, DEM | NC | 2023/Q3 | ESRI, GeoTiff, DEM | 2a: NC / 3: no info / 4: NC | 2023/Q3 |  |  |  |  | 2023/Q3 | ESRI, GeoTiff, DEM | NC | 2023/Q3 | ESRI, GeoTiff, DEM | 2a: NC / 3: no info / 4: NC |  |  | 2022-02-01
Tunisia | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NA
Turkey | 2025/Q4 | AIXM 5.1.1 (Eurocontrol Spec) |  | 2014/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | FC Digital obstacle data already available on the AIP as of 2014/Q4 | 2014/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: FC / 3: no info / 4: FC Digital obstacle data for some AD already available on the AIP as of 2014/Q4, Currently all AD obstacle data set available on the AIP. | 2025/Q4 |  | TBD | TBD |  | 2014/Q4 | DTED; GeoTIFF | FC | 2016/Q4 | DTED; GeoTIFF | 2a: FC / 3: no info / 4: FC | Yes | AIP tables related to obstacle data are already removed. ENR 5.4-2014/Q4 AD 2.10-2014/Q4
Turkmenistan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Ukraine | TBD | AIXM 5.1.1 (Eurocontrol Spec) |  | 2021/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | FC | TBD | AIXM 5.1.1 (Eurocontrol Spec) | 2a: PC / 3: no info / 4: PC (UKHH, UKBB, UKLL) | TBD |  | No info | No info |  | 2020/Q1 | ESRI Shape Files; GDB | FC | TBD | TBD | 2a: NC / 3: no info / 4: NC (UKHH, UKBB, UKLL) | No | No | 2023-02-01
United Kingdom | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec) | Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | PC Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM 5.1.1 (Eurocontrol Spec); CSV | 2a: PC / 3: no info / 4: PC Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | As Procedures are provided. Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan -Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2024/Q4 | AIXM | Deliverables will be AIXM files compliant with the relevant ICAO Annex 15 SARPs and PANS-AIM, created using ECTL specifications and made available securely online. Trial AIXM files will be provided as part of the implementation plan - Timescales for operational delivery are currently being discussed between UK CAA and UK AIS. | 2019/Q1 | GML; ESRI Shape Files; GeoPackage | PC UK Area 1 terrain dataset is widely available, more information to be provided in GEN 3.1.6. | 2022/Q1 | GeoTIFF; GML | 2a: PC / 3: no info / 4: PC Terrain datasets for Areas 2-4 provided directly by the aerodorme operators. More information to be provided in GEN 3.1.6.For Area 1: GML 3.2 and ASCII (DTM grid); GeoPackage, GML 3.2 and Esri shapefile (Contours). | Yes | UK CAA support the implementation of ICAO datasets, but also recognises the importance of keeping information in the AIP during a transition period, which will be as long as needed. No tables will be removed until there is a level of assurance that users are ready to use datasets instead of the AIP tables and no data will become unavailable to users. | 2023-02-01
Uzbekistan | [5 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC | [7 empty] | NC |  |  | 2a: NC / 3: no info / 4: NC
Note on F43: Galbavy Lukas: Doplniť možnosť publikovania v 5.1, termín