## Approved at EASPG7
DEF ID | DEF Priority | State | DEF Type | DEF Req - ICAO Doc | DEF Req - Detail | DEF Descr | Reported by | Date Reported | DEF Rmk | Cor Act Recom ICAO | CAP Submited | CAP Description | CAP Exec Body | CAP / Expected Target Date | Last review/progress | Date Removed
Remark: According to the Uniform Methodology, deficiencies are prioritized with regard to their implications on the safety or regularity and eficiency, as follows: U priority = Urgent requirements having a direct impact on safety and requiring immediate corrective actions. A priority = Top priority requirements necessary for air navigation safety. B priority = Intermediate requirements necessary for air navigation regularity and efficiency.
EUR-AIS-01-05 | A | Tajikistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 2004-01-12 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Tajikistan CAA | 2011-12-01
EUR-AIS-01-06 | A | Turkmenistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 2004-01-12 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Turkmenistan CAA | 2018-12-01
EUR-AIS-01-07 | A | Uzbekistan | WGS-84 | An 15 | Par. 1.2.1 | WGS-84 - Not implemented | COG/ AIM TF | 37998 | The difficulties which impede CIS States to speed up and complete the implementation of WGS-84 are systematic and have legal and financial aspects. | Implement WGS-84 | N |  | Uzbekistan CAA | 45261 | 23 October 2025: taking into consideration the information published in the AIP (GEN 2.1 on WGS-84 and Tables AD 2.2 on geoid undulation), the deficiency EUR-AIS-01-07 will be submitted for deletion to the EASPG/7 meeting;
EUR-AIS-02-08 | A | Tajikistan | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | COG/ AIM TF | 15/05/2008 |  | Implement QMS for AIS | N |  | Tajikistan CAA | 2018-12-01
EUR-AIS-02-09 | A | Turkmenistan | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | COG/ AIM TF | 15/05/2008 |  | Implement QMS for AIS | N |  | Turkmenistan CAA | 2018-12-01
EUR-AIS-02-11 | A | Bosnia and Herzegovina | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | Eurocontrol / COG | 20/10/2009 |  | Implement QMS for AIS | N |  | Bosnia and Herzegovina CAA | 2011-12-01
EUR-AIS-02-13 | A | Malta | QMS for AIS | An 15 | Par. 3.6 | QMS not implemented | Eurocontrol / COG | 20/10/2009 |  | Implement QMS for AIS | N |  | Malta CAA | 2011-12-01
EUR-AIS-04-05 | A | Kyrgyzstan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Kyrgyzstan CAA | 2025-12-01 | KGZ informed officialy on 3 Oct. 2022 that this should be resolved by 2025
EUR-AIS-04-08 | A | Tajikistan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Tajikistan CAA | 2011-12-01
EUR-AIS-04-09 | A | Turkmenistan | Aeronautical charts and flight instrument procedures | An 4/ Doc 8168 (PANS-OPS) | Par. 9.9.4.3, 10.9.4.3, 11.10.9/ Flight Instrument Procedures | Non- compiance with ICAO An. 4 & Doc 8168 (PANS-OPS) provisions | COG/ AIM TF | 2009-12-02 | Lack of mechanism to ensure compliance with ICAO An. 4 and Doc. 8168 (PANS-OPS) provisions. | Comply with ICAO SARPs | N |  | Turkmenistan CAA | 2011-12-01
EUR-AIS-05-02 | A | Bulgaria | Publication of air navigation obstacles in AIP | PANS AIM | Par. 4.1.1, Appendix 2 | Air navigation obstacles are not published in AIP | EANPG/56 | 2014-11-26 | Air navigation obstacles to be published in the National AIP section ENR 5.4 (EANPG Conclusion 54/8 refers) | Comply with ICAO SARPs | N
EUR-ATM-03-01 | A | Cyprus | ATS coordination procedures | An 11, EUR ANP | SARPs and reg. procedures related to coordination between ACCs | Safety deficiencies in the N part of Nikosia FIR |  |  | Long lasting issue. Any solution envisaged requires political agreement between the parties involved |  | Y |  | Cyprus |  | Official letter received from Cyprus on 31st March 2023. Action plan proposed. EASPG/7 agreed to remove this deficiency.
EUR-ATM-03-02*,** | A | Türkiye | ATS coordination procedures | An 11, EUR ANP | SARPs and reg. procedures related to coordination between ACCs | Safety deficiencies in the N part of Nikosia FIR |  |  | Long lasting issue. Any solution envisaged requires political agreement between the parties involved |  | N |  | Türkiye | 2011-12-01
EUR-ATM-04-11 | U | Morocco | Provision of air space safety monitoring data | An 11 | Par. 3.3.5.1 | The State authority concened does not report the required data to the RMA | EUR RMA | 15/11/2007 | THE EUR air space SAFETY MONITORING REPORTS- Reporting Status "N" | Required monitoring data to be sent to the RMA on a regular basis | N |  | Morocco CAA | 2011-12-01 | COG/66 EUR RMA TBC?
*Note: Turkiye expressed disagreement with deficiency (paragraph 6.12 of the EANPG/49 report refers). **Note: CAP under development. On-going negociations facilitated by EC, Eurocontrol and ICAO.
EUR-ATM-05-04 | A | Bulgaria | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-ATM-05-09 | A | Turkmenistan | Validation of RVSM approvals | An 6+11 | A6,PartI, Par.7.2+ A6, partII,Par.2.5.2 + A11, Par. 3.3.5.1 | No evidence of an effective, compliant system for the management of RVSM approvals | EANPG | 2014-11-26 | The State failed to provide evidence of compliance with State RVSM related requirements | Provide detailed and comprehensive replies to the the State Letters EUR/NAT 14-0229.TEC or EUR/NAT 14-0530.TEC | N
EUR-MET-01-07 | A | Monaco | METAR availability | EUR FASID | Table MET 1A | LNMC METAR not available internationally | DMG of METG | 2015-06-01 |  | Make LNMC METAR available internationally | N |  |  | 2017-12-01
EUR-MET-01-12 | A | Turkmenistan | WAFS forecasts | An 3 | Annex 3, 9.1.4, 9.3.1, 9.4.1 and Appendix 2, 2.1.1 and para 38 of EUR Basic ANP, Part VI - MET | WAFS forecasts needed for briefing and flight documentation | DMG of METG | 2013-09-01 |  | comply with SARPs | N |  |  | 2017-12-01
EUR-MET-01-13 | A | Turkmenistan | QMS | An 3 | Annex 3, 2.2.2 | establish and implement a properly organized quality system comprising procedures, processes and resources necessary to provide for the quality management of the meteorological information to be supplied to the users listed in 2.1.2 | WMO | 2017-09-19 |  | comply with SARPs | N |  |  | 2017-12-01 | COG/69
EUR-MET-01-15 | A | Algeria | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N | The Translation of OPMET messages from TAC to IWXXM 3.0 has been fully carried out by the ONM. The ONM is sully capable of translating OPMET messages from TAC to IWXXM 3.0, having already implemented its own AMHS system since 2016. Finalize the acquisition and implementation of the AMHS system by the National Air Navigation Establishment (ENNA) to enable ONM to carry out the necessary transmission tests. | National Meteorological Office (ONM) | 2025 | Official letter from ANAC Ref. 5261 dated 17 Oct. 2024
'EUR-MET-01-16 | A | Armenia | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-17 | A | Azerbaijan | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-18 | A | Belarus | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-19 | A | Hungary | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-20 | A | Ireland | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-21 | A | Kyrgyzstan | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-22 | A | Latvia | MET | An 3 | App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N | 1) Finding was raised by Latvian Civil Aviation Agency in December, 2023; 2) New SW purchasing/installation and deployment activities, incl. systems testing and personnel training. | Latvian Environment, Geology and Meteorology Centre (METSP) | 30/06/2025. | CAP provided by Latvia to the EUR/NAT office on 2025
'EUR-MET-01-23 | A | Lithuania | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-24 | A | Malta | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N |  |  |  | September 2025: Malta fully implemented IWXXM for OPMET Data Exchange-METG35, September 2025
'EUR-MET-01-25 | A | The Netherlands | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-26 | A | North Macedonia | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-27 | A | Tajikistan | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-28 | A | Tunisia | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-29 | A | Türkiye | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-30 | A | Turkmenistan | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-01-31 | A | Ukraine | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N | a) Establishing of National OPMET Centre b) Taking appropriate measures to connect to the AMHS net work in order to transmit OPMET data c) Obtaining equipment and implementation of software to convert information into the IWXXM format for forming and transmitting OPMET Data, including systems testing. | a) The State Emergency Service of Ukraine / Ukrainian State Air Traffic Services Enterprise b) The State Emergency Service of Ukraine / Ukrainian State Air Traffic Services Enterprise (optional) c) The State Emergency Service of Ukraine / Ukrainian State Air Traffic Services Enterprise | a) After the end of martial law + 1 year b) December 2025 c) After the end of martial law + 2 years | EASPG/7 November 2025
'EUR-MET-01-32 | A | Uzbekistan | MET | An 3 | App 3 2.1.3 App 5 1.1.2 App 6 1.1.6 App 6 2.1.6 | IWXXM not implemented for OPMET Data Exchange | METG/33 | 16/09/2023 | Currently relies on translation services by the appropriate regional OPMET Center. | To implement IWXXM for Opmet Data Exchange | N
'EUR-MET-02-01 | U | Russian Federation | AGA | Ann 3, 6, 8, 14, 15. Doc 4444, Doc 9981 Doc 10066 | *See Note | GRF not implemented | METG/33 | 16/09/2023 | Involves other domains such as AIS, ATS, MET | To implement GRF | N
'EUR-MET-02-02 | U | Tajikistan | AGA | Ann 3, 6, 8, 14, 15. Doc 4444, Doc 9981 Doc 10066 | *See Note | GRF not implemented | METG/33 | 16/09/2023 | Involves other domains such as AIS, ATS, MET | To implement GRF | N
'EUR-MET-02-03 | U | Tunisia | AGA | Ann 3, 6, 8, 14, 15. Doc 4444, Doc 9981 Doc 10066 | *See Note | GRF not implemented | METG/33 | 16/09/2023 | Involves other domains such as AIS, ATS, MET | To implement GRF | N
'EUR-MET-02-04 | U | Turkmenistan | AGA | Ann 3, 6, 8, 14, 15. Doc 4444, Doc 9981 Doc 10066 | *See Note | GRF not implemented | METG/33 | 16/09/2023 | Involves other domains such as AIS, ATS, MET | To implement GRF | N
EUR-AIS-06-02 | B | Algeria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for DAAG 23 and Terrain dataset area 4 for DAAG 23 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-03 | B | Austria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LOWG 35C, LOWK 28R, LOWL 26, LOWL 08, LOWS 15, LOWW 16 and LOWW 29 and Terrain dataset area 4 for LOWG 35C, LOWK 28R, LOWL 26, LOWL 08, LOWS 15, LOWW 16 and LOWW 29 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | Update Austria in March 2022: Obstacle Data Set for Area 1 already published. Still lack of Obstacle Data set for Area 4 and Terrain Data Set for Area 4
EUR-AIS-06-04 | B | Azerbaijan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UBBB 17 and UBBB 35 and Terrain dataset area 4 for UBBB 17 and UBBB 35 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-05 | B | Belarus | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 4 for UMMC 31 and Terrain dataset area 4 for UMMC 31 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-06 | B | Belgium | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EBBR 25L, EBBR 25R, EBCI 25, EBLG 05R, EBLG 23L, EBLG 23R, EBOS 08 and EBOS 26. and Terrain dataset area 4 for EBBR 25L, EBBR 25R, EBCI 25, EBLG 05R, EBLG 23L, EBLG 23R, EBOS 08 and EBOS 26. should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-07 | B | Bosnia and Herzegovina | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-08 | B | Bulgaria | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LBSF 27 and Terrain dataset area 4 for LBSF 27 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-09 | B | Croatia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LDZA 05 and Terrain dataset area 4 for LDZA 05 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-10 | B | Czechia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LKMT 22 and LKPR 24 and Terrain dataset area 4 for LKMT 22 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | EASPG/4
EUR-AIS-06-11 | B | Denmark | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for: EKAH 28L, EKBI 09, EKBI 27, EKCH 04L, EKCH 22L, EKEB 26, EKKA 27L and EKYT 26R. and Terrain dataset area 4 for: EKAH 28L, EKBI 09, EKBI 27, EKCH 04L, EKCH 22L, EKEB 26, EKKA 27L and EKYT 26R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-12 | B | Estonia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-13 | B | France | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LFBL 21, LFJL 22, LFOB 12, LFQQ 26, LFRB 25L and LFOK 10 and Terrain dataset area 4 for: LFBL 21, LFJL 22, LFOB 12, LFQQ 26, LFRB 25L and LFOK 10 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-15 | B | Germany | TOD | An 15 | Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EDDB 25, EDDB 07, EDDC 22, EDDE 28, EDDE 10, EDDF 07L, EDDF 07C, EDDF 07R, EDDF 25L, EDDF 25C, EDDF 25R, EDDG 25, EDDH 23, EDDK 32R, EDDK 14L, EDDL 05R, EDDL 23L, EDDL 23R, EDDM 08L, EDDM 08R, EDDM 26L, EDDM 26R, EDDN 28, EDDP 08L, EDDP 08R, EDDP 26L, EDDP 26R, EDDS 07, EDDS 25, EDDV 09L, EDDV 27R, EDDW 09, EDDW 27, EDFH 21, EDLV 27, EDLW 06, EDNY 24 and EDSB 21 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 | N |  |  |  | Email Exchange of 4 May 2022 with Germany refers.
EUR-AIS-06-16 | B | Greece | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LGAV 03L, LGAV 03R, LGAV 21L, LGAV 21R and LGTS 16 and Terrain dataset area 4 for LGAV 03L, LGAV 03R, LGAV 21L, LGAV 21R and LGTS 16.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-17 | B | Hungary | TOD | An 15 | Para 5.3.3.3 | Lack of Terrain dataset for TOD area 4 | AIM/SWIM Team | 2016-10-11 | Terrain dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for: LHBP 13L, LHBP 13R, LHBP 31L and LHBP 31R. | Provide the required terrain dataset(s) for TOD area 4. | N |  |  |  | Hungary informed on 12 Oct. 2022 all the necessary informations related to Terrain Dataset of TOD Area 4 are not available yet in AIP, ENR 3.1, section 6.1.2. - Work is in progress
EUR-AIS-06-18 | B | Iceland | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for BIKF 02, BIKF 11, BIKF 20 and BIKF 29 and Terrain dataset area 4 for BIKF 02, BIKF 11, BIKF 20 and BIKF 29.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-19 | B | Israel | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N | Obstacle dataset for TOD area 1 is already provided since 2018 within the AIP of Israel (chapter ENR-5.4). However, the dataset does not meet the quality and completeness requirements in the ICAO Annex 15. An updated survey of TOD obstacles in area 1 is planned to be completed by 2027, and is already included in the CAA budget plan. This survey will be performed according to Annex 15 requirements. | CAA of Israel | 2027-12-01 | CAP confirmed by Israel on 11 March 2025
EUR-AIS-06-20 | B | Italy | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LIMC 35R, LIMC 35L, LIME 28, LIMF 36, LIML 36, LIMP 20, LIPE 12, LIPH 07, LIPO 32, LIPQ 09, LIPX 04, LIPZ 04R, LIRF 16L, LIRF 16R and LIRF 34R and Terrain dataset area 4 for LIMC 35R, LIMC 35L, LIME 28, LIMF 36, LIML 36, LIMP 20, LIPE 12, LIPH 07, LIPO 32, LIPQ 09, LIPX 04, LIPZ 04R, LIRF 16L, LIRF 16R and LIRF 34R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-21 | B | Kyrgyzstan | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | COG/AIM TF | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | N |  |  |  | KGZ informed with official letter on 3rd Oct. 2022 that an action plan will be developped.
EUR-AIS-06-22 | B | Luxembourg | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for ELLX 24 and Terrain dataset area 4 for ELLX 24 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-23 | B | Malta | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LMML 32 and Terrain dataset area 4 for LMML 32 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-24 | B | Montenegro | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-25 | B | Morocco | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for GMMN 35L, GMMN 35R and Terrain dataset area 4 for GMMN 35L, GMMN 35R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-26 | B | Netherlands | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for EHAM 06, EHAM 18C, EHAM 18R, EHAM 27, EHAM 36C, EHAM 36R and EHBK 21 and Terrain dataset area 4 for EHAM 06, EHAM 18C, EHAM 18R, EHAM 27, EHAM 36C, EHAM 36R and EHBK 21 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | NLD informed on 9 March 2022 that the obstacles datasets are being worked on, but cannot be published until the international coding standards are established. Publication TBD.
EUR-AIS-06-27 | B | Poland | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EPGD 29, EPKT 27, EPMO 08, EPKK 25, EPWA 11 and EPWA 33 and Terrain dataset area 4 for EPGD 29, EPKT 27, EPMO 08, EPKK 25, EPWA 11 and EPWA 33 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-28 | B | Portugal | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for LPFR 28, LPPR 17 and LPPT 21 and Terrain dataset area 4 for LPFR 28, LPPR 17 and LPPT 21.should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-29 | B | Romania | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LRAR 27, LRBS 07, LRCL 25, LRIA 14, LROP 08L, LROP 08R, LRTM 07, LRTR 11 and LRTR 29 and Terrain dataset area 4 for LRAR 27, LRBS 07, LRCL 25, LRIA 14, LROP 08L, LROP 08R, LRTM 07, LRTR 11 and LRTR 29 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-30 | B | Russian Federation | TOD | An 15 | Para 5.3.3.3 | Lack of Terrain dataset for TOD area 4 | COG/AIM TF | 2016-10-11 | Terrain dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for UHPP 34L, URWW 06, UWKD 11, UWUU 14R, UEEE 23L, ULLI 10R, 10L, 28R, UNKL 11, 29, UNNT 16, URMM 12, URRR 04, UUWW 19, 06, 24, UUDD 32R, 14R, UUEE 24L, 24R, 06R, UHWW 25L, UHHH 23L | Provide the required terrain dataset(s) for TOD area 4. | N |  |  | 2020-12-01 | COG75/RCOG12
EUR-AIS-06-31 | B | Serbia | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for LYBE 12L, LYBE 12R and Terrain dataset area 4 for LYBE 12L, LYBE 12R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | EASPG/6
EUR-AIS-06-33 | B | Sweden | TOD | An 15 | Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for ESGG 03, ESGG 21, ESMS 17, ESSA 19L, ESSA 01L and ESSA 01R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 | N | Update information since last reporting: Ref. 5.3.3.4 Obstacle dataset for area 4 for required aerodromes not yet provided but under development. This provision will be fulfilled during 2023/2024 by the deployment of a national AIS-system supporting the required dataset provision. |  | 2024-12-24 | 02/2023. Update provided by Sweden on 24 February 2023 through official state letter
EUR-AIS-06-34 | B | Switzerland | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 4 should be developed (COG Conclusion 65/14 refers) for: LSGG 22, LSZH 16 and LSZH 14. | Provide the required obstacle dataset(s) for TOD area 4. | Y | Obstacle management is under the responsibility of the Data Collection Services provider (ITV) and the obstacle publication process will be fully managed by Skyguide latest by end of 2023. Implementation of the provision of obstacle data sets for Area 4 for LSGG 22, LSZH 16 and LSZH 14 is planned until end of 2024. | 'Skyguide/D. Guler, Head of Data Management | 2024-12-24 | EASPG/4
EUR-AIS-06-35 | B | Tajikistan | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | COG/AIM TF | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | N |  |  |  | COG75/RCOG12
EUR-AIS-06-36 | B | North Macedonia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers). | Provide the obstacle dataset(s) for TOD area 1 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-37 | B | Tunisia | TOD | An 15 | Para. 5.3.3.4 | Lack of Obstacle dataset for TOD area 1 | ICAO EUR/NAT | 2016-10-11 | Obstacle dataset for TOD area 1 should be developed (COG Conclusion 65/14 refers) | Provide the required obstacle dataset(s) for TOD area 1. | Y | - Implementation of the National TOD policy - launch of an international call for tenders for the collection of obstacle and field data for 5 Tunisian INTL airports. (The obstacle collection surfaces take into consideration: 1. Areas 2a, 2b and 2d of Annex 15. 2. the surfaces of the final approach segments (LNAV & VNAV) of the PANS-OPS. 3. OLS of Annex 14. 4. the take-off surface The terrain data will comply with the requirements of Area 2 of Annex 15) - Collection of obstacle data of the Area 1 - launch of an international call for tenders for the collection of obstacle and field data for 04 Tunisian international airports. | OACA/CEO | 2023(Q1-Q2) | EASPG/3
EUR-AIS-06-38 | B | Turkmenistan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UTAA 12R, UTAA 30L, UTAA 12L, UTAA 30R and Terrain dataset area 4 for UTAA 12R, UTAA 30L, UTAA 12L, UTAA 30R should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | COG75/RCOG12
EUR-AIS-06-40 | B | United Kingdom | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 4 - Terrain dataset for area 4 | AIM/SWIM Team | 2016-10-11 | Obstacle dataset area 4 for EGAA 17, EGAA 25, EGBB 15, EGBB 33, EGHH 26, EGGD 27, EGCN 20, EGNX 09, EGNX 27, EGPH 06, EGPH 24, EGPF 05, EGPF 23, EGNS 08, EGNS 26, EGNM 32, EGGP 27, EGKK 08R, EGKK 26L, EGLL 09L, EGLL 09R, EGLL 27L, EGLL 27R, EGGW 08, EGGW 26, EGSS 04, EGSS 22, EGCC 05L, EGCC 23R, EGNT 07, EGNT 25 and EGHQ 30 and Terrain dataset area 4 for EGAA 17, EGAA 25, EGBB 15, EGBB 33, EGHH 26, EGGD 27, EGCN 20, EGNX 09, EGNX 27, EGPH 06, EGPH 24, EGPF 05, EGPF 23, EGNS 08, EGNS 26, EGNM 32, EGGP 27, EGKK 08R, EGKK 26L, EGLL 09L, EGLL 09R, EGLL 27L, EGLL 27R, EGGW 08, EGGW 26, EGSS 04, EGSS 22, EGCC 05L, EGCC 23R, EGNT 07, EGNT 25 and EGHQ 30 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 4 and terrain dataset area 4 | N | Oct 2025: Obstacle datasets in AIXM and CSV formats for areas 2/3/4 to be made available as of AIRAC 03/26: to be released on a staggered basis as each aerodrome submits an update to its survey data. Terrain datasets still in development/discussion. |  |  | COG75/RCOG12
EUR-AIS-06-41 | B | Uzbekistan | TOD | An 15 | Para 5.3.3.3 Para. 5.3.3.4 | Lack of: - Obstacle dataset for area 1 - Obstacle dataset for area 4 - Terrain dataset for area 4 | COG/AIM TF | 2016-10-11 | Obstacle dataset area 1, Obstacle dataset area 4 for UTTT 08L, UTSA 07, UTSA 25 and Terrain dataset area 4 for UTTT 08L, UTSA 07, UTSA 25 should be developed (COG Conclusion 65/14 refers). | Provide the required obstacle dataset area 1, obstacle dataset area 4 and terrain dataset area 4 | N |  |  |  | State Lettter from UZB Ref. 01-39/12-4583 dated 21 Oct 2025: Uzbekistan published obstacles in tabular format and in the precision approach terrain charts. However, in accordance with the below Annex 15 provision, datasets shall be provided using aeronautical information exchange models. Therefore, the deficiency cannot be proposed for elimination at this stage.
EUR-AIS-07-01 | U | Russian Federation | Aeronautical information publication | An 11 An 15 | Par. 2.1.2, 2.1.3 Par 2.1.2 | Publication of the aeronautical information not in compliance with ICAO provisions | Ukraine | 16/10/2016 | Publication by the Russian Federation of several aeronautical information related documents, such as NOTAMs, AICs, Amendments, and Supplements to the AIP of the Russian Federation, concerning the Simferopol FIR | To remove the incompliant AIS publication | N |  |  |  | EASPG/6 |  | “Progress reports of the PT work were presented to COG 72/RCOG 09 and COG 74/RCOG 11. Further progress of the PT work is contingent on the concurrent work in ICAO Headquarters concerning the revision of the main body of the Uniform Methodology

## Note GRF Def
SARPS related to GRF
Annex 3 - 5.5
Annex 3 - App 3 4.8.1.5-6
Annex 6 - Part I 4.4.2.1
Annex 6 - Part I 4.4.11
Annex 6 - Part I 5.2.6
Annex 6 - Part I 5.2.11
Annex 6 - Part II 2.2.4.2
Annex 6 - Part II 2.2.4.4
Annex 6 - Part II 3.4.4.5
Annex 6 - Part II 3.5.2.5
Annex 6 - Part II 3.5.2.7
Annex 6 - Part II 3.5.2.9
Annex 8 - 2.2.1-3
Annex 8 - 2.2.4.1-2
Annex 8 - 2.2.5 c)
Annex 8 - 2.2.7
Annex 8 - 2.2.7.2-3
Annex 14 - 2.9.2 c)
Annex 14 - 2.9.3-10
Annex 14 - 10.2.2-8
Annex 14 - 10.3.1
Annex 14 - 10.3.4-6
Annex 14 - 6.1-2
Annex 14 - 7.1-2
Annex 15 - 1.1
Doc 4444 - 4.12
Doc 4444 - 4.12.3 i)
Doc 4444 - 4.12.7
Doc 4444 - 7.5.2 c) - d)
Doc 4444 - 11.4.3.4.2-3
Doc 4444 - 12.3.1.11
Doc 4444 - App 1
Doc 9981 - 2.1.1.1-2
Doc 9981 - Att
Doc 10066 - Chap 1
Doc 10066 - 5.2.2.2 a)
Doc 10066 - 5.2.5.1.4
Doc 10066 - App 4