## ProjectSchedule Phase 1
SMS Implementation Plan - Phase 1 Planning SMS implementation
[Company Name] |  | Project Start: | 2021-04-01
[Project Lead] |  | Today: | 2021-04-09
|  | Display Week: | 1 |  |  | 2021-03-29 | [6 empty] | 2021-04-05 | [6 empty] | 2021-04-12 | [6 empty] | 2021-04-19 | [6 empty] | 2021-04-26 | [6 empty] | 2021-05-03 | [6 empty] | 2021-05-10 | [6 empty] | 2021-05-17 | [6 empty] | 2021-05-24 | [6 empty] | 2021-05-31 | [6 empty] | 2021-06-07 | [6 empty] | 2021-06-14 | [6 empty] | 2021-06-21 | [6 empty] | 2021-06-28 | [6 empty] | 2021-07-05 | [6 empty] | 2021-07-12 | [6 empty] | 2021-07-19 | [6 empty] | 2021-07-26 | [6 empty] | 2021-08-02 | [6 empty] | 2021-08-09 | [6 empty] | 2021-08-16 | [6 empty] | 2021-08-23 | [6 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18 | [6 empty] | 2021-10-25 | [6 empty] | 2021-11-01 | [6 empty] | 2021-11-08 | [6 empty] | 2021-11-15 | [6 empty] | 2021-11-22 | [6 empty] | 2021-11-29 | [6 empty] | 2021-12-06 | [6 empty] | 2021-12-13 | [6 empty] | 2021-12-20 | [6 empty] | 2021-12-27 | [6 empty] | 2022-01-03 | [6 empty] | 2022-01-10 | [6 empty] | 2022-01-17 | [6 empty] | 2022-01-24 | [6 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28
 | time axis 2021-03-29 to 2022-04-03
TASK Name | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2021-03-29 to 2022-04-03
Phase 1 - Planning SMS implementation |  | 0% | 2021-04-04 | 2022-02-26 | 328
Management commitment |  |  | 2021-04-04 | 2021-07-21 | 99
Accountable Excecutive and SMS Planning group |  |  | 2021-04-04 | 2021-04-11 | 7
identify the Accountable Executive |  | 100% | 2021-04-04 | 2021-04-05 | 1
select person/planning group for SMS implementation plan |  | 60% | 2021-04-06 | 2021-04-11 | 5
System Description and Gap Analysis |  |  | 2021-04-12 | 2021-05-18 | 36
perform system description |  | 50% | 2021-04-12 | 2021-04-27 | 15
perform gap analysis |  | 10% | 2021-04-28 | 2021-05-18 | 20
Safety Policy and Objectives |  |  | 2021-05-19 | 2021-06-09 | 21
develop safety policy |  |  | 2021-05-19 | 2021-05-24 | 5
safety policy signed by accountable executive |  |  | 2021-05-25 | 2021-05-25 | 0
develop safety objectives for the SMS |  |  | 2021-05-26 | 2021-05-31 | 5
safety objectives for the SMS established |  |  | 2021-06-01 | 2021-06-03 | 2
establish SMS requirements for sub-contractors |  |  | 2021-06-04 | 2021-06-09 | 5
Safety accountabilities and appointment of key safety personnel |  |  | 2021-06-10 | 2021-07-21 | 41
develop SMS organizational structure |  |  | 2021-06-10 | 2021-06-20 | 10
establish the Safety Service Office |  |  | 2021-06-21 | 2021-06-24 | 3
select the Safety Manager |  |  | 2021-06-25 | 2021-07-05 | 10
establish Safety Review Board |  |  | 2021-07-06 | 2021-07-09 | 3
establish Safety Action Group(s) |  |  | 2021-07-10 | 2021-07-17 | 7
lines of safety accountability established |  |  | 2021-07-18 | 2021-07-20 | 2
SMS organizational structure in place |  |  | 2021-07-21 | 2021-07-21 | 0
Coordination of the emergency responese planning (ERP) |  |  | 2021-07-22 | 2022-01-01 | 46
Internal coordination |  |  | 2021-07-22 | 2021-08-12 | 20
review ERP delegation of authority and emergency resposibilities |  | 10% | 2021-07-22 | 2021-07-27 | 5
develop coordination procedures for key personnel |  |  | 2021-07-28 | 2021-08-12 | 15
External coordination |  |  | 2021-08-13 | 2022-01-01 | 26
identify external entities with interaction during emergencies |  | 30% | 2021-08-13 | 2021-08-18 | 5
access and assessment of their ERP |  |  | 2021-08-19 | 2021-09-08 | 20
establish coodination between different ERPs |  |  | 2021-09-09 | 2021-09-10 | 1
SMS Documentation |  |  | 2021-09-11 | 2022-01-01 | 105
SMS implementation plan |  |  | 2021-09-11 | 2021-11-20 | 65
develop an SMS implementation plan draft proposal |  |  | 2021-09-11 | 2021-10-21 | 40
identify potential challenges in the SMS implementation plan |  |  | 2021-10-22 | 2021-10-29 | 7
develop provisions to address identified challenges |  |  | 2021-10-30 | 2021-11-07 | 8
draft budget for SMS impplementation approved |  |  | 2021-11-08 | 2021-11-13 | 5
initial draft budget for SMS implementation approved |  |  | 2021-11-14 | 2021-11-19 | 5
SMS implementation plan approved |  |  | 2021-11-20 | 2021-11-20 | 0
Safety Management Systems Manual |  |  | 2021-11-21 | 2022-01-01 | 40
develop draft manual |  |  | 2021-11-21 | 2021-12-31 | 40
initial draft of Safety Management Systems Manual published |  |  | 2022-01-01 | 2022-01-01 | 0
Safety Training |  |  | 2022-01-02 | 2022-03-29 | 78
Training requirements |  |  | 2022-01-02 | 2022-01-23 | 19
develop a documented process to identify training requirement |  |  | 2022-01-02 | 2022-01-09 | 7
develop a validation process to measure effectiveness of training |  |  | 2022-01-10 | 2022-01-17 | 7
indentify costs associated for training |  |  | 2022-01-18 | 2022-01-23 | 5
Training programme |  |  | 2022-01-24 | 2022-03-29 | 59
develop initial (general safety) job-specific |  |  | 2022-01-24 | 2022-02-03 | 10
indoctrination/initial on SMS, human factors and organizational safety objectives |  |  | 2022-02-04 | 2022-02-24 | 20
develop recurrent training syllabus |  |  | 2022-02-25 | 2022-03-04 | 7
schedule initial (general safety) training job-wise for all staff |  |  | 2022-03-05 | 2022-03-07 | 2
deliver intial (general safety) training |  |  | 2022-03-08 | 2022-03-28 | 20
training on SMS planning phase delivered |  |  | 2022-03-29 | 2022-03-29 | 0
Safety Promotion - Communication |  |  | 2022-03-30 | 2022-04-19 | 17
Safety policy communicated with visible endorsement to all staff |  |  | 2022-03-30 | 2022-03-30 | 0
identify and develop means to convey safety related issues |  |  | 2022-03-31 | 2022-04-15 | 15
convey to all staff information related to SMS organizational structure |  |  | 2022-04-16 | 2022-04-18 | 2
means to communicate safety issues established |  |  | 2022-04-19 | 2022-04-19 | 0
Insert new rows ABOVE this one
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.