## Slide 1
Workshop on the Implementation of the New SADIS API Data Sets
(Dakar, Senegal, 19 – 21 May 2025)

## Slide 2: Proposed Steps for Implementing the SADIS API
Goama Ilboudo
Regional Officier, MET, ICAO WACAF Office

## Slide 3: Overview
01
03
02
04
05
06
Awareness and Planning Phase
Technical Preparation Phase
Capacity Building and Training
System Integration and Testing
Operationalization Phase
Sustainability and Continuous Improvement

## Slide 4: Awareness and Planning Phase 1/3
Identify national stakeholders (Civil Aviation Authorities, ANSPs, MET service providers, IT departments).
Convene an awareness meeting/workshop to introduce the SADIS API, its benefits, and transition deadlines (APIRG/26 Conclusion 26/14 and APIRG/27 Conclusion 27/09).
Stakeholder Engagement

## Slide 5: Awareness and Planning Phase 2/3
Assess current national regulatory frameworks.
Update national policies to reflect ICAO Annex 3 and regional requirements /guidance on WAFS/OPMET data access through SADIS Systems.
Policy and Regulatory Review

## Slide 6: Awareness and Planning Phase 3/3
Assess current capabilities (infrastructure, systems, and staff competencies).
Compare current data access mechanisms with SADIS API requirements.
Initial Gap Analysis

## Slide 7: Technical Preparation Phase 1/2
Review existing internet connectivity, firewall settings, and server infrastructure.
Plan for secure and reliable internet access to support API communications.
Infrastructure Assessment

## Slide 8: Technical Preparation Phase 2/2
Apply for SADIS API access credentials via the UK Met Office SADIS Gateway.
Assign a SADIS API focal point for managing access and credentials.
Access Credential Request

## Slide 9: Capacity Building and Training 1/2
Conduct training workshops/webinars for:
  Aeronautical Meteorological Staff (Forecasters, Observers) (on data usage and interpretation).
  Maintenance Technicians and IT staff (on API integration and cybersecurity).
Training

## Slide 10: Capacity Building and Training 2/2
Develop and disseminate national guidance on using the SADIS API.
Include tools and troubleshooting tips.
Development of Local Guidance

## Slide 11: System Integration and Testing 1/2
Simulate operational scenarios to validate data access, response times, and failover behavior.
Ensure backup mechanisms are in place (e.g., redundant connections, data caching).
End-to-End Testing

## Slide 12: System Integration and Testing 2/2
Involve operational meteorologists and aviation stakeholders in validation.
Gather feedback for improvements before full deployment.
Validation with End Users

## Slide 13: Operationalization Phase 1/3
Plan a phased transition from legacy access methods (FTP/SADIS FTP) to the API.
Coordinate with ICAO Regional Offices and SADIS provider as well as States/Organization having operationalized SADIS API.
Go-Live Transition

## Slide 14: Operationalization Phase 2/3
Set up monitoring tools for API uptime, latency, and usage.
Create a helpdesk or focal point for technical support and troubleshooting.
Monitoring and Support

## Slide 15: Operationalization Phase 3/3
Maintain records of implementation steps, configurations, and lessons learned.
Report progress to regional ICAO offices and WAFS user forums.
Documentation and Reporting

## Slide 16: Sustainability and Continuous Improvement 1/3
Establish channels for users to report issues and suggest improvements.
Participate in ICAO SADIS workshops and API user forums.
Feedback Mechanism

## Slide 17: Sustainability and Continuous Improvement 2/3
Track SADIS API updates and implement changes in local systems accordingly.
Review and update internal procedures regularly.
Regular Updates

## Slide 18: Sustainability and Continuous Improvement 3/3
Ensure the SADIS API implementation is embedded in the organization's quality management system for continuous improvements.
Integration with QMS