|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **MEETING REF. (APIRG/RA SG)** | **CONCLUSI**  **ON/ DECISION** | **REF N°** | **TITLE OF CONCLUSION/DECIS ION** | **TEXT OF CONCLUSION/DECISION** | **ACTIVITY** | **DELIVERABLE** | **STATUS** |
| IIM/SG7 | Decision | 7/01 | Establishment of the Flight and Flow – Information for Collaborative Environment (FF-ICE) Project | That; to ensure a harmonized and timely implementation of FF-ICE in the AFI region.  a) The proposed Termes of References of the FF-ICE Task force are approved for coordination with the AAO Subgroup.  b) The IIM/SG to coordinate with the AAO/SG for endorsement of the proposed ToR by 30 October 2024;  c)The FF-ICE Task force to develop the FF-ICE Project document and submit it to the Secretariat for APIRG consideration through the APCC by 30 October 2024.  d)The FF-ICE Task force to conduct the awareness workshop called for by the APIRG Decision 26/17 by 28 February 2025. | By whom:  a) IIM/SG  b) The Secretariat  c)FF-ICE Task force, Secretariat  d)FF-ICE Task force  By when:  b)30 October 2024  c)30 October 2024,  d)28 February 2025 | Project document submitted to APIRG  Workshop conducted | **Completed.**   * The FF-ICE project team was established. * Project document and ToRs endorsed by APIRG/27. * FP webinar conducted on 25 March 2025. |
| IIM/SG7 | Decision | 7/02 | Selection of Experts to the AIM 4 and AIM 5 projects teams | That; to set up the projects’ teams of AIM Project 4 and AIM Project 5,  a) The criteria for the selection of Experts provided in Appendix 8 are adopted,  b) States and Organizations to nominate Experts for both AIM 4 and AIM 5 Projects based on the agreed criteria by October 2024. | By whom:  Secretariat  By when:  30 October 2024 | Criteria circulated | **Completed**   * Selection criteria approved by APIRG/27. * SL referenced 2025-T17-6-11 C -0153 circulated to States for submission of candidates. * Project experts selected. * Launching meeting conducted |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **MEETING REF. (APIRG/RA SG)** | **CONCLUSI**  **ON/ DECISION** | **REF N°** | **TITLE OF CONCLUSION/DECIS ION** | **TEXT OF CONCLUSION/DECISION** | **ACTIVITY** | **DELIVERABLE** | **STATUS** |
| IIM/SG7 | Conclusion | 7/03 | Conduct of the third volcanic ash exercise in the AFI Region | That, to practice and develop inter-agency response to volcanic activity  a) The proposal of Kenya to lead the third volcanic ash exercise is endorsed  b) Kenya to direct and coordinate the third volcanic ash exercise in the AFI Region by 30 November 2025; and  c)ESAF and WACF Offices to facilitate the conduct of the volcanic ash exercise in the AFI Region by 30 November 2025. | By whom:  a) APIRG  b) Kenya  c)ESAF and WACAF Offices  By when:  b) and c): By 30 November 2025 | Approved volcanic ash exercise schedule  Final Report of the third volcanic ash exercise | **In progress**   * Kenya proposal to lead the 2025 volcanic ash exercise approved by APIRG/27. * The Fourth Meeting of the AFI Volcanic Ash Exercise Steering Group held in April 2025 approved the objectives of the 2025 Volcex. * Regional workshop on the provision of information on volcanic eruptions and ash clouds conducted from 16 to 20 June 2025. * Preparatory activities are ongoing. |
| IIMSG7 | Conclusion | 7/04 | New SADIS API and WIFS API services | That, to prepare for the upcoming SIGWX changes and ensure the use of the new IWXXM format SIGWX data sets  a) SADIS user States and Organizations to conduct awareness activities on the upcoming T+24 SIGWX changes effective on 26 November 2024 by sharing the SIGWX flyer or by directing them to https://www.metoffice.gov.uk/services/transport/aviation/regulated/wafs-2023 by end of December 2024; and  b) States and Organizations to develop plans to upgrade their systems to be able to visualize the higher resolution WAFS gridded data sets and new IWXXM SIGWX data sets and use the new SADIS API by November 2025. | By whom:  a) SADIS user States and Organizations  b)States and Organizations.  By when:  By end of December 2024 | Number of States with capability SADIS API capabilities  Conducted awareness activities | **In progress**   * Regional workshop on the implementation of SADIS API conducted from 19 to 21 May 2025. * States and Organizations provided with a roadmap to upgrade their existing SADIS System to the SADIS API. * States and Organizations started developing software for retrieving MET data in IWXXM format. |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **MEETING REF. (APIRG/RA SG)** | **CONCLUSI**  **ON/ DECISION** | **REF N°** | **TITLE OF CONCLUSION/DECIS ION** | **TEXT OF CONCLUSION/DECISION** | **ACTIVITY** | **DELIVERABLE** | **STATUS** |
| IIM/SG7 | Decision | 7/05 | Preparation of the Air Navigation Services Summit | That, to foster the preparation of the AFI Air Navigation Service Summit.  a) The AFI ANS Summit is postponed; and  b) The Secretariat to coordinate with key stakeholders the review of:  i). the ANS Summit related terms of references to ensure its alignment with the provisions of the APIRG Procedural Handbook; and  ii). required activities for the effective conduct of the AFI Air Navigation Services Summit. | By whom:  a)  APIRG  b)  Secretariat.  By when:  a) and b) by December 2025 | Established expert teams  Deliverables for the Summit | **In progress**   * Ongoing discussions for the preparation of the ANS Summit. * The roadmap for the preparation of the ANS Summit drafted for the IIM/SG8 review and guidance. |
| IIMSG7 | Decision | 7/06 | Scope of the minimum reporting framework | That, to ensure consistency of the minimum reporting areas,  The list of minimum reporting areas shall be revised as appropriate by 31 December 2024 | By whom:  APIRG  By when:  31 December 2024 | Updated list of minimum reporting areas | **Not completed** |

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| **MEETING REF. (APIRG/RA SG)** | **CONCLUSI**  **ON/ DECISION** | **REF N°** | **TITLE OF CONCLUSION/DECIS ION** | **TEXT OF CONCLUSION/DECISION** | **ACTIVITY** | **DELIVERABLE** | **STATUS** |
| IIM/SG7 | Conclusion | 7/07 | Revision of IIM Projects membership | That, to enhance the effectiveness of APIRG IIM Projects,  a) The Secretariat and the IIM Project Team Coordinators to consider qualified experts and revise project teams’ composition by 31 December 2024;  b) The Secretariat to notify States and Organizations the designation of their experts by 31 December 2024;  c) States and Organizations to ensure the effective participation of experts in projects’ activities and Subgroup meetings by 31 December 2024. | By whom:  a) Secretariat, IIM Project Team Coordinators  b) Secretariat  c)States, Organizations  By when:  a), b) and c): 31 December 2024 | Revised project team composition  Sensitization activities conducted | **In progress**   * Project team Coordinators briefed on the need to reframe project in line with the AASPG Procedural Handbook. * Project reframed to align with the results-based management approach. * a), b), d) ongoing |
| IIM/SG7 | Decision | 7/08 | Work Programme of APIRG IIM/SG for 2024/2025 | That to support the implementation of the Subgroup objectives, The Work Programme as provided in Appendix 16 is approved. | By whom:  APIRG/27 meeting  By when:  By November 2024 | Approved Work Programme | **Completed**   * Work programme approved by APIRG/27 and RASG-AFI/10 |