Space-Based VHF Correspondence Group

Works Plan

### Background:

At the World Radiocommunication Conference 2023, a new allocation to the aeronautical mobile-satellite (R) service (AMS(R)S, in the frequency band 117.975 - 137 MHz was approved. The RESOLUTION 406 (WRC-23) was also approved inviting the International Civil Aviation Organization (ICAO) to take into account this Resolution in the course of developing SARPs for the VHF AMS(R)S and planning the AM(R)S and AMS(R)S in the frequency band 117.975-137 MHz.

At FSMP-WG/17 the Space-Based VHF Correspondence Group (CG) was established, and this is the Works Plan for that group.

### Meeting Schedule:

The CG will meet virtually approximately every 4 weeks to progress the work. The CG will also meet 2 weeks before a FSMP-WG meeting to agree on what will be submitted into that meeting.

### Deliverables:

Assuming that the next panel meeting of the FSMP will occur in September 2025, after FSMP WG/21, this is the planned deliverables of the CG. This will allow time for review of the proposed changes to Annex 10 Volume 5, in context of the validation report and the proposed changes to Doc.9718.

.

FSMP WG/19 (July 2024)

- Work Plan

- Initial Draft:

  - Vol.5 PfA

  - Validation Report

  - Impact Assessment and Implementation Plan

- Draft Vol.3 PfA

FSMP WG/20 (Feb 2025)

- Work Plan Update

- Final Version

  - Doc.9718 Update (Vol 1)

- 2nd Draft:

  - Vol.5 PfA

  - Validation Report

  - Impact Assessment and Implementation Plan

- Initial Draft

  - Doc.9718 Update (Vol 2)

FSMP WG/21 (Sept 2025)

- Work Plan Update

- Final Version

  - Vol.5 PfA

  - Validation Report

  - Impact Assessment and Implementation Plan

- 2nd Draft

  - Doc.9718 Update (Vol 2)

- Vol.3 PfA (Recommended by DCIWG)

FSMP/4 (Sept 2025)

- FSMP-WG Endorsed:

  - Vol.5 PfA

  - Validation Report

  - Impact Assessment and Implementation Plan

FSMP WG/22 (Feb 2026)

- Final Draft:

  - Doc.9718 Update (Vol 2)