| REGIONAL PERFORMANCE OBJECTIVE: SAM SAR/01 COOPERATION AND COORDINATION OF SAR SERVICES AT REGIONAL LEVEL |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Benefits |  |  |  |  |  |
| Safety |  | - Favours the application of practical risk management principles |  |  |  |
| Environmental protection and development of air transport |  | - Ensure cooperation and coordination amongst the interested parties |  |  |  |
| Metrics |  |  |  |  |  |
| - Number of letters of agreement established for SAR - Number of SAR exercises conducted |  |  |  |  |  |
| 2012 - 2018 Strategy |  |  |  |  |  |
| ATM OC COMPONENTS | TASKS |  | PERIOD | RESPONSIBILITY | STATUS |
| N/A | - Assess SAR requirements at regional level |  | 2011 | ICAO-States | Valid |
|  | - Adopt SAR requirements at regional level |  | 2012 - 2014 | States | Valid |
|  | - Comply with risk and quality management practical principles |  | (*) - 2017 | States | Valid |
|  | - Develop, update, establish and ratify SAR agreements between States |  | (*) - 2017 | States | Valid |
|  | - Harmonise SAR training plans |  | (*) - 2013 | CATC | Valid |
|  | - Conduct annual SAR exercises at regional level |  | (*) - 2015 | States | Valid |
|  | - Monitor implementation progress |  | 2012 - 2018 | GREPECAS | Valid |
| Relation-ship with GPIs | Not applicable |  |  |  |  |

(*) Indicates that the task has been started before the date contemplated in this planning.