| REGIONAL PERFORMANCE OBJECTIVE: SAM SM/01 SAFETY MANAGEMENT |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Benefits |  |  |  |  |  |
| Safety |  | - Strengthens safety |  |  |  |
| Metrics |  |  |  |  |  |
| - Number of States that have implemented SSPs - Number of international airports that have implemented SMS - Number of ATS services that have implemented SMS. |  |  |  |  |  |
| 2012 - 2018 Strategy |  |  |  |  |  |
| ATM OC COMPONENTS | TASKS |  | PERIOD | RESPONSIBILITY | STATUS |
| AOM AUO | - Development of associated standards and procedures to comply with safety surveillance requirements at the air navigation services |  | 2013-2015 | Regional Project | Valid |
|  | - Assist in the strengthening of the civil aviation administrations, to comply with the air navigation services surveillance tasks |  | 2014-2018 | Regional Project | Valid |
|  | - Follow up of the RASG-PA work programme, as a reference for the activities of the region. |  | (*) – 2018+ | States | Valid |
|  | - Prepare guidelines for the implementation of SMS in ATS services and international aerodromes. |  | (*) - 2012 | Regional Project | Valid |
|  | - Assist in the implementation of State safety programmes (SSPs). |  | 2012 | Regional Office | Valid |
|  | - Develop regional safety databases |  | 2012 - 2013 | Regional Project | Valid |
|  | - Formulate guidelines for the protection of safety data |  | 2012 - 2014 | Regional Project | Valid |
|  | - Effective implementation of SMS in ATS and international airports. |  | (*) - 2014 | States | Valid |
|  | - Develop and implement a training plan concerning the development and application of a safety case |  | (*) - 2012 | States | Valid |
|  | - Assess and assist States in the effective implementation of actions, in order to improve safety. |  | (*) - 2018 | GREPECAS | Valid |
|  | - Continuous monitoring and periodical assessment of safety efficacy and SMS and SSP implementation |  | 2012 - 2018 | GREPECAS | Valid |
| Relation-ship with GPIs | The systemic safety approach is holistic, applied to the whole ANS system. |  |  |  |  |

(*)  Indicates that the task has been started before the date contemplated in this planning.